## Main Information
TYNDP Annex A |  |  |  | Main Information - Page 1
Type | Code | Name | Country |  | Promoter | Status | PCI 2nd List | PCI Code | PCI Priority Corridors | Commissioning Year | Is Part of a NDP | NDP Number | NDP Name Or Reason for non-NDP inclusion | CBCA Decision | CBCA Decision Date
Storage Facility | UGS-F-259 | Bordolano first phase | Italy |  | STOGIT | FID | No |  |  | 2016 | Yes | NA | Snam Rete Gas TYNDP 2016-2025
Pipeline including CS | TRA-F-029 | Romania-Bulgaria Interconnection (EEPR-2009-INTg-RO-BG) | Romania |  | SNTGN Transgaz SA | FID | No |  |  | 2016 | No | N/A | The project is in the final stage of the construction works and will be comissioned during 2016.
Pipeline including CS | TRA-F-1047 | Exit Capacity Budince | Slovakia |  | eustream, a.s. | FID | No |  |  | 2016 | Yes | 11.a.i. | Slovak national development plan 2015-2024
Pipeline including CS | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | Croatia |  | Plinacro Ltd | FID | Yes | 6.24.3 | NSIE | 2017 | Yes | 5.1, | 2017-2026
Pipeline including CS | TRA-F-241 | MONACO section phase I (Burghausen-Finsing) | Germany |  | bayernets GmbH | FID | No |  |  | 2017 | Yes | 030-02 | Netzentwicklungsplan (NEP) | Yes | 2014-04-10
Pipeline including CS | TRA-F-291 | NOWAL - Nord West Anbindungsleitung | Germany |  | GASCADE Gastransport GmbH | FID | No |  |  | 2017 | Yes | 083-07, 409-01, ... | NOWAL
Pipeline including CS | TRA-F-768 | Extension Receiving Terminal Greifswald | Germany |  | NEL Gastransport, Fluxys Deutschland, Gasunie Deutschland | FID | No |  |  | 2017 | Yes | 408-01 | Entwurf Netzentwicklungsplan 2016
LNG Terminal | LNG-F-147 | Revythoussa (2nd upgrade) | Greece |  | DESFA S.A. | FID | No |  |  | 2017 | Yes | 2.2.1.5 | Development Plan NNGS 2015-2024
Pipeline including CS | TRA-F-137 | Interconnection Bulgaria - Serbia | Bulgaria |  | Ministry of Energy | FID | Yes | 6.10. | NSIE | 2018 | Yes | Sectin 5.2 (5.2.3) | 2016-2025 Ten-year network development plan of BTG
Pipeline including CS | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | Bulgaria |  | ICGB a.d. | FID | Yes | 6.8.1 | NSIE | 2018 | Yes | not applicable | Included in both the TYNDPs of Greece and Bulgaria
Pipeline including CS | TRA-F-43 | Val de Saône project | France |  | GRTgaz | FID | Yes | 5.7 | NSIW | 2018 | Yes | na | GRTgaz PDD 2015
Pipeline including CS | TRA-F-45 | Reverse capacity from CH to FR at Oltingue | France |  | GRTgaz | FID | No |  |  | 2018 | Yes | na | GRTgaz PDD 2015
Pipeline including CS | TRA-F-331 | Gascogne Midi | France |  | TIGF - GRTgaz | FID | Yes | 5.7.2 | NSIW | 2018 | Yes | No number | 2015 NDP of GRTgaz and TIGF
Pipeline including CS | TRA-F-391 | Gascogne-Midi : adaptation of stations in Cruzy and St Martin | France |  | GRTgaz | FID | Yes | 5.7 | NSIW | 2018 | Yes | na | GRTgaz PDD 2015
Pipeline including CS | TRA-F-208 | Reverse Flow TENP Germany | Germany |  | Fluxys TENP GmbH & Open Grid Europe GmbH | FID | Yes | 5.10 | NSIW | 2018 | Yes | 305-01 | Netzentwicklungsplan 2015 | Yes | 2014-05-12
Pipeline including CS | TRA-F-337 | CS Rothenstadt | Germany |  | GRTgaz Deutschland GmbH | FID | No |  |  | 2018 | Yes | 026-06 | Netzentwicklungsplan Gas 2015
Pipeline including CS | TRA-F-343 | Pipeline project "Schwandorf-Finsing" | Germany |  | Open Grid Europe GmbH | FID | No |  |  | 2018 | Yes | 024-04a and 028-04a | Netzentwicklungsplan 2015 (German NDP 2015)
Pipeline including CS | TRA-F-344 | Compressor station "Herbstein" | Germany |  | Open Grid Europe GmbH | FID | No |  |  | 2018 | Yes | 049-07 | Netzentwicklungsplan 2015 (German NDP 2015)
Pipeline including CS | TRA-F-345 | Compressor station "Werne" | Germany |  | Open Grid Europe GmbH | FID | No |  |  | 2018 | Yes | 040-05 | Netzentwicklungsplan 2015 (German NDP 2015)
Pipeline including CS | TRA-F-753 | West to East operation of the IP Waidhaus | Germany |  | GRTgaz Deutschland GmbH | FID | No |  |  | 2018 | Yes | 026-06 | Netzentwicklungsplan Gas 2015
Pipeline including CS | TRA-F-214 | Support to the North West market and bidirectional cross-border flows | Italy |  | Snam Rete Gas S.p.A. | FID | Yes | 5.11 | NSIW | 2018 | Yes | TRA-F-214(into text) | Snam Rete Gas TYNDP 2016-2025
Pipeline including CS | TRA-F-230 | Reverse Flow Transitgas Switzerland | Switzerland |  | FluxSwiss | FID | No |  |  | 2018 | No | N/A | No public NDP.
Pipeline including CS | TRA-F-221 | TANAP - Trans Anatolian Natural Gas Pipeline Project | Turkey |  | SOCAR (The State Oil Company of the Azerbaijan Republic) | FID | Yes | 7.1.1 | SGC | 2018 | No | N/A | TANAP Project is not directly constructed by Turkish Government whereas it is executed by a private legal entity. However, there are referrals to TANAP Project in National Development Plans of Turkey since TANAP has a strategic importance.
LNG Terminal | LNG-F-229 | Zeebrugge LNG Terminal - 5th Tank & 2nd Jetty | Belgium |  | Fluxys LNG | FID | No |  |  | 2019 | Yes | 5th Tank & 2nd Jetty | Fluxys Belgium NDP 2016
Pipeline including CS | TRA-F-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Rogatec) | Croatia |  | Plinacro Ltd | FID | Yes | 6.26.1 | NSIE | 2019 | Yes | 1.24, 1.25 | 2017-2026
Pipeline including CS | TRA-F-937 | Nord Stream 2 | Germany |  | Nord Stream 2 AG | FID | No |  |  | 2019 | No | N/A | Nord Stream 2 is to be included in the German Net Development Plan 2016 (currently under discussion).
Pipeline including CS | TRA-F-051 | Trans Adriatic Pipeline | Greece |  | Trans Adriatic Pipeline AG | FID | Yes | 7.1.3 | SGC | 2019 | No | N/A | The TAP project is being developed on a stand-alone basis, independent from the national transmission systems of Greece, Albania and Italy.
Storage Facility | UGS-F-1045 | Bordolano Second phase | Italy |  | STOGIT S.p.A. | FID | No |  |  | 2019 | Yes | NA | Snam Rete Gas TYNDP 2016-2025
LNG Terminal | LNG-F-183 | Tenerife LNG Terminal | Spain |  | Gascan | FID | No |  |  | 2020 | Yes | No code in the NDP | Planta de regasificacion de Tenerife
LNG Terminal | LNG-F-163 | Gran Canaria LNG Terminal | Spain |  | Gascan | FID | No |  |  | 2021 | Yes | No code in the NDP | Planta de regasificación de Gran Canaria
Pipeline including CS | TRA-F-1028 | Albania - Kosovo Gas Pipeline | Albania |  | Min. of Energy and Industry of AL & Min. of Economic Development of KO | FID | No |  |  | 2022 | Yes | Energy chapter | NDP of AL is in final stage for approval.
Storage Facility | UGS-F-260 | System Enhancements - Stogit - on-shore gas fields | Italy |  | STOGIT | FID | No |  |  | 2026 | Yes | NA | Snam Rete Gas TYNDP 2016-2025
Pipeline including CS | TRA-F-017 | System Enhancements - Eustream | Slovakia |  | eustream, a.s. | FID | No |  |  | 2026 | Yes | 10.3. | National Development Plan 2016-2025
LNG Terminal | LNG-F-178 | Musel LNG terminal | Spain |  | Enagás Transporte, S.A.U. | FID | No |  |  | 2026 | Yes | No code in the NDP | planta de regasificación de El Musel
Pipeline including CS | TRA-F-025 | Industrial Emissions Directive (IPPC) - FID | United Kingdom |  | National Grid Gas plc | FID | No |  |  | Unknown | Yes | Section 5.2 | Gas Ten Year Statement 2015
Pipeline including CS | TRA-N-814 | Upgrade IP Deutschneudorf and Lasow | Germany |  | ONTRAS Gastransport GmbH | Advanced Non-FID | No |  |  | 2016 | No | N/A | The project is not yet part of the recent German NDP 2016. The German NRA by decree of 11th December 2015 had ordered the German TSOs to only modell a 42 % coverage of the expected additional national demand from North East in the scenario Q2 including Nord Stream 2, but no further flows at IPs.
Storage Facility | UGS-N-235 | Nuovi Sviluppi Edison Stoccaggio | Italy |  | Edison Stoccaggio S.p.A | Advanced Non-FID | No |  |  | 2017 | Yes | No Number | National Energy Strategy
LNG Terminal | LNG-N-082 | LNG terminal Krk | Croatia |  | LNG Hrvatska d.o.o. za poslovanje ukapljenim prirodnim plinom | Advanced Non-FID | Yes | 6.5.1. | NSIE | 2018 | Yes | 6.5.1. | Desetogodišnji plan razvoja plinskog...
Pipeline including CS | TRA-N-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | Croatia |  | Plinacro Ltd | Advanced Non-FID | No |  | NSIE | 2018 | Yes | 1.17 | 2017-2026
Pipeline including CS | TRA-N-429 | Adaptation L- gas - H-gas | France |  | GRTgaz, GRDF and Storengy | Advanced Non-FID | No |  | NSIW | 2018 | Yes | na | GRTgaz PDD 2015
LNG Terminal | LNG-N-062 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | Greece |  | Gastrade S.A. | Advanced Non-FID | Yes | 6.9.1 | NSIE | 2018 | No | N/A | The Project is not included in the NDP because it is an Independent Natural Gas System and therefore the NTSO is not obliged to include it in the NDP because it is not the Project's promoter and/or operator.
Pipeline including CS | TRA-N-063 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Greece |  | Gastrade S.A. | Advanced Non-FID | Yes | 6.9.1 | NSIE | 2018 | No | N/A | The Project is not included in the NDP because it is an Independent Natural Gas System and therefore the NTSO is not obliged to include it in the NDP because it is not the Project's promoter and/or operator.
Pipeline including CS | TRA-N-361 | GCA 2015/08: Entry/Exit Murfeld | Austria |  | GAS CONNECT AUSTRIA GmbH | Advanced Non-FID | Yes | 6.26.4 | SGC | 2019 | Yes | GCA 2015/08 | NDP 2016 - 2025
Pipeline including CS | TRA-N-066 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Croatia |  | Plinacro Ltd | Advanced Non-FID | No |  | NSIE | 2019 | Yes | 1.13 | 2017-2026
Pipeline including CS | TRA-N-136 | Poland-Czech Republic Interconnection (CZ) | Czechia |  | NET4GAS, s.r.o. | Advanced Non-FID | Yes | 6.1.1, 6.1.12 | NSIE | 2019 | Yes | TRA-N-136 | NDP 2016-2025 | Yes | 2014-10-17
Pipeline including CS | TRA-N-752 | Capacity4Gas (C4G) – DE/CZ | Czechia |  | NET4GAS, s.r.o. | Advanced Non-FID | No |  |  | 2019 | Yes | TRA-N-752 | NDP 2017-2026 (new project)
Pipeline including CS | TRA-N-918 | Capacity4Gas (C4G) – CZ/SK | Czechia |  | NET4GAS, s.r.o. | Advanced Non-FID | No |  |  | 2019 | Yes | TRA-N-918 | NDP 2017-2026 (new project)
Pipeline including CS | TRA-N-895 | Balticconnector | Estonia |  | Elering AS | Advanced Non-FID | Yes | 8.1.1 | BEMIP | 2019 | Yes | 3.2 | EESTI GAASIÜLEKANDEVÕRGU ARENGUKAVA 2016‐2025 | Yes | 2016-04-22
Pipeline including CS | TRA-N-915 | Enhancement of Estonia-Latvia interconnection | Estonia |  | Elering AS | Advanced Non-FID | Yes | 8.2.2 | BEMIP | 2019 | Yes | 3.2 | EESTI GAASIÜLEKANDEVÕRGU ARENGUKAVA 2016‐2025 | Yes | 2016-04-22
Pipeline including CS | TRA-N-928 | Balticconnector Finnish part | Finland |  | Baltic Connector Oy | Advanced Non-FID | Yes | 8.1.1 | BEMIP | 2019 | No | N/A | The national Natural Gas Market legislation does not set system operators any obligation to draw up and publish a NDP | Yes | 2016-04-22
Pipeline including CS | TRA-N-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | Germany |  | GASCADE Gastransport GmbH | Advanced Non-FID | No |  |  | 2019 | No | N/A | Capacities for this project will ultimately be allocated by auctioning in 2017. At the moment, it is assumed that these auction results will be included as an identified capacity requirement in the process for the NDP 2018. - Parts are included (Vierow 412-01) (www.more-capacity.eu/en)
Pipeline including CS | TRA-N-012 | GALSI Pipeline Project | Italy |  | Galsi S.p.A. | Advanced Non-FID | Yes | 5.20 | NSIW | 2019 | Yes | n.a. | SNAM NDP 2015 (page 61)
Storage Facility | UGS-N-237 | Palazzo Moroni | Italy |  | Edison Stoccaggio S.p.A | Advanced Non-FID | No |  | NSIE | 2019 | Yes | No Number | National Energy Strategy
Storage Facility | UGS-N-374 | Enhancement of Incukalns UGS | Latvia |  | JSC "Latvijas Gaze" | Advanced Non-FID | Yes | 8.2.4 | BEMIP | 2019 | No | N/A | National developmeny plan for 2014-2020 does not specify particular projects, however, under Activity "Energy efficiency and energy production" item "7. Development of enery infrastructure networks" may include the project. | Yes | 2014-04-30
LNG Terminal | LNG-N-912 | Skulte LNG | Latvia |  | AS Skulte LNG Terminal | Advanced Non-FID | No |  | BEMIP | 2019 | No | N/A | Project will be included in NDP at beginning of June 2016 when a special meeting of the Council for Large Investment Projects of Stretegic Importance will be held. The meeting will be leaded by Prime Minister.
Pipeline including CS | TRA-N-341 | Gas Interconnection Poland-Lithuania (GIPL) (Lithuania's section) | Lithuania |  | AB Amber Grid | Advanced Non-FID | Yes | 8.5 | BEMIP | 2019 | Yes | n/a | Ten-year Network Development Plan 2014-2023 | Yes | 2014-08-11
Pipeline including CS | TRA-N-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | Poland |  | GAZ-SYSTEM S.A. | Advanced Non-FID | Yes | 8.5 | BEMIP | 2019 | Yes | N/A | Network Development Plan 2016-2025 | Yes | 2014-08-11
Pipeline including CS | TRA-N-247 | North - South Gas Corridor in Western Poland | Poland |  | GAZ-SYSTEM S.A. | Advanced Non-FID | Yes | 6.1.2 | NSIE | 2019 | Yes | N/A | Network Development Plan 2016-2025
Pipeline including CS | TRA-N-273 | Poland - Czech Republic interconnection (PL section) | Poland |  | GAZ-SYSTEM S.A. | Advanced Non-FID | Yes | 6.1.1, 6.1.2 | NSIE | 2019 | Yes | N/A | Network Development Plan 2016-2025 | Yes | 2014-06-24
Pipeline including CS | TRA-N-275 | Poland - Slovakia interconnection (PL section) | Poland |  | GAZ-SYSTEM S.A. | Advanced Non-FID | Yes | 6.2.1, 6.2.3 | NSIE | 2019 | Yes | N/A | Network Development Plan 2016-2025 | Yes | 2014-11-28
Storage Facility | UGS-N-233 | Depomures | Romania |  | Engie Romania SA | Advanced Non-FID | Yes | 6.20.4 | NSIE | 2019 | No | N/A | As far as we are aware, currently there is no comprehrensive system wide national development plan, only one regarding the gas transmission infrastructure put together by the TSO. Nevertheless, the operator submitted a 5-year investment plan to Romanian NRA in 2015, which is updated anually.
Pipeline including CS | TRA-N-190 | Poland - Slovakia interconnection | Slovakia |  | eustream, a.s. | Advanced Non-FID | Yes | 6.2.1. | NSIE | 2019 | Yes | 10.1.2.-PL-SK | National Development Plan 2016-2025 | Yes | 2014-11-28
Pipeline including CS | TRA-N-902 | Capacity increase at IP Lanžhot entry | Slovakia |  | eustream, a.s. | Advanced Non-FID | No |  | NSIE | 2019 | Yes | 10.1.2. Lanžhot | National Development Plan 2016-2025
Pipeline including CS | TRA-N-021 | Bidirectional Austrian-Czech Interconnector (BACI, formerly LBL project) | Austria |  | GAS CONNECT AUSTRIA GmbH | Advanced Non-FID | Yes | 6.4 | NSIE | 2020 | Yes | GCA 2015/01a | NDP 2016-2025
Pipeline including CS | TRA-N-423 | GCA Mosonmagyaróvár | Austria |  | GAS CONNECT AUSTRIA GmbH | Advanced Non-FID | Yes | 6.24.3 | SGC | 2020 | Yes | GCA 2015/05 | NDP 2016 - 2025
Pipeline including CS | TRA-N-801 | Břeclav-Baumgarten Interconnection (BBI) AT | Austria |  | GAS CONNECT AUSTRIA GmbH | Advanced Non-FID | No |  |  | 2020 | No | N/A | The BBI project is a new project and will be part of the NDP 2017-2026.
Pipeline including CS | TRA-N-500 | L/H Conversion | Belgium |  | Fluxys Belgium | Advanced Non-FID | No |  | NSIW | 2020 | Yes | L/H Conversion | Fluxys Belgium NDP 2016
Pipeline including CS | TRA-N-075 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Croatia |  | Plinacro Ltd | Advanced Non-FID | Yes | 6.5.2. | NSIE | 2020 | Yes | 1.18, 1.19, 1.20 | 2017-2026
Pipeline including CS | TRA-N-133 | Bidirectional Austrian Czech Interconnection (BACI) | Czechia |  | NET4GAS, s.r.o. | Advanced Non-FID | Yes | 6.4 | NSIE | 2020 | Yes | TRA-N-133 | NDP 2016-2025
Pipeline including CS | TRA-N-919 | Capacity4Gas (C4G) – CZ/AT | Czechia |  | NET4GAS, s.r.o. | Advanced Non-FID | No |  |  | 2020 | Yes | TRA-N-919 | NDP 2017-2026 (new project)
LNG Terminal | LNG-N-079 | Paldiski LNG Terminal | Estonia |  | Balti Gaas plc | Advanced Non-FID | Yes | 8.1.2.2 | BEMIP | 2020 | No | N/A | There is no such thing as National Development Plan in Estonia. The project is mentioned in the development plan of transmission grid in Estonia, but only on an informative level.
Pipeline including CS | TRA-N-807 | Expansion NEL | Germany |  | Gasunie Deutschland, NEL Gastransport, Fluxys Deutschland | Advanced Non-FID | No |  |  | 2020 | Yes | 110-08 | Draft Netzentwicklungsplan Gas 2016
Pipeline including CS | TRA-N-010 | Poseidon Pipeline | Greece |  | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced Non-FID | Yes | 7.1.4 | SGC | 2020 | No | N/A | Poseidon pipeline is mentioned in the latest Italian NDP in ANNEX 4 (page 76) while in the Greek NDP there is no reference to the project, since it constitutes an Independent Natural Gas System (INGS).
Pipeline including CS | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | Slovenia |  | Plinovodi d.o.o. | Advanced Non-FID | Yes | 6.26.6 | NSIE | 2020 | Yes | C12 | TYNDP for the period 2016-2025
LNG Terminal | LNG-N-032 | Project GO4LNG LNG terminal Gothenburg | Sweden |  | Swedegas AB | Advanced Non-FID | Yes | 8.6 | BEMIP | 2020 | No | N/A | Not applicable for Sweden. There is no NDP. | Yes | 2015-10-01
Pipeline including CS | TRA-N-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | Croatia |  | Plinacro Ltd | Advanced Non-FID | No |  | NSIE | 2021 | Yes | 1.3 | 2017-2026
Pipeline including CS | TRA-N-808 | Transport of gas volumes to the Netherlands | Germany |  | Gasunie Deutschland Technical Services GmbH | Advanced Non-FID | No |  |  | 2021 | No | N/A | Decision of BNetzA (Tenor 3d) regarding the NEP 2016: The H-Gas balance related to variant Q2 of the NEP 2016 shows an add. demand of 42% in the region "North-East". Any other add. demands which are not covered by binding bookings are not taken into account on IPs (neither entry nor exit).
LNG Terminal | LNG-N-198 | Porto Empedocle LNG | Italy |  | Nuove Energie S.r.l. | Advanced Non-FID | No |  | NSIW | 2021 | Yes | n.a. | Piano decennale di sviluppo SNAM 2015-2024
Pipeline including CS | TRA-N-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | Portugal |  | REN-Gasodutos, S.A. | Advanced Non-FID | Yes | 5.4 | NSIW | 2021 | Yes | - | PDIRGN 2015
Pipeline including CS | TRA-N-320 | Carregado Compressor Station | Portugal |  | REN-Gasodutos, S.A. | Advanced Non-FID | No |  |  | 2021 | Yes | - | PDIRGN 2015
Pipeline including CS | TRA-N-161 | South Transit East Pyrenees (STEP) - ENAGAS | Spain |  | Enagás Transporte, S.A.U. | Advanced Non-FID | Yes | 5.5 | NSIW | 2021 | Yes | No code in the NDP | Conexión internacional con Francia por Cataluña
Pipeline including CS | TRA-N-068 | Ionian Adriatic Pipeline | Croatia |  | Plinacro Ltd | Advanced Non-FID | No |  | NSIE, SGC | 2022 | Yes | 1.1, 1.2,1.4,1.5,5.4 | 2017-2026
Pipeline including CS | TRA-N-252 | South Transit East Pyrenees (STEP) - TIGF | France |  | TIGF | Advanced Non-FID | Yes | 5.5 | NSIW | 2022 | Yes | No number | 2015 TIGF NDP
Pipeline including CS | TRA-N-974 | LARINO - RECANATI Adriatic coast backbone | Italy |  | Società Gasdotti Italia | Advanced Non-FID | No |  | SGC | 2022 | Yes | Not applicable | There is no NDP currently in force
Pipeline including CS | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | Hungary |  | Magyar Gáz Tranzit Zrt. | Less-Advanced Non-FID | Yes | TRN-A-524 | SGC | 2017 | No | N/A | MGT submitted this project to FGSZ and proposed to forward for approval to Hungarian Energy Office (MEKH). FGSZ is responsible for setup the Hungarian TYNDP and for submit it to MEKH. FGSZ put this project to the documentation of Development Plan 2015 but dosn't propose it for approval.
Pipeline including CS | TRA-N-636 | Development of Transmission Capacity at Slovak-Hungarian interconnector | Hungary |  | Magyar Gáz Tranzit Zrt. | Less-Advanced Non-FID | Yes | TRA-N-636 | SGC | 2017 | No | N/A | MGT submitted this project to FGSZ and proposed to forward for approval to Hungarian Energy Office (MEKH). FGSZ is responsible for setup the Hungarian TYNDP and for submit it to MEKH. FGSZ put this project to the documentation of Development Plan 2015 but dosn't propose it for approval.
Pipeline including CS | TRA-N-645 | HU-UA Interconnector (Ukrainian section) | Ukraine |  | PJSC Ukrtransgaz | Less-Advanced Non-FID | No |  |  | 2017 | Yes | N/A | Ten-Year Network Development Plan of UTG
Pipeline including CS | TRA-N-660 | Gas to the West | United Kingdom |  | West Transmission Limited | Less-Advanced Non-FID | No |  |  | 2017 | Yes | n.a. | Northern Ireland Gas Capacity Statement
Pipeline including CS | TRA-N-954 | TAG Reverse Flow | Austria |  | Trans Austria Gasleitung GmbH | Less-Advanced Non-FID | No |  |  | 2018 | Yes | TAG 2017-01 | Coordinated Network Development Plan 2017-2026
Pipeline including CS | TRA-N-379 | ​A project for the construction of a gas pipeline BG-RO | Bulgaria |  | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | 6.8.4. | NSIE | 2018 | Yes | Section 5 (5.1.3. ) | 2016-2025 Ten-year network development plan of BTG
Pipeline including CS | TRA-N-545 | Infrastructure gas pipeline Skopje - Tetovo - Gostivar - Albanian border | former Yugoslav Republic of Macedonia |  | GA-MA joint stock company Skopje | Less-Advanced Non-FID | No |  | SGC | 2018 | No | N/A | The project is part of GA-MA development plan and is submitted to the Ministry of economy which is responsible for energy matters.
Pipeline including CS | TRA-N-357 | NTS developments in North-East Romania | Romania |  | SNTGN Transgaz SA | Less-Advanced Non-FID | No |  |  | 2018 | Yes | 7.4 | Developement Plan for the National GTS 2016 - 2025
Storage Facility | UGS-N-203 | Preesall Gas Storage | United Kingdom |  | Halite Energy Group Ltd | Less-Advanced Non-FID | No |  |  | 2018 | Yes | Preesall | National Grid Ten Year Statement
LNG Terminal | LNG-N-962 | Tallinn LNG | Estonia |  | Vopak E.O.S. AS / Vopak LNG Holdings B.V/ Port of Tallinn AS | Less-Advanced Non-FID | Yes | 8.1.2.3 | BEMIP | 2019 | No | N/A | Valid energy NDA ﴾ENMAK 2020﴿ foresees the diversification of energy supply via construction of LNG terminals ﴾p.18﴿. The construction of LNG infrastructure is on the list of foremost measures ﴾p.40﴿ and activities ﴾p.41﴿. As this NDA was adopted in 2009 no specific PCI projects could be listed.
Pipeline including CS | TRA-N-582 | Macedonian part of Tesla project | former Yugoslav Republic of Macedonia |  | GA-MA joint stock company Skopje | Less-Advanced Non-FID | Yes | TRA-N-582 |  | 2019 | No | N/A | This project is part of the development plan of GAMA and it is provided to the relevant Ministry of economy, which is responsible for energy matters.
Pipeline including CS | TRA-N-340 | VDS Wertingen | Germany |  | bayernets GmbH | Less-Advanced Non-FID | No |  |  | 2019 | Yes | 036-04 | Netzentwicklungsplan
Pipeline including CS | TRA-N-941 | Metering and Regulating station at Nea Messimvria | Greece |  | DESFA S.A. | Less-Advanced Non-FID | Yes | 7.1.6 | SGC | 2019 | Yes | 2.2.1.3 | Development Plan NNGS 2015-2024
Storage Facility | UGS-N-034 | Syderiai | Lithuania |  | JSC Lietuvos energija AB | Less-Advanced Non-FID | No |  | BEMIP | 2019 | No | N/A | NPD was prepared by public entities, which didnt include projects form third parties. Yet project is included in the National energy independancy strategy.
Pipeline including CS | TRA-N-139 | Interconnection of the NTS with the DTS and reverse flow at Isaccea | Romania |  | SNTGN Transgaz SA | Less-Advanced Non-FID | Yes | 6.15 | NSIE | 2019 | Yes | 7.3 | Developement Plan for the National GTS 2016 - 2025
Pipeline including CS | TRA-N-964 | New NTS developments for taking over gas from the Black Sea shore | Romania |  | SNTGN Transgaz SA | Less-Advanced Non-FID | No |  |  | 2019 | Yes | 7.6 | Development Plan for the National GTS 2016 - 2025
Pipeline including CS | TRA-N-365 | M6 Ajdovščina – Lucija | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | No |  |  | 2019 | Yes | A15 | TYNDP for the period 2016-2025
Pipeline including CS | TRA-N-561 | Poland-Ukraine Interconnector (Ukrainian section) | Ukraine |  | PJSC Ukrtransgaz | Less-Advanced Non-FID | No |  | NSIE | 2019 | Yes | N/A | Ten-Year Network Development Plan of UTG
LNG Terminal | LNG-N-328 | Eagle LNG and Pipeline | Albania |  | Burns Srl | Less-Advanced Non-FID | No |  |  | 2020 | Yes | Eagle LNG | Italy - Gas Grid NDP - Ministerial Decree 20.10.15
Pipeline including CS | TRA-N-140 | Interconnection Turkey-Bulgaria | Bulgaria |  | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | 7.4.2. | SGC | 2020 | Yes | ITB | 2016-2025 Ten-year network development plan of BTG
Pipeline including CS | TRA-N-298 | Rehabilitation, Modernization and Expansion of the NTS | Bulgaria |  | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | 6.8.2. | NSIE | 2020 | Yes | Section 5.5. | 2016-2025 Ten-year network development plan of BTG
Pipeline including CS | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | Croatia |  | Plinacro Ltd | Less-Advanced Non-FID | Yes | 6.24.3 | NSIE | 2020 | Yes | 5.2 and 5.3 | 2017-2026
LNG Terminal | LNG-N-225 | Montoir LNG Terminal Expansion | France |  | Elengy | Less-Advanced Non-FID | No |  | NSIW | 2020 | Yes | Montoir Extension | GRTgaz Ten Year Development plan 2015-2024
LNG Terminal | LNG-N-227 | Fos Cavaou LNG Terminal Expansion | France |  | Fosmax LNG | Less-Advanced Non-FID | No |  | NSIW | 2020 | Yes | Fos Cavaou Extension | GRTgaz Ten Year Development plan 2015-2024
Pipeline including CS | TRA-N-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Germany |  | Gastransport Nord GmbH | Less-Advanced Non-FID | No |  |  | 2020 | Yes | 432-01 | Netzentwicklungsplan Entwurf 2016
Pipeline including CS | TRA-N-951 | Embedding CS Folmhusen in H-Gas | Germany |  | Gasunie Deutschland Transport Services GmbH | Less-Advanced Non-FID | No |  |  | 2020 | Yes | 300-02 | Draft Netzentwicklungsplan Gas 2016
Pipeline including CS | TRA-N-128 | Compressor Station Kipi | Greece |  | DESFA S.A. | Less-Advanced Non-FID | Yes | 6.9.3 and 7.4.1 | SGC | 2020 | Yes | 2.2.1.3 | Development Plan NNGS 2015-2024
Pipeline including CS | TRA-N-330 | EastMed Pipeline | Greece |  | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Less-Advanced Non-FID | Yes | 7.3.1 | SGC | 2020 | No | N/A | EastMed pipeline is not included in the Greek NDP, as the project is considered an Indipendent Natural gas System. In Cyprus there is no NND as the country does not have any gas TSO.
Pipeline including CS | TRA-N-631 | Greek part of Tesla project | Greece |  | DESFA S.A. | Less-Advanced Non-FID | Yes | 6.25.2 | NSIE | 2020 | No | N/A | The NDP 2016-2025, (in consultation) presently refers to this project as a second stage of the M/R station installation that will enable the flow from TAP into the Greek Transmission System (TRA-N-941). At that second stage the Compressor station will also enable the flow from the Greek TS to TAP.
Pipeline including CS | TRA-N-940 | Metering and Regulating station at Komotini | Greece |  | DESFA S.A. | Less-Advanced Non-FID | Yes | 7.1.6 | SGC | 2020 | Yes | 2.2.1.3 | Development Plan NNGS 2015-2024
Pipeline including CS | TRA-N-957 | Metering Station at Komotini to IGB | Greece |  | DESFA S.A. | Less-Advanced Non-FID | No |  | NSIE | 2020 | No | N/A | This project is included in the 10-year Development Study. The D. S. includes projects which are likely to be implemented but are not yet part of the compulsory Projects.
Pipeline including CS | TRA-N-967 | Nea-Messimvria to FYROM pipeline | Greece |  | DESFA S.A. | Less-Advanced Non-FID | No |  | NSIE | 2020 | No | N/A | The Project is included in the 10-year Development Study. The D. S. includes projects which are likely to be implemented but are not yet part of the compulsory Projects.
Pipeline including CS | TRA-N-1090 | Metering and Regulating Station at Alexandroupoli | Greece |  | DESFA S.A. | Less-Advanced Non-FID | No |  | NSIE | 2020 | No | N/A | This project is not included in the National Development Plan because no application has been made, by the promoter of the LNG terminal in Northern Greece, for the connection of this project to the Greek gas transmission system.
Pipeline including CS | TRA-N-286 | Romanian-Hungarian reverse flow Hungarian section 1st stage | Hungary |  | FGSZ Ltd. | Less-Advanced Non-FID | Yes | 6.24.1 | NSIE | 2020 | Yes | 12.6.1. | Hungarian TYNDP 2015 | Yes | 2016-10-06
Pipeline including CS | TRA-N-325 | Slovenian-Hungarian interconnector | Hungary |  | FGSZ Ltd. | Less-Advanced Non-FID | Yes | 6.23 | NSIE | 2020 | Yes | 12.12.1.-12.12.2 | Hungarien TYNDP 2015
Pipeline including CS | TRA-N-585 | Hungarian section of Tesla project | Hungary |  | FGSZ Ltd. | Less-Advanced Non-FID | Yes | 6.25.2. | NSIE | 2020 | Yes | 12.15.1. - 12.15.2. | Hungarian TYNDP 2015
Pipeline including CS | TRA-N-586 | HU-UA reverse flow | Hungary |  | FGSZ Ltd. | Less-Advanced Non-FID | No |  |  | 2020 | Yes | 12.17. | Hungarian TYNDP 2015
Pipeline including CS | TRA-N-382 | Enhancement of Latvia-Lithuania interconnection (Latvian part) | Latvia |  | JSC "Latvijas Gaze" | Less-Advanced Non-FID | Yes | 8.2.1 | BEMIP | 2020 | No | N/A | National Development Plan for 2014-2020 does not specify particular projects. Under activity "Energy efficiency and energy production" title "7.Development of energy infrastructure networks" may include project of enhancement of Latvia-Lithuania interconnection
Pipeline including CS | TRA-N-342 | Enhancement of Latvia-Lithuania interconnection (Lithuania's part) | Lithuania |  | AB Amber Grid | Less-Advanced Non-FID | Yes | 8.2.1 | BEMIP | 2020 | Yes | n/a | Ten-year Network Development Plan 2014-2023
LNG Terminal | LNG-N-050 | Gate terminal phase 3 | Netherlands |  | Gate | Less-Advanced Non-FID | No |  |  | 2020 | No | N/A | It is not known whether this project has to be part of a National Development Plan, according to the promoter indications.
Pipeline including CS | TRA-N-191 | Blending | Netherlands |  | Gasunie Transport Services B.V. | Less-Advanced Non-FID | No |  |  | 2020 | Yes | n.a. | Additional quality conversion
Pipeline including CS | TRA-N-192 | Entry capacity expansion GATE terminal | Netherlands |  | Gasunie Transport Services B.V. | Less-Advanced Non-FID | No |  | NSIW | 2020 | Yes | n.a. | Exp. entry cap. due to add. supply GATE Terminal
Pipeline including CS | TRA-N-882 | H-gas conversion of L-gas export border points | Netherlands |  | Gasunie Transport Services B.V. | Less-Advanced Non-FID | No |  |  | 2020 | No | N/A | The project idea was mentioned in the Netwerk Ontwikkeling Plan 2015 (NOP) as a topic for cross border cooperation. Initially, measures at Tegelen, Winterswijk en Zevenaar were proposed. However, after discussion with the German TSO's, the project scope was changed.
LNG Terminal | LNG-N-272 | Upgrade of LNG terminal in Świnoujście | Poland |  | GAZ-SYSTEM S.A. | Less-Advanced Non-FID | Yes | 8.7 | BEMIP | 2020 | Yes | N/A | Network Development Plan 2016-2025
Pipeline including CS | TRA-N-621 | Poland - Ukraine Gas interconnection (PL section) | Poland |  | GAZ-SYSTEM S.A. | Less-Advanced Non-FID | No |  | NSIE | 2020 | Yes | N/A | Network Development Plan 2016-2025
LNG Terminal | LNG-N-947 | FSRU Polish Baltic Sea Coast | Poland |  | GAZ-SYSTEM S.A. | Less-Advanced Non-FID | No |  | BEMIP | 2020 | No | N/A | N/A. This is a new project
Pipeline including CS | TRA-N-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT Corridor) | Romania |  | SNTGN Transgaz S.A. | Less-Advanced Non-FID | Yes | Stage I: 6.24.2 Stage II: 6.24.7 | NSIE | 2020 | Yes | 7.1 | Development Plan for the National GTS 2016-2025 | Yes | 2015-10-06
Pipeline including CS | TRA-N-362 | Development on the Romanian territory of the Southern Transmission Corridor | Romania |  | SNTGN Transgaz SA | Less-Advanced Non-FID | Yes | 6.24.8 | NSIE | 2020 | Yes | 7.2 | Development Plan for the National GTS 2016-2025
Pipeline including CS | TRA-N-094 | CS Kidričevo, 2nd phase of upgrade | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | Yes | 6.26.2 | NSIE | 2020 | Yes | C5 | TYNDP for the period 2016-2025
Pipeline including CS | TRA-N-108 | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | No |  |  | 2020 | Yes | C2 | TYNDP for the period 2016-2025
Pipeline including CS | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | Yes | 6.23 | NSIE | 2020 | Yes | C3 | TYNDP for the period 2016-2025
Pipeline including CS | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak) | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | Yes | 6.26.5 | NSIE | 2020 | Yes | C4 | TYNDP for the period 2016-2025
LNG Terminal | LNG-N-296 | Mugardos LNG Terminal: 2nd Jetty | Spain |  | Reganosa | Less-Advanced Non-FID | No |  |  | 2020 | No | N/A | The last aproved Spanish NDP ended in 2016. The Royal Decree-Law 13/2012 cancel any award procedures of new regasification plants in Spain.
Pipeline including CS | TRA-N-950 | Guitiriz - Zamora pipeline | Spain |  | Reganosa | Less-Advanced Non-FID | No |  | NSIE, NSIW | 2020 | No | N/A | The last approved Spanish NDP ended in 2016. The Royal Decree-Law 13/2012 cancel the process of obtaining administrative authorization to transport pipelines and metering regulation stations even if they were included in this NDP.This Project was included in the NDP 2008-2016.
Pipeline including CS | TRA-N-829 | PCI 5.1.1 Physical Reverse Flow at Moffat interconnection point (IE/UK) | United Kingdom |  | GNI (UK) Limited | Less-Advanced Non-FID | Yes | PCI 5.1.1/Tran-N-059 | NSIW | 2020 | Yes | PCI 5.1.1 | GNI, Network Development Plan 2015
Pipeline including CS | TRA-N-1064 | Moffat Physical Reverse Flow | United Kingdom |  | National Grid Gas plc | Less-Advanced Non-FID | Yes | TRA-N-532 | NSIW | 2020 | No | N/A | This project is not part of our network development plan as we do not view it as a network development issue but rather we view it as a connection issue. It is for Gaslink to make the investment decision on this project.
Pipeline including CS | TRA-N-1138 | South Caucasus Pipeline Future Expansion - SCPFX | Azerbaijan |  | SOCAR Midstream Operations LLC | Less-Advanced Non-FID | Yes | 7.1 | SGC | 2021 | No | N/A | South Caucasus Pipeline Future Expansion project to be developed based on investment decision of consortium consisting from international companies and after approval of Azerbaijan Government, which consider energy infrastructure projects as an investment in projects containing strategic interest.
Pipeline including CS | TRA-N-851 | Southern Interconnection pipeline BiH/CRO | Bosnia Herzegovina |  | BH-GAS d.o.o. | Less-Advanced Non-FID | No |  |  | 2021 | Yes | PTG2 | SPP-Strategic plan and programme of FBiH
Pipeline including CS | TRA-N-654 | Eastring - Bulgaria | Bulgaria |  | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | 6.25.1 | NSIE | 2021 | Yes | Section 5.1(5.1,2) | 2016-2025 Ten-year network development plan of BTG
Pipeline including CS | TRA-N-965 | Interconnection Macedonia-Serbia | former Yugoslav Republic of Macedonia |  | MER JSC Skopje | Less-Advanced Non-FID | No |  |  | 2021 | Yes | N/A | Work Program of the Government of R. Macedonia
Pipeline including CS | TRA-N-976 | Interconnection Macedonia-Bulgaria | former Yugoslav Republic of Macedonia |  | MER JSC Skopje | Less-Advanced Non-FID | No |  |  | 2021 | Yes | N/A | Work Program of the Government of R.Macedonia
Pipeline including CS | TRA-N-980 | Interconnection Macedonia-Greece | former Yugoslav Republic of Macedonia |  | MER JSC Skopje | Less-Advanced Non-FID | No |  |  | 2021 | Yes | N/A | Work Program of the Government of R.Macedonia
Pipeline including CS | TRA-N-329 | ZEELINK | Germany |  | Open Grid Europe GmbH | Less-Advanced Non-FID | No |  |  | 2021 | Yes | 204-02a, 205-02a, .. | Netzentwicklungsplan 2015 (German NDP 2015)
Pipeline including CS | TRA-N-656 | Eastring - Hungary | Hungary |  | FGSZ Ltd. | Less-Advanced Non-FID | Yes | Not Defined yet | SGC | 2021 | Yes | 12.16 | Eastring pipeline
Pipeline including CS | TRA-N-831 | Vecsés-Városföld gas transit pipeline | Hungary |  | Magyar Gáz Tranzit Zrt. | Less-Advanced Non-FID | No |  | SGC | 2021 | No | N/A | This is a new project wich will be submitted to Hungarian Enegy Office (MEKH) for approval by MGT via FGSZ. (FGSZ is responsible for setup the Hungarian TYNDP) till end of 2016. MEKH's decision on National Development Plan 2016 will take effect in 2017 Q1 expectedly.
LNG Terminal | LNG-N-217 | Onshore LNG terminal in the Northern Adriatic | Italy |  | Gas Natural Rigassificazione Italia | Less-Advanced Non-FID | No |  | NSIE | 2021 | No | N/A | This project is not part of a National Development Plan as it is located on the Italian coast and there is no National Development Plan in Italy, which is the project host country.
Pipeline including CS | TRA-N-873 | Capacity expansion OSZ related to West Stream | Netherlands |  | Gasunie Transport Services B.V. | Less-Advanced Non-FID | No |  |  | 2021 | No | N/A | Expansion measures at Oude Statenzijl were already foreseen in the Netwerk Ontwikkeling Plan 2015 (NOP). Recently, the scope of these measures was expanded, related to the plans of Nord Stream 2 and West Stream
Pipeline including CS | TRA-N-655 | Eastring - Romania | Romania |  | SNTGN Transgaz SA | Less-Advanced Non-FID | Yes | 6.25.1 | NSIE | 2021 | No | N/A | For the moment, the project lacks sufficient descriptive elements in order for it to be included in the National Gas Transmission System Development Plan.
Pipeline including CS | TRA-N-628 | Eastring - Slovakia | Slovakia |  | Eastring B.V. | Less-Advanced Non-FID | Yes | 6.25.1 | NSIE | 2021 | Yes | 10.1.2. Eastring | National Development Plan 2016-2025
Pipeline including CS | TRA-N-092 | CS Ajdovščina, 1st phase of upgrade | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | No |  |  | 2021 | Yes | C1 | TYNDP for the period 2016-2025
Pipeline including CS | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Spain |  | Enagás Transporte, S.A.U. | Less-Advanced Non-FID | Yes | 5.4 | NSIW | 2021 | No | N/A | The project was not included in the last NDP that was published in 2008. The project was identified later on, and was selected as PCI by the European Commission in 2013 and in 2015. Additionally, this project is being considered in the High Level Group on Interconnections for South-West Europe.
Pipeline including CS | TRA-N-027 | Physical reverse flow from NI to GB and IE via SNIP pipeline | United Kingdom |  | Premier Transmission Limited | Less-Advanced Non-FID | Yes | 5.1.2 | NSIW | 2021 | Yes | n.a. | Northern Ireland Gas Capacity Statement
Storage Facility | UGS-N-294 | Islandmagee Gas Storage Facility | United Kingdom |  | Islandmagee Storage Limited | Less-Advanced Non-FID | Yes | 5.1.3 | NSIW | 2021 | Yes | n.a. | Northern Ireland Gas Capacity Statement
LNG Terminal | LNG-N-742 | Zeebrugge LNG Terminal - 3rd Jetty | Belgium |  | Fluxys LNG | Less-Advanced Non-FID | No |  | NSIW | 2022 | Yes | 3rd Jetty | Fluxys Belgium NDP 2016
Storage Facility | UGS-N-138 | UGS Chiren Expansion | Bulgaria |  | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | 6.20.2. | NSIE | 2022 | Yes | Section 5.3 (5.3.1) | 2016-2025 Ten-year network development plan of BTG
Pipeline including CS | TRA-N-592 | Looping CS Valchi Dol - Line valve Novi Iskar | Bulgaria |  | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | 6.25.4 | NSIE | 2022 | Yes | Section 5.1. (5.1.1) | 2016-2025 Ten-year network development plan of BTG
Pipeline including CS | TRA-N-593 | Varna-Oryahovo gas pipeline | Bulgaria |  | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | 6.25.4 | NSIE | 2022 | Yes | Section 5.1. (5.1.1) | 2016-2025 Ten-year network development plan of BTG
Pipeline including CS | TRA-N-594 | Construction of a Looping CS Provadia – Rupcha village | Bulgaria |  | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | 6.25.4 | NSIE | 2022 | Yes | Section 5.1. (5.1.1) | 2016-2025 Ten-year network development plan of BTG
Pipeline including CS | TRA-N-135 | Connection to Oberkappel | Czechia |  | NET4GAS, s.r.o. | Less-Advanced Non-FID | No |  | NSIE | 2022 | Yes | TRA-N-135 | NDP 2016-2025
Pipeline including CS | TRA-N-394 | Gassled - Danish upstream system | Denmark |  | Energinet.dk | Less-Advanced Non-FID | No |  | NSIW | 2022 | No | N/A | This is an upstream project from the North Sea (Norway) to a Danish North Sea Platform. The project is vital for the Baltic-Pipe project (gas pipeline between Denmark and Poland). The project will be included in future national plans in connection when possibly including the Baltic Pipe.
Pipeline including CS | TRA-N-428 | (Mirror) Baltic Pipe | Denmark |  | Energinet.dk | Less-Advanced Non-FID | Yes | 8.3 | BEMIP | 2022 | No | N/A | Presently a feasibility study for the Baltic Pipe is carried out in cooperation between Gaz-System (Polish TSO) and Energinet.dk (Danish TSO). This study will be finalized by end of 2016. Depending on the result of the study, the project will be included in the future national development plan.
Pipeline including CS | TRA-N-780 | Nybro-Interconnector PL-DK - reinforcement | Denmark |  | Energinet.dk | Less-Advanced Non-FID | No |  | BEMIP | 2022 | No | N/A | Presently a feasibility study for the Baltic Pipe is carried out in cooperation between Gaz-System (Polish TSO) and Energinet.dk. The study will be finalized by end of 2016. If the study recommends a capacity of Baltic Pipe well above 3 bcm/y , this reinforcement project will be included in NDP.
Pipeline including CS | TRA-N-966 | Interconnection Macedonia-Kosovo | former Yugoslav Republic of Macedonia |  | MER JSC Skopje | Less-Advanced Non-FID | No |  |  | 2022 | Yes | N/A | Work Program of the Government of R.Macedonia
Pipeline including CS | TRA-N-998 | Interconnection Macedonia-Albania | former Yugoslav Republic of Macedonia |  | MER JSC Skopje | Less-Advanced Non-FID | No |  |  | 2022 | Yes | N/A | Work Program of the Government of R.Macedonia
Pipeline including CS | TRA-N-047 | Reverse capacity from France to Germany at Obergailbach | France |  | GRTgaz | Less-Advanced Non-FID | Yes | 5.6 | NSIW | 2022 | Yes | na | GRTgaz PDD 2015
Pipeline including CS | TRA-N-258 | Developments for Montoir LNG terminal 2.5 bcm expansion | France |  | GRTgaz | Less-Advanced Non-FID | No |  |  | 2022 | Yes | na | GRTgaz PDD 2015
Pipeline including CS | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | France |  | GRTgaz | Less-Advanced Non-FID | No |  |  | 2022 | Yes | na | GRTgaz PDD 2015
Storage Facility | UGS-N-385 | South Kavala Underground Gas Storage facility | Greece |  | Hellenic Republic Asset anagement Fund | Less-Advanced Non-FID | No |  | NSIE | 2022 | No | N/A | The Project Promoter is not a Transmission System Operator and as such does not have the obligation to submit a National Development Plan.
Pipeline including CS | TRA-N-971 | Compressor station at Nea Messimvria | Greece |  | DESFA S.A. | Less-Advanced Non-FID | No |  | SGC | 2022 | No | N/A | The Compressor station is included in the 10-year Development Study. The D. S. includes projects which are likely to be implemented but are not yet part of the compulsory Projects or projects that require the commercial binding agreements by users of the infrastructure.
Pipeline including CS | TRA-N-1091 | Metering and Regulating station at Megalopoli | Greece |  | DESFA S.A. | Less-Advanced Non-FID | No |  | SGC | 2022 | No | N/A | This project is not included in the National Development Plan because no application has been made, by the promoter of the East-Med pipeline, for the connection of this project to the Greek gas transmission system.
Pipeline including CS | TRA-N-018 | Városföld-Ercsi-Győr | Hungary |  | FGSZ Ltd. | Less-Advanced Non-FID | Yes | 6.24.4. | NSIE | 2022 | Yes | 12.7. | Hungarian TYNDP 2015 | Yes | 2016-10-06
Pipeline including CS | TRA-N-061 | Ercsi-Szazhalombatta | Hungary |  | FGSZ Ltd. | Less-Advanced Non-FID | Yes | 6.24.5 | NSIE | 2022 | Yes | 12.9. | Hungarian TYNDP 2015 | Yes | 2016-12-31
Pipeline including CS | TRA-N-123 | Városföld CS | Hungary |  | FGSZ Ltd. | Less-Advanced Non-FID | Yes | 6.24.6. | NSIE | 2022 | Yes | 12.10. | Hungarian TYNDP 2015
Pipeline including CS | TRA-N-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | Hungary |  | FGSZ Ltd. | Less-Advanced Non-FID | Yes | 6.24.9. | NSIE | 2022 | Yes | 12.6.1. | Hungarian TYNDP 2015 | Yes | 2016-10-06
Pipeline including CS | TRA-N-071 | Physical Reverse Flow on South North Pipeline | Ireland |  | Gas Networks Ireland | Less-Advanced Non-FID | No |  |  | 2022 | Yes | N/A | Gaslink, Network development Plan 2013
Pipeline including CS | TRA-N-271 | Poland - Denmark interconnection (Baltic Pipe) - PL section | Poland |  | GAZ-SYSTEM S.A. | Less-Advanced Non-FID | Yes | 8.3 | BEMIP | 2022 | Yes | N/A | Network Development Plan 2016-2025
Storage Facility | UGS-N-659 | RENC-8 Carriço UGS cavern | Portugal |  | REN - Armazenagem, S.A. | Less-Advanced Non-FID | No |  |  | 2022 | Yes | - | PDIRGN 2015
Pipeline including CS | TRA-N-053 | White Stream | Romania |  | White Stream Ltd | Less-Advanced Non-FID | No |  | SGC | 2022 | No | N/A | Countries outside EU do not have established practices similar to EU MSs for the NDPs. As for EU MSs, Germany has included the White Stream project, a continuation of the TCP project: http://www.fnb-gas.de/files/2015_07_27_nep_gas_2016_szenariorahmen.pdf
Storage Facility | UGS-N-371 | Sarmasel undeground gas storage in Romania | Romania |  | Societatea Naţională de Gaze Naturale ROMGAZ S.A. | Less-Advanced Non-FID | Yes | 6.20.6 | NSIE | 2022 | No | N/A | S.N.G.N. ROMGAZ S.A., the project promotor, is not a TSO, therefore it is not mandatory to have a TYNDP, as Transgaz does. There is no NDP at country level.
Pipeline including CS | TRA-N-093 | CS Ajdovščina, 2nd phase of upgrade | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | No |  |  | 2022 | Yes | C1 | TYNDP for the period 2016-2025
Pipeline including CS | TRA-N-099 | M3/1a Šempeter - Ajdovščina | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | No |  |  | 2022 | Yes | C7 | TYNDP for the period 2016-2025
Pipeline including CS | TRA-N-101 | M8 Kalce - Jelšane | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | No |  |  | 2022 | Yes | C10 | TYNDP for the period 2016-2025
Pipeline including CS | TRA-N-107 | M6 Interconnection Osp | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | No |  |  | 2022 | No | N/A | The project is not included in the currently valid and confirmed NDP (2016-2025), but it was included in the previous one (2015-2024) and it will also be included in the new one, which is in preparation (TYNDP 2017-2026) and will be confirmed by our regulator expectedly in the next months.
Pipeline including CS | TRA-N-261 | M3/1c Kalce - Vodice | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | No |  |  | 2022 | Yes | C9 | TYNDP for the period 2016-2025
Pipeline including CS | TRA-N-262 | M3/1b Ajdovščina - Kalce | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | No |  |  | 2022 | Yes | C8 | TYNDP for the period 2016-2025
LNG Terminal | LNG-N-297 | Mugardos LNG Terminal: Storage Extension | Spain |  | Reganosa | Less-Advanced Non-FID | No |  |  | 2022 | No | N/A | The last aproved Spanish NDP ended in 2016. The Royal Decree-Law 13/2012 cancel any award procedures of new regasification plants in Spain.
Pipeline including CS | TRA-N-727 | Iberian‐French corridor: Eastern Axis ‐ Midcat Project | Spain |  | Enagás Transporte, S.A.U. | Less-Advanced Non-FID | Yes | 5.5 | NSIW | 2022 | Yes | No code in the NDP | Conexión internacional con Francia por Cataluña
Pipeline including CS | TRA-N-224 | Gaspipeline Brod - Zenica | Bosnia Herzegovina |  | BH-Gas d.o.o. | Less-Advanced Non-FID | No |  |  | 2023 | Yes | PTG1 | SPP-Strategic plan and programme of FBiH
Pipeline including CS | TRA-N-910 | Western interconnection BiH/CRO | Bosnia Herzegovina |  | BH-Gas d.o.o. | Less-Advanced Non-FID | No |  |  | 2023 | Yes | PTG4 | SPP-Strategic plan and programme of FBiH
Pipeline including CS | TRA-N-070 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo) | Croatia |  | Plinacro Ltd | Less-Advanced Non-FID | No |  | NSIE | 2023 | Yes | 1.11, 1.12 | 2017-2026
Pipeline including CS | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | Croatia |  | Plinacro Ltd | Less-Advanced Non-FID | Yes | 2.5.2 | NSIE | 2023 | Yes | 1.21 | 2017-2026
Pipeline including CS | TRA-N-755 | CS Rimpar | Germany |  | GRTgaz Deutschland GmbH | Less-Advanced Non-FID | No |  |  | 2023 | Yes | 312-01 | Netzentwicklungsplan Gas 2016
Pipeline including CS | TRA-N-809 | Additional East-West transport NL | Germany |  | Gasunie Deutschland Transport Services GmbH | Less-Advanced Non-FID | No |  |  | 2023 | No | N/A | Project idea. The inclusion in the NDP is planned at a later time.
Pipeline including CS | TRA-N-825 | Compressor station "Legden" | Germany |  | Open Grid Europe GmbH | Less-Advanced Non-FID | No |  |  | 2023 | Yes | 416-01 | Entwurf Netzentwicklungsplan Gas 2016
Pipeline including CS | TRA-N-014 | Komotini-Thesprotia pipeline | Greece |  | DESFA S.A. | Less-Advanced Non-FID | Yes | 7.1.7 | SGC | 2023 | Yes | 2.2.1.4 | Development Plan NNGS 2015-2024
Pipeline including CS | TRA-N-1092 | Metering and Regulating Station at UGS South Kavala | Greece |  | DESFA S.A. | Less-Advanced Non-FID | No |  |  | 2023 | No | N/A | This project is not included in the National Development Plan because no application has been made, by the promoter of the UGS in South Kavala, for the connection of this project to the Greek gas transmission system.
Pipeline including CS | TRA-N-007 | Development for new import from the South (Adriatica Line) | Italy |  | Snam Rete Gas S.p.A. | Less-Advanced Non-FID | Yes | 6.18 | NSIE | 2023 | Yes | TRA-N-007(into text) | Snam Rete Gas TYNDP 2016-2025
Pipeline including CS | TRA-N-354 | Interconnection with Slovenia | Italy |  | Snam Rete Gas S.p.A. | Less-Advanced Non-FID | No |  |  | 2023 | Yes | TRA-N-354 | Snam Rete Gas TYNDP 2016-2025
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | Poland |  | GAZ-SYSTEM S.A. | Less-Advanced Non-FID | Yes | 6.2.2 | NSIE | 2023 | Yes | N/A | Network Development Plan 2016-2025
Storage Facility | UGS-N-366 | New undergound gas storage in Romania | Romania |  | Societatea Naţională de Gaze Naturale ROMGAZ S.A. | Less-Advanced Non-FID | Yes | 6.20.5 | NSIE | 2023 | No | N/A | S.N.G.N. ROMGAZ, the project promoter, is not a TSO, it is only storage operator, therefore it is not mandatory to have a TYNDP, as Transgaz has. There is no NDP country level.
Pipeline including CS | TRA-N-959 | Further enlargement of the BG—RO—HU—AT transmission corridor (BRUA) phase 3 | Romania |  | SNTGN Transgaz SA | Less-Advanced Non-FID | Yes | 6.25.3 | NSIE | 2023 | Yes | 7.5 | Developement Plan for the National GTS 2016 - 2025
Storage Facility | UGS-N-127 | Underground Gas Storage in salt leached caverns in the Bages area (ES) | Spain |  | Gas Natural | Less-Advanced Non-FID | No |  |  | 2023 | No | N/A | As of today there is not NPD. The project was initially included in a former draft. Afterwards the draft was amended without including this underground storage. Nowadays NPD is under study and we dont know whether this underground storage will be included or not.
LNG Terminal | LNG-N-295 | Mugardos LNG Terminal: Send-out Increase | Spain |  | Reganosa | Less-Advanced Non-FID | No |  |  | 2023 | Yes | N/A | PLANIFICACION ELECTRICIDAD Y GAS 2008-2016
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | France |  | GRTgaz and TIGF | Less-Advanced Non-FID | Yes | 5.5 - 5.8 | NSIW | 2024 | Yes | na | GRTgaz and TIGF development plans 2015
Pipeline including CS | TRA-N-380 | BG-RO-HU-AT transmission corridor | Hungary |  | FGSZ Ltd. | Less-Advanced Non-FID | No |  | NSIE | 2024 | Yes | 12.13.1.-12.14.7 | Hungarian TYNDP 2015
LNG Terminal | LNG-N-824 | LNG Terminal in Klaipeda | Lithuania |  | AB Klaipėdos Nafta | Less-Advanced Non-FID | No |  | BEMIP | 2024 | No | N/A | NDP covers only TSO investments. LNG terminal is not a part of TSO network, therefore NDP does not include LNG terminal projects. LNG projects are covered by TYNDP at EU level, not at the national level.
Pipeline including CS | TRA-N-114 | R61 Dragonja - Izola | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | No |  |  | 2024 | Yes | C11 | TYNDP for the period 2016-2025
Pipeline including CS | TRA-N-284 | 3rd IP between Portugal and Spain (Compressor Station) | Portugal |  | REN-Gasodutos, S.A. | Less-Advanced Non-FID | Yes | 5.4 | NSIW | 2025 | Yes | - | PDIRGN 2015
Pipeline including CS | TRA-N-285 | 3rd IP between Portugal and Spain (pipeline Cantanhede-Mangualde) | Portugal |  | REN-Gasodutos, S.A. | Less-Advanced Non-FID | Yes | 5.4 | NSIW | 2025 | Yes | - | PDIRGN 2015
Pipeline including CS | TRA-N-729 | Interconnection ES-PT (3rd IP) - 2nd phase | Spain |  | Enagás Transporte, S.A.U. | Less-Advanced Non-FID | Yes | 5.4 | NSIW | 2025 | No | N/A | The project was not included in the last NDP that was published in 2008. The project was identified later on, and was selected as PCI by the European Commission in 2013 and in 2015. Additionally, this project is being considered in the High Level Group on Interconnections for South-West Europe.
Pipeline including CS | TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Croatia |  | Plinacro Ltd | Less-Advanced Non-FID | No |  |  | 2026 | Yes | 1.32 and 1.33 | 2017-2026
Pipeline including CS | TRA-N-336 | Interconnection Croatia/Slovenia (Umag-Koper) | Croatia |  | Plinacro Ltd | Less-Advanced Non-FID | No |  |  | 2026 | Yes | 1.34 | 2017-2026
Pipeline including CS | TRA-N-031 | Connection of Malta to the European Gas Network - Pipelines | Malta |  | Office of the Prime Minister (Energy) | Less-Advanced Non-FID | Yes | 5.19 | NSIW | 2026 | Yes | Section 3.4.2 | Malta National Reform Programme April 2015
Storage Facility | UGS-N-914 | UGS Damaslawek | Poland |  | GAZ-SYSTEM S.A. | Less-Advanced Non-FID | No |  |  | 2026 | Yes | N/A | Network Development Plan 2016-2025
Pipeline including CS | TRA-N-376 | Azerbaijan, Georgia, Romania Interconnector - AGRI | Romania |  | AGRI LNG Project Company SRL (RO) | Less-Advanced Non-FID | No |  | SGC | 2026 | No | N/A | AGRI is not a Transmission System Operator, so it is not necessary for its project to be part of a National Development Plan.
LNG Terminal | LNG-N-165 | Gran Canaria send out increase | Spain |  | Gascan | Less-Advanced Non-FID | No |  |  | 2026 | Yes | No code in the NDP | Ampliación emisión en Gran Canaria
LNG Terminal | LNG-N-185 | Tenerife Send-Out increase | Spain |  | Gascan | Less-Advanced Non-FID | No |  |  | 2026 | Yes | No code in the NDP | Ampliación emisión en Tenerife a 225.000 m3(n)/h
Pipeline including CS | TRA-N-955 | GUD: Complete conversion to H-gas | Germany |  | Gasunie Deutschland Transport Services GmbH | Less-Advanced Non-FID | No |  |  | 2030 | No | N/A | The project is only a Capacity Modification, which does not require actual investment or construction works.
Pipeline including CS | TRA-N-975 | Sardinia Gas Transportation Network | Italy |  | Società Gasdotti Italia | Less-Advanced Non-FID | No |  |  | 2031 | Yes | Not applicable | There is no NDP currently in force
LNG Terminal | LNG-N-211 | Connection of Malta to the European Gas Network - LNG Regasification | Malta |  | Office of the Prime Minister (Energy) | Less-Advanced Non-FID | Yes | 5.19 | NSIW | 2031 | Yes | Section 3.4.2 | Malta National Reform Programme April 2015
Pipeline including CS | TRA-N-008 | Import developments from North-East | Italy |  | Snam Rete Gas S.p.A. | Less-Advanced Non-FID | No |  |  | 2034 | Yes | TRA-N-008(into text) | Snam Rete Gas TYNDP 2016-2025
Pipeline including CS | TRA-N-009 | Additional Southern developments | Italy |  | Snam Rete Gas S.p.A. | Less-Advanced Non-FID | No |  |  | 2034 | Yes | TRA-N-009(into text) | Snam Rete Gas TYNDP 2016-2025
Storage Facility | UGS-N-141 | Construction of new gas storage facility on the territory of Bulgaria | Bulgaria |  | Bulgartransgaz EAD | Less-Advanced Non-FID | No |  |  | Unknown | Yes | section 5.3.2. | 2016-2025 Ten-year network development plan of BTG
Pipeline including CS | TRA-N-065 | Hajduszoboszlo CS | Hungary |  | FGSZ Natural Gas transmission Company limited by Shares. | Less-Advanced Non-FID | No |  |  | Unknown | Yes | 12-11 | Hungarian TYNDP 2015
LNG Terminal | LNG-N-030 | Shannon LNG Terminal and Connecting Pipeline | Ireland |  | Shannon LNG | Less-Advanced Non-FID | Yes | Project Code 5.3 under Commission Delegated Regulation (EU) No 1391/2013 | NSIW | Unknown | Yes | PCI 5.3 | Gas Networks Ireland 2015 Network Development Plan
LNG Terminal | LNG-N-162 | Gran Canaria 2º LNG Tank | Spain |  | Gascan | Less-Advanced Non-FID | No |  |  | Unknown | Yes | No code in the NDP | Gran Canaria: 2º Tanque de 150.000 m3 GNL
LNG Terminal | LNG-N-184 | Tenerife 2º LNG Storage Tank | Spain |  | Gascan | Less-Advanced Non-FID | No |  |  | Unknown | Yes | No code in the NDP | Gran Canaria: 2º Tanque de 150.000 m3 GNL
Pipeline including CS | TRA-N-339 | Trans-Caspian | Turkmenistan |  | W-Stream Caspian Pipeline Company Ltd | Less-Advanced Non-FID | Yes | 7.1.1 | SGC | Unknown | No | N/A | Countries outside EU do not have established practices similar to EU MSs for the NDPs. As for EU MSs, Germany has included the White Stream project, a continuation of the TCP project: http://www.fnb-gas.de/files/2015_07_27_nep_gas_2016_szenariorahmen.pdf
Pipeline including CS | TRA-N-346 | Industrial Emissions Directive (LCP) | United Kingdom |  | National Grid Gas plc | Less-Advanced Non-FID | No |  |  | Unknown | Yes | Section 5.2 | Gas Ten Year Statement 2015
Pipeline including CS | TRA-N-349 | Industrial Emisssion Directive (IPPC) - Non-FID | United Kingdom |  | National Grid Gas plc | Less-Advanced Non-FID | No |  |  | Unknown | Yes | Section 5.2 | Gas Ten Year Statement 2015

## Capacities
TYNDP Annex A |  |  |  | Capacities - Page 2
Capacity Created by the Projects
Point Category | Point | From System | To System |  | Code | Name | Promoter | Status | PCI 2nd List | Operator | Commissioning Year | Capacity (GWh/d)
Cross-Border Storage IP within EU | Haidach (AT) / Haidach USP (DE) | Transmission Germany (NCG) | Storage Austria (CEGH) |  | TRA-F-241 | MONACO section phase I (Burghausen-Finsing) | bayernets GmbH | FID | No | bayernets GmbH | 2017 | 267.12
Cross-Border Storage IP within EU | Haidach (AT) / Haidach USP (DE) | Storage Austria (CEGH) | Transmission Germany (NCG) |  | TRA-F-241 | MONACO section phase I (Burghausen-Finsing) | bayernets GmbH | FID | No | bayernets GmbH | 2017 | 293.83
Cross-Border Storage IP within EU | Haiming 2 7F/bn | Transmission Germany (NCG) | Storage Austria (CEGH) |  | TRA-F-241 | MONACO section phase I (Burghausen-Finsing) | bayernets GmbH | FID | No | bayernets GmbH | 2017 | 160.78
Cross-Border Storage IP within EU | Haiming 2 7F/bn | Storage Austria (CEGH) | Transmission Germany (NCG) |  | TRA-F-241 | MONACO section phase I (Burghausen-Finsing) | bayernets GmbH | FID | No | bayernets GmbH | 2017 | 241.17
Cross-Border Storage IP within EU | Haiming 2-RAGES/bn | Transmission Germany (NCG) | Storage Austria (CEGH) |  | TRA-F-241 | MONACO section phase I (Burghausen-Finsing) | bayernets GmbH | FID | No | bayernets GmbH | 2017 | 16.31
Cross-Border Storage IP within EU | Haiming 2-RAGES/bn | Storage Austria (CEGH) | Transmission Germany (NCG) |  | TRA-F-241 | MONACO section phase I (Burghausen-Finsing) | bayernets GmbH | FID | No | bayernets GmbH | 2017 | 16.31
Cross-Border Transmission IP between EU and Non-EU | Beregdaróc 800 (HU) - Beregovo (UA) (HU>UA) | Transmission Hungary (MGP) | Transmission Ukraine (Exports) |  | TRA-N-645 | HU-UA Interconnector (Ukrainian section) | PJSC Ukrtransgaz | Less-Advanced Non-FID | No | Ukrtransgaz | 2017 | 0
Cross-Border Transmission IP between EU and Non-EU | Beregdaróc 800 (HU) - Beregovo (UA) (HU>UA) | Transmission Hungary (MGP) | Transmission Ukraine (Exports) |  | TRA-N-586 | HU-UA reverse flow | FGSZ Ltd. | Less-Advanced Non-FID | No | FGSZ Ltd. | 2020 | 180
Cross-Border Transmission IP between EU and Non-EU | Budince | Transmission Slovakia | Transmission Ukraine (Exports) |  | TRA-F-1047 | Exit Capacity Budince | eustream, a.s. | FID | No | eustream, a.s. | 2016 | 135.2
Cross-Border Transmission IP between EU and Non-EU | Eagle LNG / Snam Rete Gas (IT) | Transmission Eagle Pipeline Italy Albania | Transmission Italy (PSV) (Southern Projects) |  | LNG-N-328 | Eagle LNG and Pipeline | Burns Srl | Less-Advanced Non-FID | No | Trans-European Energy B.V., Sh.A. | 2020 | 300
Cross-Border Transmission IP between EU and Non-EU | Eastring Cross-Border BG/EAR>TR | Transmission Eastring Bulgaria | Transmission Turkey (Exports) |  | TRA-N-654 | Eastring - Bulgaria | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | Bulgartransgaz EAD | 2021 | 570
Cross-Border Transmission IP between EU and Non-EU | Eastring Cross-Border BG/EAR>TR | Transmission Eastring Bulgaria | Transmission Turkey (Exports) |  | TRA-N-654 | Eastring - Bulgaria | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | Bulgartransgaz EAD | 2025 | 570
Cross-Border Transmission IP between EU and Non-EU | Griespass (CH) / Passo Gries (IT) | Transmission Italy (PSV) (Italy Northern Export Fork) | Transmission Switzerland |  | TRA-F-214 | Support to the North West market and bidirectional cross-border flows | Snam Rete Gas S.p.A. | FID | Yes | Snam Rete Gas S.p.A. | 2018 | 368
Cross-Border Transmission IP between EU and Non-EU | Griespass (CH) / Passo Gries (IT) (FluxSwiss) | Transmission Italy (PSV) (Italy Northern Export Fork) | Transmission Switzerland |  | TRA-F-230 | Reverse Flow Transitgas Switzerland | FluxSwiss | FID | No | FluxSwiss | 2018 | 428
Cross-Border Transmission IP between EU and Non-EU | Interconnector BG RS | Transmission Bulgaria (NGTS) | Transmission Serbia |  | TRA-F-137 | Interconnection Bulgaria - Serbia | Ministry of Energy | FID | Yes | IBS Future Operator | 2018 | 51
Cross-Border Transmission IP between EU and Non-EU | Interconnector BG RS | Transmission Serbia | Transmission Bulgaria (NGTS) |  | TRA-F-137 | Interconnection Bulgaria - Serbia | Ministry of Energy | FID | Yes | IBS Future Operator | 2018 | 51
Cross-Border Transmission IP between EU and Non-EU | Interconnector BG RS | Transmission Bulgaria (NGTS) | Transmission Serbia |  | TRA-N-298 | Rehabilitation, Modernization and Expansion of the NTS | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | IBS Future Operator | 2020 | 19.36
Cross-Border Transmission IP between EU and Non-EU | Interconnector BG RS | Transmission Serbia | Transmission Bulgaria (NGTS) |  | TRA-N-298 | Rehabilitation, Modernization and Expansion of the NTS | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | IBS Future Operator | 2020 | 19.36
Cross-Border Transmission IP between EU and Non-EU | Novo Selo (MK) / Samuilova Krepost (BG) | Transmission Bulgarian Transit Bulgaria (GTNTT) | Transmission former Yugoslav Republic of Macedonia |  | TRA-N-976 | Interconnection Macedonia-Bulgaria | MER JSC Skopje | Less-Advanced Non-FID | No | MER JSC Skopje | 2021 | 1
Cross-Border Transmission IP between EU and Non-EU | Oltingue (FR) / Rodersdorf (CH) | Transmission Switzerland | Transmission France (PEG North) |  | TRA-F-230 | Reverse Flow Transitgas Switzerland | FluxSwiss | FID | No | FluxSwiss | 2018 | 100
Cross-Border Transmission IP between EU and Non-EU | Oltingue (FR) / Rodersdorf (CH) | Transmission Switzerland | Transmission France (PEG North) |  | TRA-F-45 | Reverse capacity from CH to FR at Oltingue | GRTgaz | FID | No | GRTgaz | 2018 | 0
Cross-Border Transmission IP between EU and Non-EU | PL>UA Interconnector | Transmission Poland (VTP - GAZ-SYSTEM) | Transmission Ukraine (Exports) |  | TRA-N-561 | Poland-Ukraine Interconnector (Ukrainian section) | PJSC Ukrtransgaz | Less-Advanced Non-FID | No | Ukrtransgaz | 2019 | 245
Cross-Border Transmission IP between EU and Non-EU | PL>UA Interconnector | Transmission Poland (VTP - GAZ-SYSTEM) | Transmission Ukraine (Exports) |  | TRA-N-621 | Poland - Ukraine Gas interconnection (PL section) | GAZ-SYSTEM S.A. | Less-Advanced Non-FID | No | GAZ-SYSTEM S.A. | 2020 | 245
Cross-Border Transmission IP between EU and Non-EU | Posušje | Transmission Bosnia Herzegovina | Transmission Ionic-Adriatic Pipeline Croatia |  | TRA-N-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | Plinacro Ltd | Advanced Non-FID | No | Plinacro Ltd | 2021 | 73
Cross-Border Transmission IP between EU and Non-EU | Posušje | Transmission Ionic-Adriatic Pipeline Croatia | Transmission Bosnia Herzegovina |  | TRA-N-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | Plinacro Ltd | Advanced Non-FID | No | Plinacro Ltd | 2021 | 73
Cross-Border Transmission IP between EU and Non-EU | Posušje | Transmission Ionic-Adriatic Pipeline Croatia | Transmission Bosnia Herzegovina |  | TRA-N-851 | Southern Interconnection pipeline BiH/CRO | BH-GAS d.o.o. | Less-Advanced Non-FID | No | BH Gas d.o.o. | 2021 | 38
Cross-Border Transmission IP between EU and Non-EU | Rakovica (HR) / Trzac (BA) | Transmission Croatia | Transmission Bosnia Herzegovina |  | TRA-N-910 | Western interconnection BiH/CRO | BH-Gas d.o.o. | Less-Advanced Non-FID | No | BH Gas d.o.o. | 2023 | 27
Cross-Border Transmission IP between EU and Non-EU | Rakovica (HR) / Trzac (BA) | Transmission Bosnia Herzegovina | Transmission Croatia |  | TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Plinacro Ltd | Less-Advanced Non-FID | No | Plinacro Ltd | 2026 | 73
Cross-Border Transmission IP between EU and Non-EU | Rakovica (HR) / Trzac (BA) | Transmission Croatia | Transmission Bosnia Herzegovina |  | TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Plinacro Ltd | Less-Advanced Non-FID | No | Plinacro Ltd | 2026 | 73
Cross-Border Transmission IP between EU and Non-EU | Slobodnica - Sotin (HR) / Bačko Novo Selo (RS) | Transmission Croatia | Transmission Serbia |  | TRA-N-070 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo) | Plinacro Ltd | Less-Advanced Non-FID | No | Plinacro Ltd | 2023 | 205
Cross-Border Transmission IP between EU and Non-EU | Slobodnica - Sotin (HR) / Bačko Novo Selo (RS) | Transmission Serbia | Transmission Croatia |  | TRA-N-070 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo) | Plinacro Ltd | Less-Advanced Non-FID | No | Plinacro Ltd | 2023 | 205
Cross-Border Transmission IP between EU and Non-EU | Slobodnica- Bosanski Brod-Zenica | Transmission Bosnia Herzegovina | Transmission Croatia |  | TRA-N-066 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Plinacro Ltd | Advanced Non-FID | No | Plinacro Ltd | 2019 | 146
Cross-Border Transmission IP between EU and Non-EU | Slobodnica- Bosanski Brod-Zenica | Transmission Croatia | Transmission Bosnia Herzegovina |  | TRA-N-066 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Plinacro Ltd | Advanced Non-FID | No | Plinacro Ltd | 2019 | 146
Cross-Border Transmission IP between EU and Non-EU | Slobodnica- Bosanski Brod-Zenica | Transmission Croatia | Transmission Bosnia Herzegovina |  | TRA-N-224 | Gaspipeline Brod - Zenica | BH-Gas d.o.o. | Less-Advanced Non-FID | No | BH Gas d.o.o. | 2023 | 35
Cross-Border Transmission IP between EU and Non-EU | Stojakovo village (MK) / Pontoiraklia (GR) | Transmission Greece | Transmission former Yugoslav Republic of Macedonia |  | TRA-N-967 | Nea-Messimvria to FYROM pipeline | DESFA S.A. | Less-Advanced Non-FID | No | DESFA S.A. | 2020 | 76.5
Cross-Border Transmission IP between EU and Non-EU | Stojakovo village (MK) / Pontoiraklia (GR) | Transmission Greece | Transmission former Yugoslav Republic of Macedonia |  | TRA-N-980 | Interconnection Macedonia-Greece | MER JSC Skopje | Less-Advanced Non-FID | No | MER JSC Skopje | 2021 | 1
Cross-Border Transmission IP between EU and Non-EU | Strandzha (BG) / Malkoclar (TR) | Transmission Bulgarian Transit Bulgaria (GTNTT) | Transmission Turkey (Exports) |  | TRA-N-298 | Rehabilitation, Modernization and Expansion of the NTS | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | Bulgartransgaz EAD | 2020 | 58.08
Cross-Border Transmission IP between EU and Non-EU | Strandzha (BG) / Malkoclar (TR) | Transmission Bulgarian Transit Bulgaria (GTNTT) | Transmission Turkey (Exports) |  | TRA-N-594 | Construction of a Looping CS Provadia – Rupcha village | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | Bulgartransgaz EAD | 2022 | 192.5
Cross-Border Transmission IP between EU and Non-EU | TESLA / GR>FYROM | Transmission TESLA Greece | Transmission TESLA former Yugoslav Republic of Macedonia |  | TRA-N-582 | Macedonian part of Tesla project | GA-MA joint stock company Skopje | Less-Advanced Non-FID | Yes | GA-MA - Skopje | 2019 | 675
Cross-Border Transmission IP between EU and Non-EU | TESLA / GR>FYROM | Transmission TESLA Greece | Transmission TESLA former Yugoslav Republic of Macedonia |  | TRA-N-631 | Greek part of Tesla project | DESFA S.A. | Less-Advanced Non-FID | Yes | DESFA S.A. | 2020 | 909
Cross-Border Transmission IP between EU and Non-EU | TESLA / RS>HU | Transmission TESLA Serbia | Transmission TESLA Hungary (MGP) |  | TRA-N-585 | Hungarian section of Tesla project | FGSZ Ltd. | Less-Advanced Non-FID | Yes | FGSZ Ltd. | 2020 | 582
Cross-Border Transmission IP between EU and Non-EU | Wallbach | Transmission Switzerland | Transmission Germany (NCG) |  | TRA-F-230 | Reverse Flow Transitgas Switzerland | FluxSwiss | FID | No | FluxSwiss | 2018 | 240
Cross-Border Transmission IP between EU and Non-EU | Wallbach | Transmission Switzerland | Transmission Germany (NCG) |  | TRA-F-208 | Reverse Flow TENP Germany | Fluxys TENP GmbH & Open Grid Europe GmbH | FID | Yes | Fluxys TENP GmbH | 2018 | 240
Cross-Border Transmission IP between EU and Non-EU | Wallbach | Transmission Switzerland | Transmission Germany (NCG) |  | TRA-F-208 | Reverse Flow TENP Germany | Fluxys TENP GmbH & Open Grid Europe GmbH | FID | Yes | Fluxys TENP GmbH | 2025 | 79.2
Cross-Border Transmission IP between EU and Non-EU (import) | AGRI / Constanta (RO) | Transmission Georgia (AGRI) | Transmission Romania |  | TRA-N-376 | Azerbaijan, Georgia, Romania Interconnector - AGRI | AGRI LNG Project Company SRL (RO) | Less-Advanced Non-FID | No | AGRI | 2026 | 240
Cross-Border Transmission IP between EU and Non-EU (import) | Constanta (White Stream) | Transmission South Caucasus Pipeline Azerbaijan | Transmission Romania |  | TRA-N-053 | White Stream | White Stream Ltd | Less-Advanced Non-FID | No | White Stream | 2022 | 505
Cross-Border Transmission IP between EU and Non-EU (import) | Eastring Cross-Border TR>BG/EAR | Transmission Turkey (Russia Connection) | Transmission Eastring Bulgaria |  | TRA-N-654 | Eastring - Bulgaria | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | Bulgartransgaz EAD | 2021 | 570
Cross-Border Transmission IP between EU and Non-EU (import) | Eastring Cross-Border TR>BG/EAR | Transmission Turkey (Russia Connection) | Transmission Eastring Bulgaria |  | TRA-N-654 | Eastring - Bulgaria | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | Bulgartransgaz EAD | 2025 | 570
Cross-Border Transmission IP between EU and Non-EU (import) | Greifswald / NEL | Transmission Nord Stream Russia (Greifswald) | Transmission Germany (GASPOOL) |  | TRA-F-768 | Extension Receiving Terminal Greifswald | NEL Gastransport, Fluxys Deutschland, Gasunie Deutschland | FID | No | NEL Gastransport GmbH | 2017 | 90.58
Cross-Border Transmission IP between EU and Non-EU (import) | Greifswald / NEL | Transmission Nord Stream Russia (Greifswald) | Transmission Germany (GASPOOL) |  | TRA-F-768 | Extension Receiving Terminal Greifswald | NEL Gastransport, Fluxys Deutschland, Gasunie Deutschland | FID | No | NEL Gastransport GmbH | 2019 | 65.42
Cross-Border Transmission IP between EU and Non-EU (import) | Interconnector ITB (Turkey - Bulgaria) (BG>TR) | Transmission Bulgaria (NGTS) | Transmission Turkey (Exports) |  | TRA-N-140 | Interconnection Turkey-Bulgaria | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | Bulgartransgaz EAD | 2020 | 97
Cross-Border Transmission IP between EU and Non-EU (import) | Interconnector ITB (Turkey - Bulgaria) (TR>BG) | Transmission Turkey (Imports) | Transmission Bulgaria (NGTS) |  | TRA-N-140 | Interconnection Turkey-Bulgaria | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | Bulgartransgaz EAD | 2020 | 97
Cross-Border Transmission IP between EU and Non-EU (import) | Kipi (TR) / Kipi (GR) | Transmission Turkey (Imports) | Transmission Greece (Komotini) |  | TRA-N-128 | Compressor Station Kipi | DESFA S.A. | Less-Advanced Non-FID | Yes | DESFA S.A. | 2020 | 54.4
Cross-Border Transmission IP between EU and Non-EU (import) | Kipi (TR) / Kipi (TAP) | Transmission Trans-Anatolian Pipeline Turkey | Transmission Trans-Adriatic Pipeline Greece |  | TRA-F-051 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | FID | Yes | Trans-Adriatic Pipeline AG | 2019 | 350
Cross-Border Transmission IP between EU and Non-EU (import) | Kipi (TR) / Kipi (TAP) | Transmission Trans-Anatolian Pipeline Turkey | Transmission Trans-Adriatic Pipeline Greece |  | TRA-F-221 | TANAP - Trans Anatolian Natural Gas Pipeline Project | SOCAR (The State Oil Company of the Azerbaijan Republic) | FID | Yes | TANAP TSO | 2019 | 318
Cross-Border Transmission IP between EU and Non-EU (import) | Koudiet Eddraouch (Galsi) (DZ) | Transmission Algeria | Transmission GALSI Algeria (International) |  | TRA-N-012 | GALSI Pipeline Project | Galsi S.p.A. | Advanced Non-FID | Yes | Galsi S.p.A. | 2019 | 258
Cross-Border Transmission IP between EU and Non-EU (import) | TESLA / TR>GR | Transmission Turkey (Russia Connection) | Transmission TESLA Greece |  | TRA-N-631 | Greek part of Tesla project | DESFA S.A. | Less-Advanced Non-FID | Yes | DESFA S.A. | 2020 | 1227
Cross-Border Transmission IP between EU and Non-EU (import) | UA>PL Interconnector | Transmission Ukraine | Transmission Poland (VTP - GAZ-SYSTEM) |  | TRA-N-561 | Poland-Ukraine Interconnector (Ukrainian section) | PJSC Ukrtransgaz | Less-Advanced Non-FID | No | Ukrtransgaz | 2019 | 215
Cross-Border Transmission IP between EU and Non-EU (import) | UA>PL Interconnector | Transmission Ukraine | Transmission Poland (VTP - GAZ-SYSTEM) |  | TRA-N-621 | Poland - Ukraine Gas interconnection (PL section) | GAZ-SYSTEM S.A. | Less-Advanced Non-FID | No | GAZ-SYSTEM S.A. | 2020 | 215
Cross-Border Transmission IP between EU and Non-EU (import) | Vierow | Transmission Nord Stream 2 Russia | Transmission Germany (GASPOOL) |  | TRA-N-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | GASCADE Gastransport GmbH | Advanced Non-FID | No | GASCADE Gastransport GmbH | 2019 | 946.8
Cross-Border Transmission IP between EU and Non-EU (import) | Vierow | Transmission Nord Stream 2 Russia | Transmission Germany (GASPOOL) |  | TRA-N-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | GASCADE Gastransport GmbH | Advanced Non-FID | No | GASCADE Gastransport GmbH | 2020 | 612
Cross-Border Transmission IP between EU and Non-EU (import) | Vierow | Transmission Nord Stream 2 Russia | Transmission Germany (GASPOOL) |  | TRA-N-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | GASCADE Gastransport GmbH | Advanced Non-FID | No | GASCADE Gastransport GmbH | 2021 | 343.1
Cross-Border Transmission IP between EU and Non-EU (import) | Vierow | Transmission Nord Stream 2 Russia | Transmission Germany (GASPOOL) |  | TRA-F-937 | Nord Stream 2 | Nord Stream 2 AG | FID | No | Nord Stream 2 AG | 2019 | 1900
Cross-Border Transmission IP Non-EU | AGRI / Poti (GE) | Transmission Georgia (?) | Transmission Georgia (AGRI) |  | TRA-N-376 | Azerbaijan, Georgia, Romania Interconnector - AGRI | AGRI LNG Project Company SRL (RO) | Less-Advanced Non-FID | No | AGRI | 2026 | 240
Cross-Border Transmission IP Non-EU | Eagle LNG / Ionic-Adriatic Pipeline | Transmission Eagle Pipeline IAP Albania | Transmission Ionic-Adriatic Pipeline Croatia (TAP-IAP Interconnection) |  | LNG-N-328 | Eagle LNG and Pipeline | Burns Srl | Less-Advanced Non-FID | No | Trans-European Energy B.V., Sh.A. | 2020 | 150
Cross-Border Transmission IP Non-EU | Gostivar (MK) / TAP | Transmission Trans-Adriatic Pipeline Greece | Transmission former Yugoslav Republic of Macedonia |  | TRA-F-051 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | FID | Yes | Trans-Adriatic Pipeline AG | 2019 | 25
Cross-Border Transmission IP Non-EU | Gostivar (MK) / TAP | Transmission Trans-Adriatic Pipeline Greece | Transmission former Yugoslav Republic of Macedonia |  | TRA-N-545 | Infrastructure gas pipeline Skopje - Tetovo - Gostivar - Albanian border | GA-MA joint stock company Skopje | Less-Advanced Non-FID | No | GA-MA - Skopje | 2018 | 25
Cross-Border Transmission IP Non-EU | Gracani (MK) / Gorance | Transmission former Yugoslav Republic of Macedonia | Transmission Serbia (Kosovo) |  | TRA-N-966 | Interconnection Macedonia-Kosovo | MER JSC Skopje | Less-Advanced Non-FID | No | MER JSC Skopje | 2022 | 1
Cross-Border Transmission IP Non-EU | Ionic-Adriatic Pipeline - IAP / AB | Transmission Ionic-Adriatic Pipeline Croatia | Transmission Albania |  | TRA-N-068 | Ionian Adriatic Pipeline | Plinacro Ltd | Advanced Non-FID | No | Plinacro Ltd | 2023 | 30
Cross-Border Transmission IP Non-EU | Ionic-Adriatic Pipeline - IAP / ME | Transmission Ionic-Adriatic Pipeline Croatia | Transmission Montenegro |  | TRA-N-068 | Ionian Adriatic Pipeline | Plinacro Ltd | Advanced Non-FID | No | Plinacro Ltd | 2023 | 15
Cross-Border Transmission IP Non-EU | Kafasan (MK) / Perrenjas (AL) | Transmission Albania | Transmission former Yugoslav Republic of Macedonia |  | TRA-N-998 | Interconnection Macedonia-Albania | MER JSC Skopje | Less-Advanced Non-FID | No | MER JSC Skopje | 2022 | 1
Cross-Border Transmission IP Non-EU | Sopot (MK) / Strezovac (RS) | Transmission Serbia | Transmission former Yugoslav Republic of Macedonia |  | TRA-N-965 | Interconnection Macedonia-Serbia | MER JSC Skopje | Less-Advanced Non-FID | No | MER JSC Skopje | 2021 | 1
Cross-Border Transmission IP Non-EU | South Caucasus Pipeline / White Stream | Transmission Azerbaijan | Transmission South Caucasus Pipeline Azerbaijan |  | TRA-N-053 | White Stream | White Stream Ltd | Less-Advanced Non-FID | No | White Stream | 2022 | 505
Cross-Border Transmission IP Non-EU | TESLA / FYROM>RS | Transmission TESLA former Yugoslav Republic of Macedonia | Transmission TESLA Serbia |  | TRA-N-582 | Macedonian part of Tesla project | GA-MA joint stock company Skopje | Less-Advanced Non-FID | Yes | GA-MA - Skopje | 2019 | 640
Cross-Border Transmission IP Non-EU | Türkgözü | Transmission South Caucasus Pipeline Azerbaijan | Transmission Trans-Anatolian Pipeline Turkey |  | TRA-F-221 | TANAP - Trans Anatolian Natural Gas Pipeline Project | SOCAR (The State Oil Company of the Azerbaijan Republic) | FID | Yes | TANAP TSO | 2018 | 490
Cross-Border Transmission IP Non-EU | Türkgözü | Transmission South Caucasus Pipeline Azerbaijan | Transmission Trans-Anatolian Pipeline Turkey |  | TRA-N-1138 | South Caucasus Pipeline Future Expansion - SCPFX | SOCAR Midstream Operations LLC | Less-Advanced Non-FID | Yes | SOCAR Midstream Operations | 2021 | 150
Cross-Border Transmission IP within EU | Balassagyarmat (HU) / Velké Zlievce (SK) | Transmission Slovakia | Transmission Hungary (SK-HU Interconnector) |  | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | Magyar Gáz Tranzit Zrt. | Less-Advanced Non-FID | Yes | MGT Hungarian Gas Transit Ltd. | 2017 | 26
Cross-Border Transmission IP within EU | Balassagyarmat (HU) / Velké Zlievce (SK) | Transmission Hungary (SK-HU Interconnector) | Transmission Slovakia |  | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | Magyar Gáz Tranzit Zrt. | Less-Advanced Non-FID | Yes | MGT Hungarian Gas Transit Ltd. | 2017 | 102
Cross-Border Transmission IP within EU | Baumgarten (TAG) | Transmission Austria (CEGH) | Transmission Slovakia |  | TRA-N-954 | TAG Reverse Flow | Trans Austria Gasleitung GmbH | Less-Advanced Non-FID | No | TAG GmbH | 2018 | 268.559
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GTG Nord) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) |  | TRA-N-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Gastransport Nord GmbH | Less-Advanced Non-FID | No | Gastransport Nord GmbH | 2020 | 48
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GTG Nord) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) |  | TRA-N-882 | H-gas conversion of L-gas export border points | Gasunie Transport Services B.V. | Less-Advanced Non-FID | No | Gasunie Transport Services B.V. | 2020 | 48
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GTG Nord) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) |  | TRA-N-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Gastransport Nord GmbH | Less-Advanced Non-FID | No | Gastransport Nord GmbH | 2022 | 60
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GTG Nord) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) |  | TRA-N-882 | H-gas conversion of L-gas export border points | Gasunie Transport Services B.V. | Less-Advanced Non-FID | No | Gasunie Transport Services B.V. | 2022 | 12
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GTG Nord) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) |  | TRA-N-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Gastransport Nord GmbH | Less-Advanced Non-FID | No | Gastransport Nord GmbH | 2024 | 72
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GTG Nord) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) |  | TRA-N-882 | H-gas conversion of L-gas export border points | Gasunie Transport Services B.V. | Less-Advanced Non-FID | No | Gasunie Transport Services B.V. | 2024 | 12
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GTG Nord) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) |  | TRA-N-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Gastransport Nord GmbH | Less-Advanced Non-FID | No | Gastransport Nord GmbH | 2026 | 96
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GTG Nord) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) |  | TRA-N-882 | H-gas conversion of L-gas export border points | Gasunie Transport Services B.V. | Less-Advanced Non-FID | No | Gasunie Transport Services B.V. | 2026 | 24
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GTG Nord) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) |  | TRA-N-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Gastransport Nord GmbH | Less-Advanced Non-FID | No | Gastransport Nord GmbH | 2027 | 120
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GTG Nord) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) |  | TRA-N-882 | H-gas conversion of L-gas export border points | Gasunie Transport Services B.V. | Less-Advanced Non-FID | No | Gasunie Transport Services B.V. | 2027 | 24
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GUD) | Transmission Germany (GASPOOL) | Transmission Netherlands (TTF) (VIP NL/Gaspool) |  | TRA-N-808 | Transport of gas volumes to the Netherlands | Gasunie Deutschland Technical Services GmbH | Advanced Non-FID | No | Gasunie Deutschland Transport Services GmbH | 2021 | 223.2
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GUD) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) |  | TRA-N-882 | H-gas conversion of L-gas export border points | Gasunie Transport Services B.V. | Less-Advanced Non-FID | No | Gasunie Transport Services B.V. | 2020 | 72.4
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GUD) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) |  | TRA-N-951 | Embedding CS Folmhusen in H-Gas | Gasunie Deutschland Transport Services GmbH | Less-Advanced Non-FID | No | Gasunie Deutschland Transport Services GmbH | 2020 | 72.38
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GUD) | Transmission Germany (GASPOOL) | Transmission Netherlands (TTF) (VIP NL/Gaspool) |  | TRA-N-873 | Capacity expansion OSZ related to West Stream | Gasunie Transport Services B.V. | Less-Advanced Non-FID | No | Gasunie Transport Services B.V. | 2021 | 223.2
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GUD) | Transmission Germany (GASPOOL) | Transmission Netherlands (TTF) (VIP NL/Gaspool) |  | TRA-N-809 | Additional East-West transport NL | Gasunie Deutschland Transport Services GmbH | Less-Advanced Non-FID | No | Gasunie Deutschland Transport Services GmbH | 2023 | 276
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GUD) | Transmission Germany (GASPOOL) | Transmission Netherlands (TTF) (VIP NL/Gaspool) |  | TRA-N-873 | Capacity expansion OSZ related to West Stream | Gasunie Transport Services B.V. | Less-Advanced Non-FID | No | Gasunie Transport Services B.V. | 2023 | 276
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GUD) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) |  | TRA-N-882 | H-gas conversion of L-gas export border points | Gasunie Transport Services B.V. | Less-Advanced Non-FID | No | Gasunie Transport Services B.V. | 2030 | 137.5
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (H) (NL) (GUD) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) |  | TRA-N-955 | GUD: Complete conversion to H-gas | Gasunie Deutschland Transport Services GmbH | Less-Advanced Non-FID | No | Gasunie Deutschland Transport Services GmbH | 2030 | 137.52
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (L) (NL) (GUD) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) |  | TRA-N-951 | Embedding CS Folmhusen in H-Gas | Gasunie Deutschland Transport Services GmbH | Less-Advanced Non-FID | No | Gasunie Deutschland Transport Services GmbH | 2020 | -54.89
Cross-Border Transmission IP within EU | Bunde (DE) / Oude Statenzijl (L) (NL) (GUD) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Germany (GASPOOL) |  | TRA-N-955 | GUD: Complete conversion to H-gas | Gasunie Deutschland Transport Services GmbH | Less-Advanced Non-FID | No | Gasunie Deutschland Transport Services GmbH | 2030 | -137.52
Cross-Border Transmission IP within EU | Csanadpalota | Transmission Romania | Transmission Hungary (MGP) |  | TRA-N-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT Corridor) | SNTGN Transgaz S.A. | Less-Advanced Non-FID | Yes | SNTGN Transgaz S.A. | 2020 | 126.1
Cross-Border Transmission IP within EU | Csanadpalota | Transmission Romania | Transmission Hungary (MGP) |  | TRA-N-286 | Romanian-Hungarian reverse flow Hungarian section 1st stage | FGSZ Ltd. | Less-Advanced Non-FID | Yes | FGSZ Ltd. | 2020 | 48.9
Cross-Border Transmission IP within EU | Csanadpalota | Transmission Hungary (MGP) | Transmission Romania |  | TRA-N-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT Corridor) | SNTGN Transgaz S.A. | Less-Advanced Non-FID | Yes | SNTGN Transgaz S.A. | 2020 | 76.5
Cross-Border Transmission IP within EU | Csanadpalota | Transmission Romania | Transmission Hungary (MGP) |  | TRA-N-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | FGSZ Ltd. | Less-Advanced Non-FID | Yes | FGSZ Ltd. | 2022 | 76.5
Cross-Border Transmission IP within EU | Csanadpalota | Transmission Hungary (MGP) | Transmission Romania |  | TRA-N-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | FGSZ Ltd. | Less-Advanced Non-FID | Yes | FGSZ Ltd. | 2022 | 76.5
Cross-Border Transmission IP within EU | Csanadpalota 2 | Transmission Romania | Transmission Hungary (MGP) |  | TRA-N-959 | Further enlargement of the BG—RO—HU—AT transmission corridor (BRUA) phase 3 | SNTGN Transgaz SA | Less-Advanced Non-FID | Yes | SNTGN Transgaz S.A. | 2023 | 128.73
Cross-Border Transmission IP within EU | Csanadpalota 2 | Transmission Hungary (MGP) | Transmission Romania |  | TRA-N-959 | Further enlargement of the BG—RO—HU—AT transmission corridor (BRUA) phase 3 | SNTGN Transgaz SA | Less-Advanced Non-FID | Yes | SNTGN Transgaz S.A. | 2023 | 128.73
Cross-Border Transmission IP within EU | Csanadpalota 2 | Transmission Romania | Transmission Hungary (MGP) |  | TRA-N-380 | BG-RO-HU-AT transmission corridor | FGSZ Ltd. | Less-Advanced Non-FID | No | FGSZ Ltd. | 2024 | 145.5
Cross-Border Transmission IP within EU | Csanadpalota 2 | Transmission Hungary (MGP) | Transmission Romania |  | TRA-N-380 | BG-RO-HU-AT transmission corridor | FGSZ Ltd. | Less-Advanced Non-FID | No | FGSZ Ltd. | 2024 | 145.5
Cross-Border Transmission IP within EU | CZ/AT Border | Transmission Czech Republic (VOB) | Transmission Austria (CEGH) |  | TRA-N-135 | Connection to Oberkappel | NET4GAS, s.r.o. | Less-Advanced Non-FID | No | NET4GAS, s.r.o. | 2022 | 55
Cross-Border Transmission IP within EU | CZ/AT Border | Transmission Austria (CEGH) | Transmission Czech Republic (VOB) |  | TRA-N-135 | Connection to Oberkappel | NET4GAS, s.r.o. | Less-Advanced Non-FID | No | NET4GAS, s.r.o. | 2022 | 55
Cross-Border Transmission IP within EU | Delimara (Malta) to Sicily (Italy) Interconnection | Transmission Italy (PSV) (Italy Southern Import Fork) | Transmission Malta |  | TRA-N-031 | Connection of Malta to the European Gas Network - Pipelines | Office of the Prime Minister (Energy) | Less-Advanced Non-FID | Yes | Office of the Prime Minister (Energy) – Malta | 2026 | 56
Cross-Border Transmission IP within EU | Delimara (Malta) to Sicily (Italy) Interconnection | Transmission Malta | Transmission Italy (PSV) (Italy Southern Import Fork) |  | TRA-N-031 | Connection of Malta to the European Gas Network - Pipelines | Office of the Prime Minister (Energy) | Less-Advanced Non-FID | Yes | Office of the Prime Minister (Energy) – Malta | 2026 | 56
Cross-Border Transmission IP within EU | Dravaszerdahely | Transmission Croatia | Transmission Hungary (MGP) |  | TRA-N-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | Plinacro Ltd | Advanced Non-FID | No | Plinacro Ltd | 2018 | 47
Cross-Border Transmission IP within EU | Dravaszerdahely | Transmission Croatia | Transmission Hungary (MGP) |  | TRA-N-075 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Plinacro Ltd | Advanced Non-FID | Yes | Plinacro Ltd | 2020 | 45
Cross-Border Transmission IP within EU | Dravaszerdahely | Transmission Hungary (MGP) | Transmission Croatia |  | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | Plinacro Ltd | Less-Advanced Non-FID | Yes | Plinacro Ltd | 2020 | 56.3
Cross-Border Transmission IP within EU | Dravaszerdahely | Transmission Croatia | Transmission Hungary (MGP) |  | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | Plinacro Ltd | Less-Advanced Non-FID | Yes | Plinacro Ltd | 2020 | 39
Cross-Border Transmission IP within EU | Dravaszerdahely | Transmission Hungary (MGP) | Transmission Croatia |  | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | Plinacro Ltd | Less-Advanced Non-FID | Yes | Plinacro Ltd | 2023 | 51
Cross-Border Transmission IP within EU | Dravaszerdahely | Transmission Croatia | Transmission Hungary (MGP) |  | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | Plinacro Ltd | Less-Advanced Non-FID | Yes | Plinacro Ltd | 2023 | 53
Cross-Border Transmission IP within EU | East Med / Crete (GR) | Transmission Greece (Crete) | Transmission East Med Greece |  | TRA-N-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Less-Advanced Non-FID | Yes | IGI Poseidon S.A. | 2020 | 190
Cross-Border Transmission IP within EU | East Med / Crete (GR) | Transmission East Med Greece | Transmission Greece (Crete) |  | TRA-N-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Less-Advanced Non-FID | Yes | IGI Poseidon S.A. | 2020 | 20
Cross-Border Transmission IP within EU | East Med / Cyprus (CY) | Transmission East Med Greece | Transmission Cyprus |  | TRA-N-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Less-Advanced Non-FID | Yes | IGI Poseidon S.A. | 2020 | 30
Cross-Border Transmission IP within EU | East Med / Peloponnesus (GR) | Transmission East Med Greece | Transmission Greece |  | TRA-N-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Less-Advanced Non-FID | Yes | IGI Poseidon S.A. | 2020 | 90
Cross-Border Transmission IP within EU | East Med / Peloponnesus (GR) | Transmission East Med Greece | Transmission Greece |  | TRA-N-1091 | Metering and Regulating station at Megalopoli | DESFA S.A. | Less-Advanced Non-FID | No | DESFA S.A. | 2022 | 90
Cross-Border Transmission IP within EU | East Med / Thesprotia (Poseidon) | Transmission East Med Greece | Transmission ITGI Poseidon Greece |  | TRA-N-010 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced Non-FID | Yes | IGI Poseidon S.A. | 2020 | 320
Cross-Border Transmission IP within EU | East Med / Thesprotia (Poseidon) | Transmission ITGI Poseidon Greece | Transmission East Med Greece |  | TRA-N-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Less-Advanced Non-FID | Yes | IGI Poseidon S.A. | 2020 | 320
Cross-Border Transmission IP within EU | Eastring Cross-Border BG/EAR <> RO/EAR | Transmission Eastring Bulgaria | Transmission Eastring Romania |  | TRA-N-654 | Eastring - Bulgaria | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | Bulgartransgaz EAD | 2021 | 570
Cross-Border Transmission IP within EU | Eastring Cross-Border BG/EAR <> RO/EAR | Transmission Eastring Bulgaria | Transmission Eastring Romania |  | TRA-N-655 | Eastring - Romania | SNTGN Transgaz SA | Less-Advanced Non-FID | Yes | SNTGN Transgaz S.A. | 2021 | 570
Cross-Border Transmission IP within EU | Eastring Cross-Border BG/EAR <> RO/EAR | Transmission Eastring Romania | Transmission Eastring Bulgaria |  | TRA-N-654 | Eastring - Bulgaria | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | Bulgartransgaz EAD | 2021 | 570
Cross-Border Transmission IP within EU | Eastring Cross-Border BG/EAR <> RO/EAR | Transmission Eastring Romania | Transmission Eastring Bulgaria |  | TRA-N-655 | Eastring - Romania | SNTGN Transgaz SA | Less-Advanced Non-FID | Yes | SNTGN Transgaz S.A. | 2021 | 570
Cross-Border Transmission IP within EU | Eastring Cross-Border BG/EAR <> RO/EAR | Transmission Eastring Bulgaria | Transmission Eastring Romania |  | TRA-N-655 | Eastring - Romania | SNTGN Transgaz SA | Less-Advanced Non-FID | Yes | SNTGN Transgaz S.A. | 2025 | 570
Cross-Border Transmission IP within EU | Eastring Cross-Border BG/EAR <> RO/EAR | Transmission Eastring Bulgaria | Transmission Eastring Romania |  | TRA-N-654 | Eastring - Bulgaria | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | Bulgartransgaz EAD | 2025 | 570
Cross-Border Transmission IP within EU | Eastring Cross-Border BG/EAR <> RO/EAR | Transmission Eastring Romania | Transmission Eastring Bulgaria |  | TRA-N-655 | Eastring - Romania | SNTGN Transgaz SA | Less-Advanced Non-FID | Yes | SNTGN Transgaz S.A. | 2025 | 570
Cross-Border Transmission IP within EU | Eastring Cross-Border BG/EAR <> RO/EAR | Transmission Eastring Romania | Transmission Eastring Bulgaria |  | TRA-N-654 | Eastring - Bulgaria | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | Bulgartransgaz EAD | 2025 | 570
Cross-Border Transmission IP within EU | Eastring Cross-Border HU/EAR <> SK/EAR | Transmission Eastring Slovakia | Transmission Eastring Hungary (MGP) |  | TRA-N-628 | Eastring - Slovakia | Eastring B.V. | Less-Advanced Non-FID | Yes | Eastring B.V. | 2021 | 570
Cross-Border Transmission IP within EU | Eastring Cross-Border HU/EAR <> SK/EAR | Transmission Eastring Slovakia | Transmission Eastring Hungary (MGP) |  | TRA-N-656 | Eastring - Hungary | FGSZ Ltd. | Less-Advanced Non-FID | Yes | FGSZ Ltd. | 2021 | 570
Cross-Border Transmission IP within EU | Eastring Cross-Border HU/EAR <> SK/EAR | Transmission Eastring Hungary (MGP) | Transmission Eastring Slovakia |  | TRA-N-628 | Eastring - Slovakia | Eastring B.V. | Less-Advanced Non-FID | Yes | Eastring B.V. | 2021 | 570
Cross-Border Transmission IP within EU | Eastring Cross-Border HU/EAR <> SK/EAR | Transmission Eastring Hungary (MGP) | Transmission Eastring Slovakia |  | TRA-N-656 | Eastring - Hungary | FGSZ Ltd. | Less-Advanced Non-FID | Yes | FGSZ Ltd. | 2021 | 570
Cross-Border Transmission IP within EU | Eastring Cross-Border HU/EAR <> SK/EAR | Transmission Eastring Slovakia | Transmission Eastring Hungary (MGP) |  | TRA-N-628 | Eastring - Slovakia | Eastring B.V. | Less-Advanced Non-FID | Yes | Eastring B.V. | 2025 | 570
Cross-Border Transmission IP within EU | Eastring Cross-Border HU/EAR <> SK/EAR | Transmission Eastring Slovakia | Transmission Eastring Hungary (MGP) |  | TRA-N-656 | Eastring - Hungary | FGSZ Ltd. | Less-Advanced Non-FID | Yes | FGSZ Ltd. | 2025 | 570
Cross-Border Transmission IP within EU | Eastring Cross-Border HU/EAR <> SK/EAR | Transmission Eastring Hungary (MGP) | Transmission Eastring Slovakia |  | TRA-N-628 | Eastring - Slovakia | Eastring B.V. | Less-Advanced Non-FID | Yes | Eastring B.V. | 2025 | 570
Cross-Border Transmission IP within EU | Eastring Cross-Border HU/EAR <> SK/EAR | Transmission Eastring Hungary (MGP) | Transmission Eastring Slovakia |  | TRA-N-656 | Eastring - Hungary | FGSZ Ltd. | Less-Advanced Non-FID | Yes | FGSZ Ltd. | 2025 | 570
Cross-Border Transmission IP within EU | Eastring Cross-Border RO/EAR <> HU/EAR | Transmission Eastring Hungary (MGP) | Transmission Eastring Romania |  | TRA-N-656 | Eastring - Hungary | FGSZ Ltd. | Less-Advanced Non-FID | Yes | FGSZ Ltd. | 2021 | 570
Cross-Border Transmission IP within EU | Eastring Cross-Border RO/EAR <> HU/EAR | Transmission Eastring Hungary (MGP) | Transmission Eastring Romania |  | TRA-N-655 | Eastring - Romania | SNTGN Transgaz SA | Less-Advanced Non-FID | Yes | SNTGN Transgaz S.A. | 2021 | 570
Cross-Border Transmission IP within EU | Eastring Cross-Border RO/EAR <> HU/EAR | Transmission Eastring Romania | Transmission Eastring Hungary (MGP) |  | TRA-N-656 | Eastring - Hungary | FGSZ Ltd. | Less-Advanced Non-FID | Yes | FGSZ Ltd. | 2021 | 570
Cross-Border Transmission IP within EU | Eastring Cross-Border RO/EAR <> HU/EAR | Transmission Eastring Romania | Transmission Eastring Hungary (MGP) |  | TRA-N-655 | Eastring - Romania | SNTGN Transgaz SA | Less-Advanced Non-FID | Yes | SNTGN Transgaz S.A. | 2021 | 570
Cross-Border Transmission IP within EU | Eastring Cross-Border RO/EAR <> HU/EAR | Transmission Eastring Hungary (MGP) | Transmission Eastring Romania |  | TRA-N-656 | Eastring - Hungary | FGSZ Ltd. | Less-Advanced Non-FID | Yes | FGSZ Ltd. | 2025 | 570
Cross-Border Transmission IP within EU | Eastring Cross-Border RO/EAR <> HU/EAR | Transmission Eastring Hungary (MGP) | Transmission Eastring Romania |  | TRA-N-655 | Eastring - Romania | SNTGN Transgaz SA | Less-Advanced Non-FID | Yes | SNTGN Transgaz S.A. | 2025 | 570
Cross-Border Transmission IP within EU | Eastring Cross-Border RO/EAR <> HU/EAR | Transmission Eastring Romania | Transmission Eastring Hungary (MGP) |  | TRA-N-656 | Eastring - Hungary | FGSZ Ltd. | Less-Advanced Non-FID | Yes | FGSZ Ltd. | 2025 | 570
Cross-Border Transmission IP within EU | Eastring Cross-Border RO/EAR <> HU/EAR | Transmission Eastring Romania | Transmission Eastring Hungary (MGP) |  | TRA-N-655 | Eastring - Romania | SNTGN Transgaz SA | Less-Advanced Non-FID | Yes | SNTGN Transgaz S.A. | 2025 | 570
Cross-Border Transmission IP within EU | Eastring SK/EAR <-> Veľké Kapušany | Transmission Slovakia | Transmission Eastring Slovakia |  | TRA-N-628 | Eastring - Slovakia | Eastring B.V. | Less-Advanced Non-FID | Yes | Eastring B.V. | 2021 | 570
Cross-Border Transmission IP within EU | Eastring SK/EAR <-> Veľké Kapušany | Transmission Eastring Slovakia | Transmission Slovakia |  | TRA-N-628 | Eastring - Slovakia | Eastring B.V. | Less-Advanced Non-FID | Yes | Eastring B.V. | 2021 | 570
Cross-Border Transmission IP within EU | Eastring SK/EAR <-> Veľké Kapušany | Transmission Slovakia | Transmission Eastring Slovakia |  | TRA-N-628 | Eastring - Slovakia | Eastring B.V. | Less-Advanced Non-FID | Yes | Eastring B.V. | 2025 | 570
Cross-Border Transmission IP within EU | Eastring SK/EAR <-> Veľké Kapušany | Transmission Eastring Slovakia | Transmission Slovakia |  | TRA-N-628 | Eastring - Slovakia | Eastring B.V. | Less-Advanced Non-FID | Yes | Eastring B.V. | 2025 | 570
Cross-Border Transmission IP within EU | GCP GAZ-SYSTEM/ONTRAS | Transmission Poland (VTP - GAZ-SYSTEM) | Transmission Germany (GASPOOL) |  | TRA-N-814 | Upgrade IP Deutschneudorf and Lasow | ONTRAS Gastransport GmbH | Advanced Non-FID | No | ONTRAS Gastransport GmbH | 2016 | 26.6
Cross-Border Transmission IP within EU | GCP GAZ-SYSTEM/ONTRAS | Transmission Poland (VTP - GAZ-SYSTEM) | Transmission Germany (GASPOOL) |  | TRA-N-814 | Upgrade IP Deutschneudorf and Lasow | ONTRAS Gastransport GmbH | Advanced Non-FID | No | ONTRAS Gastransport GmbH | 2019 | 45.4
Cross-Border Transmission IP within EU | GCP GAZ-SYSTEM/ONTRAS | Transmission Germany (GASPOOL) | Transmission Poland (VTP - GAZ-SYSTEM) |  | TRA-N-814 | Upgrade IP Deutschneudorf and Lasow | ONTRAS Gastransport GmbH | Advanced Non-FID | No | ONTRAS Gastransport GmbH | 2019 | 14.4
Cross-Border Transmission IP within EU | Gorizia (IT) /Šempeter (SI) | Transmission Italia (PSV) | Transmission Slovenia |  | TRA-N-108 | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia | Plinovodi d.o.o. | Less-Advanced Non-FID | No | Plinovodi d.o.o. | 2020 | 35.5
Cross-Border Transmission IP within EU | Gorizia (IT) /Šempeter (SI) | Transmission Slovenia | Transmission Italia (PSV) |  | TRA-N-108 | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia | Plinovodi d.o.o. | Less-Advanced Non-FID | No | Plinovodi d.o.o. | 2020 | 38
Cross-Border Transmission IP within EU | Gorizia (IT) /Šempeter (SI) (Planned) | Transmission Italy (PSV) (Northern Projects) | Transmission Slovenia |  | TRA-N-099 | M3/1a Šempeter - Ajdovščina | Plinovodi d.o.o. | Less-Advanced Non-FID | No | Plinovodi d.o.o. | 2022 | 340
Cross-Border Transmission IP within EU | Gorizia (IT) /Šempeter (SI) (Planned) | Transmission Slovenia | Transmission Italy (PSV) (Northern Projects) |  | TRA-N-099 | M3/1a Šempeter - Ajdovščina | Plinovodi d.o.o. | Less-Advanced Non-FID | No | Plinovodi d.o.o. | 2022 | 340
Cross-Border Transmission IP within EU | Hať | Transmission Poland (VTP - GAZ-SYSTEM) | Transmission Czech Republic (VOB) |  | TRA-N-273 | Poland - Czech Republic interconnection (PL section) | GAZ-SYSTEM S.A. | Advanced Non-FID | Yes | GAZ-SYSTEM S.A. | 2019 | 153.2
Cross-Border Transmission IP within EU | Hať | Transmission Poland (VTP - GAZ-SYSTEM) | Transmission Czech Republic (VOB) |  | TRA-N-136 | Poland-Czech Republic Interconnection (CZ) | NET4GAS, s.r.o. | Advanced Non-FID | Yes | NET4GAS, s.r.o. | 2019 | 153.2
Cross-Border Transmission IP within EU | Hať | Transmission Czech Republic (VOB) | Transmission Poland (VTP - GAZ-SYSTEM) |  | TRA-N-136 | Poland-Czech Republic Interconnection (CZ) | NET4GAS, s.r.o. | Advanced Non-FID | Yes | NET4GAS, s.r.o. | 2019 | 219.1
Cross-Border Transmission IP within EU | Hať | Transmission Czech Republic (VOB) | Transmission Poland (VTP - GAZ-SYSTEM) |  | TRA-N-273 | Poland - Czech Republic interconnection (PL section) | GAZ-SYSTEM S.A. | Advanced Non-FID | Yes | GAZ-SYSTEM S.A. | 2019 | 219.1
Cross-Border Transmission IP within EU | Hora Svaté Kateřiny (CZ) / Deutschneudorf (Sayda) (DE) | Transmission Germany (GASPOOL) | Transmission Czech Republic (VOB) |  | TRA-N-814 | Upgrade IP Deutschneudorf and Lasow | ONTRAS Gastransport GmbH | Advanced Non-FID | No | ONTRAS Gastransport GmbH | 2019 | 55.2
Cross-Border Transmission IP within EU | HSK-EUGAL (CZ) / Deutschneudorf 2 (DE) | Transmission Germany (GASPOOL) | Transmission Czech Republic (VOB) |  | TRA-N-752 | Capacity4Gas (C4G) – DE/CZ | NET4GAS, s.r.o. | Advanced Non-FID | No | NET4GAS, s.r.o. | 2019 | 508.6
Cross-Border Transmission IP within EU | HSK-EUGAL (CZ) / Deutschneudorf 2 (DE) | Transmission Germany (GASPOOL) | Transmission Czech Republic (VOB) |  | TRA-N-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | GASCADE Gastransport GmbH | Advanced Non-FID | No | GASCADE Gastransport GmbH | 2019 | 661.2
Cross-Border Transmission IP within EU | HSK-EUGAL (CZ) / Deutschneudorf 2 (DE) | Transmission Germany (GASPOOL) | Transmission Czech Republic (VOB) |  | TRA-N-752 | Capacity4Gas (C4G) – DE/CZ | NET4GAS, s.r.o. | Advanced Non-FID | No | NET4GAS, s.r.o. | 2020 | 855.4
Cross-Border Transmission IP within EU | HSK-EUGAL (CZ) / Deutschneudorf 2 (DE) | Transmission Germany (GASPOOL) | Transmission Czech Republic (VOB) |  | TRA-N-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | GASCADE Gastransport GmbH | Advanced Non-FID | No | GASCADE Gastransport GmbH | 2020 | 535.2
Cross-Border Transmission IP within EU | HSK-EUGAL (CZ) / Deutschneudorf 2 (DE) | Transmission Germany (GASPOOL) | Transmission Czech Republic (VOB) |  | TRA-N-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | GASCADE Gastransport GmbH | Advanced Non-FID | No | GASCADE Gastransport GmbH | 2021 | 214.8
Cross-Border Transmission IP within EU | Interconnector PL - SK | Transmission Slovakia | Transmission Poland (VTP - GAZ-SYSTEM) |  | TRA-N-275 | Poland - Slovakia interconnection (PL section) | GAZ-SYSTEM S.A. | Advanced Non-FID | Yes | GAZ-SYSTEM S.A. | 2019 | 174.5
Cross-Border Transmission IP within EU | Interconnector PL - SK | Transmission Poland (VTP - GAZ-SYSTEM) | Transmission Slovakia |  | TRA-N-275 | Poland - Slovakia interconnection (PL section) | GAZ-SYSTEM S.A. | Advanced Non-FID | Yes | GAZ-SYSTEM S.A. | 2019 | 143.9
Cross-Border Transmission IP within EU | Interconnector PL - SK | Transmission Poland (VTP - GAZ-SYSTEM) | Transmission Slovakia |  | TRA-N-190 | Poland - Slovakia interconnection | eustream, a.s. | Advanced Non-FID | Yes | eustream, a.s. | 2019 | 143.96
Cross-Border Transmission IP within EU | Interconnector PL - SK | Transmission Slovakia | Transmission Poland (VTP - GAZ-SYSTEM) |  | TRA-N-190 | Poland - Slovakia interconnection | eustream, a.s. | Advanced Non-FID | Yes | eustream, a.s. | 2019 | 174.59
Cross-Border Transmission IP within EU | Interconnector PL-DK | Transmission Denmark | Transmission Poland (VTP - GAZ-SYSTEM) |  | TRA-N-428 | (Mirror) Baltic Pipe | Energinet.dk | Less-Advanced Non-FID | Yes | Energinet.dk | 2022 | 306.8
Cross-Border Transmission IP within EU | Interconnector PL-DK | Transmission Denmark | Transmission Poland (VTP - GAZ-SYSTEM) |  | TRA-N-780 | Nybro-Interconnector PL-DK - reinforcement | Energinet.dk | Less-Advanced Non-FID | No | Energinet.dk | 2022 | 0.1
Cross-Border Transmission IP within EU | Interconnector PL-DK | Transmission Denmark | Transmission Poland (VTP - GAZ-SYSTEM) |  | TRA-N-271 | Poland - Denmark interconnection (Baltic Pipe) - PL section | GAZ-SYSTEM S.A. | Less-Advanced Non-FID | Yes | GAZ-SYSTEM S.A. | 2022 | 306.8
Cross-Border Transmission IP within EU | Interconnector PL-DK | Transmission Poland (VTP - GAZ-SYSTEM) | Transmission Denmark |  | TRA-N-271 | Poland - Denmark interconnection (Baltic Pipe) - PL section | GAZ-SYSTEM S.A. | Less-Advanced Non-FID | Yes | GAZ-SYSTEM S.A. | 2022 | 91.1
Cross-Border Transmission IP within EU | Interconnector PL-DK | Transmission Poland (VTP - GAZ-SYSTEM) | Transmission Denmark |  | TRA-N-428 | (Mirror) Baltic Pipe | Energinet.dk | Less-Advanced Non-FID | Yes | Energinet.dk | 2022 | 91.1
Cross-Border Transmission IP within EU | Interconnector PL-DK | Transmission Poland (VTP - GAZ-SYSTEM) | Transmission Denmark |  | TRA-N-780 | Nybro-Interconnector PL-DK - reinforcement | Energinet.dk | Less-Advanced Non-FID | No | Energinet.dk | 2022 | 0.1
Cross-Border Transmission IP within EU | Interconnector PL-LT | Transmission Poland (VTP - GAZ-SYSTEM) | Transmission Lithuania |  | TRA-N-341 | Gas Interconnection Poland-Lithuania (GIPL) (Lithuania's section) | AB Amber Grid | Advanced Non-FID | Yes | AB Amber Grid | 2019 | 73.92
Cross-Border Transmission IP within EU | Interconnector PL-LT | Transmission Poland (VTP - GAZ-SYSTEM) | Transmission Lithuania |  | TRA-N-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | GAZ-SYSTEM S.A. | Advanced Non-FID | Yes | GAZ-SYSTEM S.A. | 2019 | 73.9
Cross-Border Transmission IP within EU | Interconnector PL-LT | Transmission Lithuania | Transmission Poland (VTP - GAZ-SYSTEM) |  | TRA-N-341 | Gas Interconnection Poland-Lithuania (GIPL) (Lithuania's section) | AB Amber Grid | Advanced Non-FID | Yes | AB Amber Grid | 2019 | 51.07
Cross-Border Transmission IP within EU | Interconnector PL-LT | Transmission Lithuania | Transmission Poland (VTP - GAZ-SYSTEM) |  | TRA-N-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | GAZ-SYSTEM S.A. | Advanced Non-FID | Yes | GAZ-SYSTEM S.A. | 2019 | 51.1
Cross-Border Transmission IP within EU | Ionic-Adriatic Pipeline - IAP / Split - HR | Transmission Croatia | Transmission Ionic-Adriatic Pipeline Croatia |  | TRA-N-068 | Ionian Adriatic Pipeline | Plinacro Ltd | Advanced Non-FID | No | Plinacro Ltd | 2022 | 75
Cross-Border Transmission IP within EU | Ionic-Adriatic Pipeline - IAP / Split - HR | Transmission Ionic-Adriatic Pipeline Croatia | Transmission Croatia |  | TRA-N-068 | Ionian Adriatic Pipeline | Plinacro Ltd | Advanced Non-FID | No | Plinacro Ltd | 2023 | 75
Cross-Border Transmission IP within EU | Ionic-Adriatic Pipeline - IAP Entry | Transmission Ionic-Adriatic Pipeline Croatia (TAP-IAP Interconnection) | Transmission Ionic-Adriatic Pipeline Croatia |  | TRA-N-068 | Ionian Adriatic Pipeline | Plinacro Ltd | Advanced Non-FID | No | Plinacro Ltd | 2023 | 150
Cross-Border Transmission IP within EU | Karksi | Transmission Estonia | Transmission Latvia |  | TRA-N-915 | Enhancement of Estonia-Latvia interconnection | Elering AS | Advanced Non-FID | Yes | Elering AS | 2019 | 112
Cross-Border Transmission IP within EU | Karksi | Transmission Latvia | Transmission Estonia |  | TRA-N-915 | Enhancement of Estonia-Latvia interconnection | Elering AS | Advanced Non-FID | Yes | Elering AS | 2019 | 49
Cross-Border Transmission IP within EU | Kiemenai | Transmission Lithuania | Transmission Latvia |  | TRA-N-342 | Enhancement of Latvia-Lithuania interconnection (Lithuania's part) | AB Amber Grid | Less-Advanced Non-FID | Yes | AB Amber Grid | 2020 | 57.4
Cross-Border Transmission IP within EU | Kiemenai | Transmission Lithuania | Transmission Latvia |  | TRA-N-382 | Enhancement of Latvia-Lithuania interconnection (Latvian part) | JSC "Latvijas Gaze" | Less-Advanced Non-FID | Yes | Latvijas Gaze | 2020 | 57.41
Cross-Border Transmission IP within EU | Kiemenai | Transmission Latvia | Transmission Lithuania |  | TRA-N-342 | Enhancement of Latvia-Lithuania interconnection (Lithuania's part) | AB Amber Grid | Less-Advanced Non-FID | Yes | AB Amber Grid | 2020 | 60
Cross-Border Transmission IP within EU | Kiemenai | Transmission Latvia | Transmission Lithuania |  | TRA-N-382 | Enhancement of Latvia-Lithuania interconnection (Latvian part) | JSC "Latvijas Gaze" | Less-Advanced Non-FID | Yes | Latvijas Gaze | 2020 | 59.9
Cross-Border Transmission IP within EU | Komotini - TAP / IGB | Transmission Trans-Adriatic Pipeline Greece | Transmission Interconnector Greece-Bulgaria Bulgaria |  | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | ICGB a.d. | FID | Yes | ICGB a.d. | 2018 | 90
Cross-Border Transmission IP within EU | Komotini - TAP / IGB | Transmission Trans-Adriatic Pipeline Greece | Transmission Interconnector Greece-Bulgaria Bulgaria |  | TRA-F-051 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | FID | Yes | Trans-Adriatic Pipeline AG | 2019 | 142
Cross-Border Transmission IP within EU | Komotini - TAP / IGB | Transmission Trans-Adriatic Pipeline Greece | Transmission Interconnector Greece-Bulgaria Bulgaria |  | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | ICGB a.d. | FID | Yes | ICGB a.d. | 2021 | 60.5
Cross-Border Transmission IP within EU | Komotini (DESFA) - GR / IGB | Transmission Greece (Komotini) | Transmission Interconnector Greece-Bulgaria Bulgaria |  | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | ICGB a.d. | FID | Yes | ICGB a.d. | 2018 | 90
Cross-Border Transmission IP within EU | Komotini (DESFA) - GR / IGB | Transmission Greece (Komotini) | Transmission Interconnector Greece-Bulgaria Bulgaria |  | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | ICGB a.d. | FID | Yes | ICGB a.d. | 2021 | 60.5
Cross-Border Transmission IP within EU | Komotini (DESFA) - GR / IGB | Transmission Greece (Komotini) | Transmission Interconnector Greece-Bulgaria Bulgaria |  | TRA-N-957 | Metering Station at Komotini to IGB | DESFA S.A. | Less-Advanced Non-FID | No | DESFA S.A. | 2020 | 206.4
Cross-Border Transmission IP within EU | Komotini (DESFA) - GR / TAP | Transmission Trans-Adriatic Pipeline Greece | Transmission Greece (Komotini) |  | TRA-N-940 | Metering and Regulating station at Komotini | DESFA S.A. | Less-Advanced Non-FID | Yes | DESFA S.A. | 2020 | 0
Cross-Border Transmission IP within EU | Kulata (BG) / Sidirokastron (GR) | Transmission Bulgarian Transit Bulgaria (GTNTT) | Transmission Greece |  | TRA-N-298 | Rehabilitation, Modernization and Expansion of the NTS | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | Bulgartransgaz EAD | 2020 | 13.78
Cross-Border Transmission IP within EU | Lanžhot | Transmission Czech Republic (VOB) | Transmission Slovakia |  | TRA-N-902 | Capacity increase at IP Lanžhot entry | eustream, a.s. | Advanced Non-FID | No | eustream, a.s. | 2019 | 780
Cross-Border Transmission IP within EU | Lanžhot | Transmission Czech Republic (VOB) | Transmission Slovakia |  | TRA-N-918 | Capacity4Gas (C4G) – CZ/SK | NET4GAS, s.r.o. | Advanced Non-FID | No | NET4GAS, s.r.o. | 2019 | 650
Cross-Border Transmission IP within EU | Mallnow | Transmission Germany (GASPOOL) | Transmission Yamal Poland (VTP - GAZ-SYSTEM) |  | TRA-N-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | GASCADE Gastransport GmbH | Advanced Non-FID | No | GASCADE Gastransport GmbH | 2019 | 138.6
Cross-Border Transmission IP within EU | Mallnow | Transmission Germany (GASPOOL) | Transmission Yamal Poland (VTP - GAZ-SYSTEM) |  | TRA-N-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | GASCADE Gastransport GmbH | Advanced Non-FID | No | GASCADE Gastransport GmbH | 2020 | 112.1
Cross-Border Transmission IP within EU | Mallnow | Transmission Germany (GASPOOL) | Transmission Yamal Poland (VTP - GAZ-SYSTEM) |  | TRA-N-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | GASCADE Gastransport GmbH | Advanced Non-FID | No | GASCADE Gastransport GmbH | 2021 | 85.8
Cross-Border Transmission IP within EU | Melendugno - IT / TAP | Transmission Trans-Adriatic Pipeline Greece | Transmission Italy (PSV) (Southern Projects) |  | TRA-F-051 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | FID | Yes | Trans-Adriatic Pipeline AG | 2019 | 334
Cross-Border Transmission IP within EU | Moffat | Transmission United Kingdom (NBP) (Moffat) | Transmission United Kingdom (NBP) |  | TRA-N-1064 | Moffat Physical Reverse Flow | National Grid Gas plc | Less-Advanced Non-FID | Yes | National Grid Gas plc | 2020 | 38.5
Cross-Border Transmission IP within EU | Moffat (IE) | Transmission Ireland (IBP) | Transmission United Kingdom (NBP) (Moffat) |  | TRA-N-829 | PCI 5.1.1 Physical Reverse Flow at Moffat interconnection point (IE/UK) | GNI (UK) Limited | Less-Advanced Non-FID | Yes | Gas Networks Ireland | 2020 | 38.5
Cross-Border Transmission IP within EU | Mosonmagyarovar | Transmission Hungary (MGP) | Transmission Austria (CEGH) |  | TRA-N-423 | GCA Mosonmagyaróvár | GAS CONNECT AUSTRIA GmbH | Advanced Non-FID | Yes | Gas Connect Austria GmbH | 2020 | 153.08
Cross-Border Transmission IP within EU | Mosonmagyarovar | Transmission Austria (CEGH) | Transmission Hungary (MGP) |  | TRA-N-018 | Városföld-Ercsi-Győr | FGSZ Ltd. | Less-Advanced Non-FID | Yes | FGSZ Ltd. | 2022 | 25
Cross-Border Transmission IP within EU | Mosonmagyarovar | Transmission Hungary (MGP) | Transmission Austria (CEGH) |  | TRA-N-018 | Városföld-Ercsi-Győr | FGSZ Ltd. | Less-Advanced Non-FID | Yes | FGSZ Ltd. | 2022 | 153
Cross-Border Transmission IP within EU | Mosonmagyarovar 2 | Transmission Austria (CEGH) | Transmission Hungary (MGP) |  | TRA-N-380 | BG-RO-HU-AT transmission corridor | FGSZ Ltd. | Less-Advanced Non-FID | No | FGSZ Ltd. | 2024 | 145.5
Cross-Border Transmission IP within EU | Mosonmagyarovar 2 | Transmission Hungary (MGP) | Transmission Austria (CEGH) |  | TRA-N-380 | BG-RO-HU-AT transmission corridor | FGSZ Ltd. | Less-Advanced Non-FID | No | FGSZ Ltd. | 2024 | 145.5
Cross-Border Transmission IP within EU | Murfeld (AT) / Ceršak (SI) | Transmission Slovenia | Transmission Austria (CEGH) |  | TRA-N-361 | GCA 2015/08: Entry/Exit Murfeld | GAS CONNECT AUSTRIA GmbH | Advanced Non-FID | Yes | Gas Connect Austria GmbH | 2019 | 166.507
Cross-Border Transmission IP within EU | Murfeld (AT) / Ceršak (SI) | Transmission Austria (CEGH) | Transmission Slovenia |  | TRA-N-361 | GCA 2015/08: Entry/Exit Murfeld | GAS CONNECT AUSTRIA GmbH | Advanced Non-FID | Yes | Gas Connect Austria GmbH | 2019 | 53.712
Cross-Border Transmission IP within EU | Murfeld (AT) / Ceršak (SI) | Transmission Austria (CEGH) | Transmission Slovenia |  | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak) | Plinovodi d.o.o. | Less-Advanced Non-FID | Yes | Plinovodi d.o.o. | 2020 | 78.7
Cross-Border Transmission IP within EU | Murfeld (AT) / Ceršak (SI) | Transmission Slovenia | Transmission Austria (CEGH) |  | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak) | Plinovodi d.o.o. | Less-Advanced Non-FID | Yes | Plinovodi d.o.o. | 2020 | 165
Cross-Border Transmission IP within EU | Nea Mesimvria | Transmission Trans-Adriatic Pipeline Greece | Transmission Greece |  | TRA-F-051 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | FID | Yes | Trans-Adriatic Pipeline AG | 2019 | 142
Cross-Border Transmission IP within EU | Nea Mesimvria | Transmission Greece | Transmission Trans-Adriatic Pipeline Greece |  | TRA-F-051 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | FID | Yes | Trans-Adriatic Pipeline AG | 2019 | 142
Cross-Border Transmission IP within EU | Nea Mesimvria | Transmission Trans-Adriatic Pipeline Greece | Transmission Greece |  | TRA-N-941 | Metering and Regulating station at Nea Messimvria | DESFA S.A. | Less-Advanced Non-FID | Yes | DESFA S.A. | 2019 | 142
Cross-Border Transmission IP within EU | Nea Mesimvria | Transmission Greece | Transmission Trans-Adriatic Pipeline Greece |  | TRA-N-971 | Compressor station at Nea Messimvria | DESFA S.A. | Less-Advanced Non-FID | No | DESFA S.A. | 2022 | 142
Cross-Border Transmission IP within EU | New IP Bulgaria (BG) / Romania (RO) (3) | Transmission Romania | Transmission Bulgaria (NGTS) |  | TRA-N-379 | ​A project for the construction of a gas pipeline BG-RO | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | Bulgartransgaz EAD | 2018 | 85
Cross-Border Transmission IP within EU | New IP Bulgaria (BG) / Romania (RO) (3) | Transmission Bulgaria (NGTS) | Transmission Romania |  | TRA-N-379 | ​A project for the construction of a gas pipeline BG-RO | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | Bulgartransgaz EAD | 2018 | 85
Cross-Border Transmission IP within EU | Obergailbach (FR) / Medelsheim (DE) | Transmission France (PEG North) | Transmission France (PEG North) (Medelsheim) |  | TRA-N-047 | Reverse capacity from France to Germany at Obergailbach | GRTgaz | Less-Advanced Non-FID | Yes | GRTgaz | 2022 | 100
Cross-Border Transmission IP within EU | Olbia (Galsi) | Transmission GALSI Italia (National) | Transmission Italy (Sardinia) |  | TRA-N-012 | GALSI Pipeline Project | Galsi S.p.A. | Advanced Non-FID | Yes | Galsi S.p.A. | 2019 | 32
Cross-Border Transmission IP within EU | Olbia (Galsi) | Transmission Italy (Sardinia) | Transmission GALSI Italia (National) |  | TRA-N-012 | GALSI Pipeline Project | Galsi S.p.A. | Advanced Non-FID | Yes | Galsi S.p.A. | 2019 | 258
Cross-Border Transmission IP within EU | Oryahovo | Transmission Varna-Oryahovo Bulgaria | Transmission Romania |  | TRA-N-593 | Varna-Oryahovo gas pipeline | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | Bulgartransgaz EAD | 2022 | 1366
Cross-Border Transmission IP within EU | Otranto - IT / IGI Poseidon | Transmission ITGI Poseidon Greece | Transmission Italy (PSV) (Southern Projects) |  | TRA-N-010 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced Non-FID | Yes | IGI Poseidon S.A. | 2020 | 329.4
Cross-Border Transmission IP within EU | Otranto - IT / IGI Poseidon | Transmission Italy (PSV) (Southern Projects) | Transmission ITGI Poseidon Greece |  | TRA-N-010 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced Non-FID | Yes | IGI Poseidon S.A. | 2020 | 252.5
Cross-Border Transmission IP within EU | Pince (SI) / Tornyszentmiklos (HU) | Transmission Hungary (MGP) | Transmission Slovenia |  | TRA-N-325 | Slovenian-Hungarian interconnector | FGSZ Ltd. | Less-Advanced Non-FID | Yes | FGSZ Ltd. | 2020 | 38.2
Cross-Border Transmission IP within EU | Pince (SI) / Tornyszentmiklos (HU) | Transmission Hungary (MGP) | Transmission Slovenia |  | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Plinovodi d.o.o. | Less-Advanced Non-FID | Yes | Plinovodi d.o.o. | 2020 | 38.1
Cross-Border Transmission IP within EU | Pince (SI) / Tornyszentmiklos (HU) | Transmission Slovenia | Transmission Hungary (MGP) |  | TRA-N-325 | Slovenian-Hungarian interconnector | FGSZ Ltd. | Less-Advanced Non-FID | Yes | FGSZ Ltd. | 2020 | 38.2
Cross-Border Transmission IP within EU | Pince (SI) / Tornyszentmiklos (HU) | Transmission Slovenia | Transmission Hungary (MGP) |  | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Plinovodi d.o.o. | Less-Advanced Non-FID | Yes | Plinovodi d.o.o. | 2020 | 38.1
Cross-Border Transmission IP within EU | Piombino (Galsi) | Transmission GALSI Italia (National) | Transmission Italy (PSV) (Southern Projects) |  | TRA-N-012 | GALSI Pipeline Project | Galsi S.p.A. | Advanced Non-FID | Yes | Galsi S.p.A. | 2019 | 226
Cross-Border Transmission IP within EU | Porto Botte (Galsi) | Transmission GALSI Algeria (International) | Transmission Italy (Sardinia) |  | TRA-N-012 | GALSI Pipeline Project | Galsi S.p.A. | Advanced Non-FID | Yes | Galsi S.p.A. | 2019 | 258
Cross-Border Transmission IP within EU | Poseidon Greek Entry | Transmission Greece (Komotini) | Transmission ITGI Poseidon Greece |  | TRA-N-010 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced Non-FID | Yes | IGI Poseidon S.A. | 2020 | 329.4
Cross-Border Transmission IP within EU | Poseidon Greek Entry | Transmission ITGI Poseidon Greece | Transmission Greece (Komotini) |  | TRA-N-010 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced Non-FID | Yes | IGI Poseidon S.A. | 2020 | 252.5
Cross-Border Transmission IP within EU | Poseidon Greek Entry | Transmission Greece (Komotini) | Transmission ITGI Poseidon Greece |  | TRA-N-014 | Komotini-Thesprotia pipeline | DESFA S.A. | Less-Advanced Non-FID | Yes | DESFA S.A. | 2023 | 275.41
Cross-Border Transmission IP within EU | Poseidon Greek Entry | Transmission ITGI Poseidon Greece | Transmission Greece (Komotini) |  | TRA-N-014 | Komotini-Thesprotia pipeline | DESFA S.A. | Less-Advanced Non-FID | Yes | DESFA S.A. | 2023 | 80
Cross-Border Transmission IP within EU | Poštorná / Reintal | Transmission Czech Republic (VOB) | Transmission Austria (CEGH) |  | TRA-N-021 | Bidirectional Austrian-Czech Interconnector (BACI, formerly LBL project) | GAS CONNECT AUSTRIA GmbH | Advanced Non-FID | Yes | Gas Connect Austria GmbH | 2020 | 201.42
Cross-Border Transmission IP within EU | Poštorná / Reintal | Transmission Czech Republic (VOB) | Transmission Austria (CEGH) |  | TRA-N-801 | Břeclav-Baumgarten Interconnection (BBI) AT | GAS CONNECT AUSTRIA GmbH | Advanced Non-FID | No | Gas Connect Austria GmbH | 2020 | 1118.071
Cross-Border Transmission IP within EU | Poštorná / Reintal | Transmission Czech Republic (VOB) | Transmission Austria (CEGH) |  | TRA-N-133 | Bidirectional Austrian Czech Interconnection (BACI) | NET4GAS, s.r.o. | Advanced Non-FID | Yes | NET4GAS, s.r.o. | 2020 | 201.42
Cross-Border Transmission IP within EU | Poštorná / Reintal | Transmission Czech Republic (VOB) | Transmission Austria (CEGH) |  | TRA-N-919 | Capacity4Gas (C4G) – CZ/AT | NET4GAS, s.r.o. | Advanced Non-FID | No | NET4GAS, s.r.o. | 2020 | 1000
Cross-Border Transmission IP within EU | Poštorná / Reintal | Transmission Austria (CEGH) | Transmission Czech Republic (VOB) |  | TRA-N-021 | Bidirectional Austrian-Czech Interconnector (BACI, formerly LBL project) | GAS CONNECT AUSTRIA GmbH | Advanced Non-FID | Yes | Gas Connect Austria GmbH | 2020 | 201.42
Cross-Border Transmission IP within EU | Poštorná / Reintal | Transmission Austria (CEGH) | Transmission Czech Republic (VOB) |  | TRA-N-133 | Bidirectional Austrian Czech Interconnection (BACI) | NET4GAS, s.r.o. | Advanced Non-FID | Yes | NET4GAS, s.r.o. | 2020 | 201.42
Cross-Border Transmission IP within EU | Rogatec | Transmission Slovenia | Transmission Croatia |  | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | Plinovodi d.o.o. | Advanced Non-FID | Yes | Plinovodi d.o.o. | 2020 | 165
Cross-Border Transmission IP within EU | Rogatec | Transmission Croatia | Transmission Slovenia |  | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | Plinovodi d.o.o. | Advanced Non-FID | Yes | Plinovodi d.o.o. | 2020 | 165
Cross-Border Transmission IP within EU | Rogatec | Transmission Slovenia | Transmission Croatia |  | TRA-F-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Rogatec) | Plinacro Ltd | FID | Yes | Plinacro Ltd | 2019 | 146
Cross-Border Transmission IP within EU | Rogatec | Transmission Croatia | Transmission Slovenia |  | TRA-F-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Rogatec) | Plinacro Ltd | FID | Yes | Plinacro Ltd | 2019 | 146
Cross-Border Transmission IP within EU | Rupa (HR) / Jelšane (SI) | Transmission Slovenia | Transmission Croatia |  | TRA-N-101 | M8 Kalce - Jelšane | Plinovodi d.o.o. | Less-Advanced Non-FID | No | Plinovodi d.o.o. | 2022 | 414
Cross-Border Transmission IP within EU | Rupa (HR) / Jelšane (SI) | Transmission Croatia | Transmission Slovenia |  | TRA-N-101 | M8 Kalce - Jelšane | Plinovodi d.o.o. | Less-Advanced Non-FID | No | Plinovodi d.o.o. | 2022 | 414
Cross-Border Transmission IP within EU | Ruse (BG) / Giurgiu (RO) | Transmission Bulgaria (NGTS) | Transmission Romania |  | TRA-F-029 | Romania-Bulgaria Interconnection (EEPR-2009-INTg-RO-BG) | SNTGN Transgaz SA | FID | No | SNTGN Transgaz S.A. | 2016 | 14.38
Cross-Border Transmission IP within EU | Ruse (BG) / Giurgiu (RO) | Transmission Romania | Transmission Bulgaria (NGTS) |  | TRA-F-029 | Romania-Bulgaria Interconnection (EEPR-2009-INTg-RO-BG) | SNTGN Transgaz SA | FID | No | SNTGN Transgaz S.A. | 2016 | 14.38
Cross-Border Transmission IP within EU | Ruse (BG) / Giurgiu (RO) | Transmission Romania | Transmission Bulgaria (NGTS) |  | TRA-N-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT Corridor) | SNTGN Transgaz S.A. | Less-Advanced Non-FID | Yes | SNTGN Transgaz S.A. | 2020 | 29.3
Cross-Border Transmission IP within EU | San Dorligo della Valle (IT) /Osp (SI) | Transmission Italia (PSV) | Transmission Slovenia |  | TRA-N-107 | M6 Interconnection Osp | Plinovodi d.o.o. | Less-Advanced Non-FID | No | Plinovodi d.o.o. | 2022 | 6.1
Cross-Border Transmission IP within EU | San Dorligo della Valle (IT) /Osp (SI) | Transmission Italia (PSV) | Transmission Slovenia |  | TRA-N-354 | Interconnection with Slovenia | Snam Rete Gas S.p.A. | Less-Advanced Non-FID | No | Snam Rete Gas S.p.A. | 2023 | 3.6
Cross-Border Transmission IP within EU | Sečovlje (SI) / Plovanija (HR) | Transmission Slovenia | Transmission Croatia |  | TRA-N-114 | R61 Dragonja - Izola | Plinovodi d.o.o. | Less-Advanced Non-FID | No | Plinovodi d.o.o. | 2024 | 5.1
Cross-Border Transmission IP within EU | Sečovlje (SI) / Plovanija (HR) | Transmission Croatia | Transmission Slovenia |  | TRA-N-114 | R61 Dragonja - Izola | Plinovodi d.o.o. | Less-Advanced Non-FID | No | Plinovodi d.o.o. | 2024 | 5.1
Cross-Border Transmission IP within EU | Sečovlje (SI) / Plovanija (HR) | Transmission Slovenia | Transmission Croatia |  | TRA-N-336 | Interconnection Croatia/Slovenia (Umag-Koper) | Plinacro Ltd | Less-Advanced Non-FID | No | Plinacro Ltd | 2026 | 14.6
Cross-Border Transmission IP within EU | Sečovlje (SI) / Plovanija (HR) | Transmission Croatia | Transmission Slovenia |  | TRA-N-336 | Interconnection Croatia/Slovenia (Umag-Koper) | Plinacro Ltd | Less-Advanced Non-FID | No | Plinacro Ltd | 2026 | 14.6
Cross-Border Transmission IP within EU | South North CSEP | Transmission BGE (NI) System United Kingdom (North Ireland) | Transmission Ireland (IBP) |  | TRA-N-071 | Physical Reverse Flow on South North Pipeline | Gas Networks Ireland | Less-Advanced Non-FID | No | Gas Networks Ireland | 2022 | 27.6
Cross-Border Transmission IP within EU | Stara Zagora - IGB / BG | Transmission Interconnector Greece-Bulgaria Bulgaria | Transmission Bulgaria (NGTS) |  | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | ICGB a.d. | FID | Yes | ICGB a.d. | 2018 | 90
Cross-Border Transmission IP within EU | Stara Zagora - IGB / BG | Transmission Interconnector Greece-Bulgaria Bulgaria | Transmission Bulgaria (NGTS) |  | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | ICGB a.d. | FID | Yes | ICGB a.d. | 2021 | 60.5
Cross-Border Transmission IP within EU | Tarvisio (IT) / Arnoldstein (AT) | Transmission Italy (PSV) (Italy Northern Export Fork) | Transmission Austria (CEGH) |  | TRA-F-214 | Support to the North West market and bidirectional cross-border flows | Snam Rete Gas S.p.A. | FID | Yes | Snam Rete Gas S.p.A. | 2018 | 189
Cross-Border Transmission IP within EU | Tarvisio (IT) / Arnoldstein (AT) | Transmission Italy (PSV) (Italy Northern Export Fork) | Transmission Austria (CEGH) |  | TRA-N-954 | TAG Reverse Flow | Trans Austria Gasleitung GmbH | Less-Advanced Non-FID | No | TAG GmbH | 2018 | 0
Cross-Border Transmission IP within EU | Trans-Adriatic Pipeline (TAP) / Ionic-Adriatic Pipeline (IAP) | Transmission Trans-Adriatic Pipeline Greece | Transmission Ionic-Adriatic Pipeline Croatia (TAP-IAP Interconnection) |  | TRA-F-051 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | FID | Yes | Trans-Adriatic Pipeline AG | 2019 | 150
Cross-Border Transmission IP within EU | Überackern ABG (AT) / Überackern (DE) | Transmission Austria (CEGH) | Transmission Germany (NCG) |  | TRA-F-241 | MONACO section phase I (Burghausen-Finsing) | bayernets GmbH | FID | No | bayernets GmbH | 2017 | 36.25
Cross-Border Transmission IP within EU | Überackern SUDAL (AT) / Überackern 2 (DE) | Transmission Germany (NCG) | Transmission Austria (CEGH) |  | TRA-F-241 | MONACO section phase I (Burghausen-Finsing) | bayernets GmbH | FID | No | bayernets GmbH | 2017 | 143.37
Cross-Border Transmission IP within EU | VIP IBERICO | Transmission Spain (MS-ATR) | Transmission Portugal |  | TRA-N-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | REN-Gasodutos, S.A. | Advanced Non-FID | Yes | REN - Gasodutos, S.A. | 2021 | 85
Cross-Border Transmission IP within EU | VIP IBERICO | Transmission Portugal | Transmission Spain (MS-ATR) |  | TRA-N-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | REN-Gasodutos, S.A. | Advanced Non-FID | Yes | REN - Gasodutos, S.A. | 2021 | 70
Cross-Border Transmission IP within EU | VIP IBERICO | Transmission Portugal | Transmission Spain (MS-ATR) |  | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Enagás Transporte, S.A.U. | Less-Advanced Non-FID | Yes | Enagás S.A. | 2021 | 70
Cross-Border Transmission IP within EU | VIP IBERICO | Transmission Spain (MS-ATR) | Transmission Portugal |  | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Enagás Transporte, S.A.U. | Less-Advanced Non-FID | Yes | Enagás S.A. | 2021 | 70
Cross-Border Transmission IP within EU | VIP IBERICO | Transmission Spain (MS-ATR) | Transmission Portugal |  | TRA-N-284 | 3rd IP between Portugal and Spain (Compressor Station) | REN-Gasodutos, S.A. | Less-Advanced Non-FID | Yes | REN - Gasodutos, S.A. | 2025 | 22
Cross-Border Transmission IP within EU | VIP IBERICO | Transmission Spain (MS-ATR) | Transmission Portugal |  | TRA-N-285 | 3rd IP between Portugal and Spain (pipeline Cantanhede-Mangualde) | REN-Gasodutos, S.A. | Less-Advanced Non-FID | Yes | REN - Gasodutos, S.A. | 2025 | 32
Cross-Border Transmission IP within EU | VIP IBERICO | Transmission Portugal | Transmission Spain (MS-ATR) |  | TRA-N-284 | 3rd IP between Portugal and Spain (Compressor Station) | REN-Gasodutos, S.A. | Less-Advanced Non-FID | Yes | REN - Gasodutos, S.A. | 2025 | 27
Cross-Border Transmission IP within EU | VIP IBERICO | Transmission Portugal | Transmission Spain (MS-ATR) |  | TRA-N-285 | 3rd IP between Portugal and Spain (pipeline Cantanhede-Mangualde) | REN-Gasodutos, S.A. | Less-Advanced Non-FID | Yes | REN - Gasodutos, S.A. | 2025 | 29
Cross-Border Transmission IP within EU | VIP IBERICO | Transmission Portugal | Transmission Spain (MS-ATR) |  | TRA-N-729 | Interconnection ES-PT (3rd IP) - 2nd phase | Enagás Transporte, S.A.U. | Less-Advanced Non-FID | Yes | Enagás S.A. | 2025 | 72
Cross-Border Transmission IP within EU | VIP IBERICO | Transmission Spain (MS-ATR) | Transmission Portugal |  | TRA-N-729 | Interconnection ES-PT (3rd IP) - 2nd phase | Enagás Transporte, S.A.U. | Less-Advanced Non-FID | Yes | Enagás S.A. | 2025 | 72
Cross-Border Transmission IP within EU | VIP PIRINEOS | Transmission France (PEG TIGF) | Transmission Spain (MS-ATR) |  | TRA-N-161 | South Transit East Pyrenees (STEP) - ENAGAS | Enagás Transporte, S.A.U. | Advanced Non-FID | Yes | Enagás S.A. | 2021 | 110
Cross-Border Transmission IP within EU | VIP PIRINEOS | Transmission Spain (MS-ATR) | Transmission France (PEG TIGF) |  | TRA-N-161 | South Transit East Pyrenees (STEP) - ENAGAS | Enagás Transporte, S.A.U. | Advanced Non-FID | Yes | Enagás S.A. | 2021 | 120
Cross-Border Transmission IP within EU | VIP PIRINEOS | Transmission France (PEG TIGF) | Transmission Spain (MS-ATR) |  | TRA-N-252 | South Transit East Pyrenees (STEP) - TIGF | TIGF | Advanced Non-FID | Yes | TIGF | 2022 | 0
Cross-Border Transmission IP within EU | VIP PIRINEOS | Transmission Spain (MS-ATR) | Transmission France (PEG TIGF) |  | TRA-N-252 | South Transit East Pyrenees (STEP) - TIGF | TIGF | Advanced Non-FID | Yes | TIGF | 2022 | 0
Cross-Border Transmission IP within EU | VIP PIRINEOS | Transmission France (PEG TIGF) | Transmission Spain (MS-ATR) |  | TRA-N-727 | Iberian‐French corridor: Eastern Axis ‐ Midcat Project | Enagás Transporte, S.A.U. | Less-Advanced Non-FID | Yes | Enagás S.A. | 2022 | 135
Cross-Border Transmission IP within EU | VIP PIRINEOS | Transmission Spain (MS-ATR) | Transmission France (PEG TIGF) |  | TRA-N-727 | Iberian‐French corridor: Eastern Axis ‐ Midcat Project | Enagás Transporte, S.A.U. | Less-Advanced Non-FID | Yes | Enagás S.A. | 2022 | 110
Cross-Border Transmission IP within EU | VIP PIRINEOS | Transmission France (PEG TIGF) | Transmission Spain (MS-ATR) |  | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF | Less-Advanced Non-FID | Yes | TIGF | 2024 | 160
Cross-Border Transmission IP within EU | VIP PIRINEOS | Transmission Spain (MS-ATR) | Transmission France (PEG TIGF) |  | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF | Less-Advanced Non-FID | Yes | TIGF | 2024 | 230
Internal Point | Italy Mezzogiorno Import Fork | Transmission Italy (PSV) (Southern Projects) | Transmission Italia (PSV) |  | TRA-N-007 | Development for new import from the South (Adriatica Line) | Snam Rete Gas S.p.A. | Less-Advanced Non-FID | Yes | Snam Rete Gas S.p.A. | 2023 | 264
Internal Point | Italy Mezzogiorno Import Fork | Transmission Italy (PSV) (Southern Projects) | Transmission Italia (PSV) |  | TRA-N-009 | Additional Southern developments | Snam Rete Gas S.p.A. | Less-Advanced Non-FID | No | Snam Rete Gas S.p.A. | 2034 | 264
Internal Point | Italy Northern Export Fork | Transmission Italia (PSV) | Transmission Italy (PSV) (Italy Northern Export Fork) |  | TRA-F-214 | Support to the North West market and bidirectional cross-border flows | Snam Rete Gas S.p.A. | FID | Yes | Snam Rete Gas S.p.A. | 2018 | 421
Internal Point | Italy Southern Import Fork | Transmission Italy (PSV) (Italy Southern Import Fork) | Transmission Italy (PSV) (Southern Projects) |  | TRA-N-009 | Additional Southern developments | Snam Rete Gas S.p.A. | Less-Advanced Non-FID | No | Snam Rete Gas S.p.A. | 2034 | 264
Internal Point | Komotini (DESFA) Bottleneck | Transmission Greece (Komotini) | Transmission Greece |  | TRA-N-128 | Compressor Station Kipi | DESFA S.A. | Less-Advanced Non-FID | Yes | DESFA S.A. | 2020 | 54.4
Internal Point | New IP North-East Italy | Transmission Italy (PSV) (Northern Projects) | Transmission Italia (PSV) |  | TRA-N-008 | Import developments from North-East | Snam Rete Gas S.p.A. | Less-Advanced Non-FID | No | Snam Rete Gas S.p.A. | 2034 | 340
Internal Point | Virtual Ips (GTS) NL-DE (Gaspool) | Transmission Netherlands (TTF) | Transmission Netherlands (TTF) (VIP NL/Gaspool) |  | TRA-N-882 | H-gas conversion of L-gas export border points | Gasunie Transport Services B.V. | Less-Advanced Non-FID | No | Gasunie Transport Services B.V. | 2020 | 120.4
Internal Point | Virtual Ips (GTS) NL-DE (Gaspool) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Netherlands (TTF) |  | TRA-N-873 | Capacity expansion OSZ related to West Stream | Gasunie Transport Services B.V. | Less-Advanced Non-FID | No | Gasunie Transport Services B.V. | 2021 | 223.2
Internal Point | Virtual Ips (GTS) NL-DE (Gaspool) | Transmission Netherlands (TTF) | Transmission Netherlands (TTF) (VIP NL/Gaspool) |  | TRA-N-882 | H-gas conversion of L-gas export border points | Gasunie Transport Services B.V. | Less-Advanced Non-FID | No | Gasunie Transport Services B.V. | 2022 | 12
Internal Point | Virtual Ips (GTS) NL-DE (Gaspool) | Transmission Netherlands (TTF) (VIP NL/Gaspool) | Transmission Netherlands (TTF) |  | TRA-N-873 | Capacity expansion OSZ related to West Stream | Gasunie Transport Services B.V. | Less-Advanced Non-FID | No | Gasunie Transport Services B.V. | 2023 | 276
Internal Point | Virtual Ips (GTS) NL-DE (Gaspool) | Transmission Netherlands (TTF) | Transmission Netherlands (TTF) (VIP NL/Gaspool) |  | TRA-N-882 | H-gas conversion of L-gas export border points | Gasunie Transport Services B.V. | Less-Advanced Non-FID | No | Gasunie Transport Services B.V. | 2024 | 12
Internal Point | Virtual Ips (GTS) NL-DE (Gaspool) | Transmission Netherlands (TTF) | Transmission Netherlands (TTF) (VIP NL/Gaspool) |  | TRA-N-882 | H-gas conversion of L-gas export border points | Gasunie Transport Services B.V. | Less-Advanced Non-FID | No | Gasunie Transport Services B.V. | 2026 | 24
Internal Point | Virtual Ips (GTS) NL-DE (Gaspool) | Transmission Netherlands (TTF) | Transmission Netherlands (TTF) (VIP NL/Gaspool) |  | TRA-N-882 | H-gas conversion of L-gas export border points | Gasunie Transport Services B.V. | Less-Advanced Non-FID | No | Gasunie Transport Services B.V. | 2027 | 24
Internal Point | Virtual Ips (GTS) NL-DE (Gaspool) | Transmission Netherlands (TTF) | Transmission Netherlands (TTF) (VIP NL/Gaspool) |  | TRA-N-882 | H-gas conversion of L-gas export border points | Gasunie Transport Services B.V. | Less-Advanced Non-FID | No | Gasunie Transport Services B.V. | 2030 | 137.5
LNG Entry IP | Agia Triada | LNG Terminals Greece | Transmission Greece |  | LNG-F-147 | Revythoussa (2nd upgrade) | DESFA S.A. | FID | No | DESFA S.A. | 2017 | 80.38
LNG Entry IP | Alexandropoulis LNG | LNG Terminals Greece | Transmission Greece (Alexandropolis LNG) |  | LNG-N-062 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | Gastrade S.A. | Advanced Non-FID | Yes | Gastrade S.A. | 2018 | 187.5
LNG Entry IP | Alexandroupolis Amphitriti | Transmission Greece (Alexandropolis LNG) | Transmission Greece (Komotini) |  | LNG-N-062 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | Gastrade S.A. | Advanced Non-FID | Yes | Gastrade S.A. | 2018 | 268
LNG Entry IP | Alexandroupolis Amphitriti | Transmission Greece (Alexandropolis LNG) | Transmission Greece (Komotini) |  | TRA-N-1090 | Metering and Regulating Station at Alexandroupoli | DESFA S.A. | Less-Advanced Non-FID | No | DESFA S.A. | 2020 | 268
LNG Entry IP | Croatia LNG | LNG Terminals Croatia | Transmission Croatia |  | LNG-N-082 | LNG terminal Krk | LNG Hrvatska d.o.o. za poslovanje ukapljenim prirodnim plinom | Advanced Non-FID | Yes | LNG Hrvatska d.o.o. | 2018 | 107
LNG Entry IP | Croatia LNG | LNG Terminals Croatia | Transmission Croatia |  | TRA-N-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | Plinacro Ltd | Advanced Non-FID | No | Plinacro Ltd | 2018 | 47
LNG Entry IP | Croatia LNG | LNG Terminals Croatia | Transmission Croatia |  | TRA-N-075 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Plinacro Ltd | Advanced Non-FID | Yes | Plinacro Ltd | 2020 | 45
LNG Entry IP | Croatia LNG | LNG Terminals Croatia | Transmission Croatia |  | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | Plinacro Ltd | Less-Advanced Non-FID | Yes | Plinacro Ltd | 2020 | 39
LNG Entry IP | Croatia LNG | LNG Terminals Croatia | Transmission Croatia |  | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | Plinacro Ltd | Less-Advanced Non-FID | Yes | Plinacro Ltd | 2023 | 99
LNG Entry IP | Fos (Tonkin/Cavaou) | LNG Terminals France (PEG South) | Transmission France (PEG South) |  | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | GRTgaz | Less-Advanced Non-FID | No | GRTgaz | 2022 | 327
LNG Entry IP | Fos Cavaou | LNG Terminals France (PEG South) | Transmission France (PEG South) |  | LNG-N-227 | Fos Cavaou LNG Terminal Expansion | Fosmax LNG | Less-Advanced Non-FID | No | Fosmax LNG | 2020 | 110
LNG Entry IP | Fos Cavaou | LNG Terminals France (PEG South) | Transmission France (PEG South) |  | LNG-N-227 | Fos Cavaou LNG Terminal Expansion | Fosmax LNG | Less-Advanced Non-FID | No | Fosmax LNG | 2022 | 220
LNG Entry IP | FSRU Polish Baltic Sea Coast | LNG Terminals Poland (VTP - GAZ-SYSTEM) | Transmission Poland (VTP - GAZ-SYSTEM) |  | LNG-N-947 | FSRU Polish Baltic Sea Coast | GAZ-SYSTEM S.A. | Less-Advanced Non-FID | No | GAZ-SYSTEM S.A. | 2020 | 275
LNG Entry IP | Gate Terminal (I) | LNG Terminals Netherlands (TTF) | Transmission Netherlands (TTF) |  | LNG-N-050 | Gate terminal phase 3 | Gate | Less-Advanced Non-FID | No | Gate Terminal B.V. | 2020 | 121
LNG Entry IP | Gate Terminal (I) | LNG Terminals Netherlands (TTF) | Transmission Netherlands (TTF) |  | TRA-N-192 | Entry capacity expansion GATE terminal | Gasunie Transport Services B.V. | Less-Advanced Non-FID | No | Gasunie Transport Services B.V. | 2020 | 134
LNG Entry IP | Gothenburg LNG | LNG Terminals Sweden | Transmission Sweden |  | LNG-N-032 | Project GO4LNG LNG terminal Gothenburg | Swedegas AB | Advanced Non-FID | Yes | Swedegas AB | 2020 | 26
LNG Entry IP | Gran Canaria LNG | LNG Terminals Spain (Canaria) | Transmission Spain (Canaria) |  | LNG-F-163 | Gran Canaria LNG Terminal | Gascan | FID | No | Gascan | 2021 | 41.9
LNG Entry IP | Gran Canaria LNG | LNG Terminals Spain (Canaria) | Transmission Spain (Canaria) |  | LNG-F-163 | Gran Canaria LNG Terminal | Gascan | FID | No | Enagás S.A. | 2021 | 41.9
LNG Entry IP | Gran Canaria LNG | LNG Terminals Spain (Canaria) | Transmission Spain (Canaria) |  | LNG-N-165 | Gran Canaria send out increase | Gascan | Less-Advanced Non-FID | No | Gascan | 2026 | 20.9
LNG Entry IP | Gran Canaria LNG | LNG Terminals Spain (Canaria) | Transmission Spain (Canaria) |  | LNG-N-165 | Gran Canaria send out increase | Gascan | Less-Advanced Non-FID | No | Enagás S.A. | 2026 | 20.9
LNG Entry IP | Klaipeda (LNG) | LNG Terminals Lithuania | Transmission Lithuania |  | LNG-N-824 | LNG Terminal in Klaipeda | AB Klaipėdos Nafta | Less-Advanced Non-FID | No | AB Klaipėdos Nafta | 2024 | 122.4
LNG Entry IP | Malta FSRU Offshore Terminal | LNG Terminals Malta | Transmission Malta |  | LNG-N-211 | Connection of Malta to the European Gas Network - LNG Regasification | Office of the Prime Minister (Energy) | Less-Advanced Non-FID | Yes | Office of the Prime Minister (Energy) – Malta | 2031 | 56
LNG Entry IP | Montoir de Bretagne | LNG Terminals France (PEG North) | Transmission France (PEG North) |  | LNG-N-225 | Montoir LNG Terminal Expansion | Elengy | Less-Advanced Non-FID | No | Elengy | 2020 | 100
LNG Entry IP | Montoir de Bretagne | LNG Terminals France (PEG North) | Transmission France (PEG North) |  | TRA-N-258 | Developments for Montoir LNG terminal 2.5 bcm expansion | GRTgaz | Less-Advanced Non-FID | No | GRTgaz | 2022 | 100
LNG Entry IP | Mugardos | LNG Terminals Spain (MS-ATR) | Transmission Spain (MS-ATR) |  | LNG-N-297 | Mugardos LNG Terminal: Storage Extension | Reganosa | Less-Advanced Non-FID | No | Reganosa (LSO) | 2022 | 0
LNG Entry IP | Mugardos | LNG Terminals Spain (MS-ATR) | Transmission Spain (MS-ATR) |  | LNG-N-295 | Mugardos LNG Terminal: Send-out Increase | Reganosa | Less-Advanced Non-FID | No | Reganosa (LSO) | 2023 | 115.2
LNG Entry IP | Mugardos | LNG Terminals Spain (MS-ATR) | Transmission Spain (MS-ATR) |  | LNG-N-295 | Mugardos LNG Terminal: Send-out Increase | Reganosa | Less-Advanced Non-FID | No | Reganosa | 2025 | 115
LNG Entry IP | Musel | LNG Terminals Spain (MS-ATR) | Transmission Spain (MS-ATR) |  | LNG-F-178 | Musel LNG terminal | Enagás Transporte, S.A.U. | FID | No | Enagás S.A. | 2026 | 223
LNG Entry IP | Paldiski LNG | LNG Terminals Estonia | Transmission Estonia |  | LNG-N-079 | Paldiski LNG Terminal | Balti Gaas plc | Advanced Non-FID | Yes | Balti Gaas plc | 2020 | 37.63
LNG Entry IP | Porto Empedocle LNG | LNG Terminals Italia (PSV) | Transmission Italy (PSV) (Italy Southern Import Fork) |  | LNG-N-198 | Porto Empedocle LNG | Nuove Energie S.r.l. | Advanced Non-FID | No | Nuove Energie S.r.l. | 2021 | 301.5
LNG Entry IP | Sines | LNG Terminals Portugal | Transmission Portugal |  | TRA-N-320 | Carregado Compressor Station | REN-Gasodutos, S.A. | Advanced Non-FID | No | REN - Gasodutos, S.A. | 2021 | 92.8
LNG Entry IP | Swinoujscie | LNG Terminals Poland (VTP - GAZ-SYSTEM) | Transmission Poland (VTP - GAZ-SYSTEM) |  | LNG-N-272 | Upgrade of LNG terminal in Świnoujście | GAZ-SYSTEM S.A. | Less-Advanced Non-FID | Yes | Polskie LNG S.A. | 2020 | 158
LNG Entry IP | Swinoujscie | LNG Terminals Poland (VTP - GAZ-SYSTEM) | Transmission Poland (VTP - GAZ-SYSTEM) |  | LNG-N-272 | Upgrade of LNG terminal in Świnoujście | GAZ-SYSTEM S.A. | Less-Advanced Non-FID | Yes | GAZ-SYSTEM S.A. | 2020 | 158
LNG Entry IP | Tallinn LNG | LNG Terminals Estonia | Transmission Estonia |  | LNG-N-962 | Tallinn LNG | Vopak E.O.S. AS / Vopak LNG Holdings B.V/ Port of Tallinn AS | Less-Advanced Non-FID | Yes | Vopak / Elering | 2019 | 121
LNG Entry IP | Tenerife LNG | LNG Terminals Spain (Canaria) | Transmission Spain (Canaria) |  | LNG-F-183 | Tenerife LNG Terminal | Gascan | FID | No | Gascan | 2020 | 41.9
LNG Entry IP | Tenerife LNG | LNG Terminals Spain (Canaria) | Transmission Spain (Canaria) |  | LNG-F-183 | Tenerife LNG Terminal | Gascan | FID | No | Enagás S.A. | 2020 | 41.9
LNG Entry IP | Tenerife LNG | LNG Terminals Spain (Canaria) | Transmission Spain (Canaria) |  | LNG-N-185 | Tenerife Send-Out increase | Gascan | Less-Advanced Non-FID | No | Gascan | 2026 | 20.9
LNG Entry IP | Tenerife LNG | LNG Terminals Spain (Canaria) | Transmission Spain (Canaria) |  | LNG-N-185 | Tenerife Send-Out increase | Gascan | Less-Advanced Non-FID | No | Enagás S.A. | 2026 | 20.9
LNG Entry IP | Zaule LNG (Trieste) | LNG Terminals Italia (PSV) | Transmission Italy (PSV) (Northern Projects) |  | LNG-N-217 | Onshore LNG terminal in the Northern Adriatic | Gas Natural Rigassificazione Italia | Less-Advanced Non-FID | No | gasNatural Rigassificazione S.p.A. | 2021 | 258
LNG Entry IP | Zeebrugge LNG | LNG Terminals Belgium (H-Zone) | Transmission Belgium (H-Zone) (Zeebrugge Beach) |  | LNG-F-229 | Zeebrugge LNG Terminal - 5th Tank & 2nd Jetty | Fluxys LNG | FID | No | Fluxys LNG | 2019 | 0
Production IP | East Med / Cyprus/Israeli Production Field | NP Send-out Cyprus | Transmission East Med Greece |  | TRA-N-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Less-Advanced Non-FID | Yes | IGI Poseidon S.A. | 2020 | 350
Storage IP | Ballylumford | Storage United Kingdom (NBP) | Transmission Premier Transmission System United Kingdom (North Ireland) |  | UGS-N-294 | Islandmagee Gas Storage Facility | Islandmagee Storage Limited | Less-Advanced Non-FID | Yes | Premier Transmission Ltd | 2021 | 66
Storage IP | Ballylumford | Transmission Premier Transmission System United Kingdom (North Ireland) | Storage United Kingdom (NBP) |  | UGS-N-294 | Islandmagee Gas Storage Facility | Islandmagee Storage Limited | Less-Advanced Non-FID | Yes | Premier Transmission Ltd | 2021 | 121
Storage IP | Ballylumford | Storage United Kingdom (NBP) | Transmission Premier Transmission System United Kingdom (North Ireland) |  | UGS-N-294 | Islandmagee Gas Storage Facility | Islandmagee Storage Limited | Less-Advanced Non-FID | Yes | Premier Transmission Ltd | 2022 | 83
Storage IP | Ballylumford | Transmission Premier Transmission System United Kingdom (North Ireland) | Storage United Kingdom (NBP) |  | UGS-N-294 | Islandmagee Gas Storage Facility | Islandmagee Storage Limited | Less-Advanced Non-FID | Yes | Premier Transmission Ltd | 2022 | 152
Storage IP | Ballylumford | Storage United Kingdom (NBP) | Transmission Premier Transmission System United Kingdom (North Ireland) |  | UGS-N-294 | Islandmagee Gas Storage Facility | Islandmagee Storage Limited | Less-Advanced Non-FID | Yes | Premier Transmission Ltd | 2025 | 99
Storage IP | Ballylumford | Transmission Premier Transmission System United Kingdom (North Ireland) | Storage United Kingdom (NBP) |  | UGS-N-294 | Islandmagee Gas Storage Facility | Islandmagee Storage Limited | Less-Advanced Non-FID | Yes | Premier Transmission Ltd | 2025 | 181
Storage IP | Ballylumford | Storage United Kingdom (NBP) | Transmission Premier Transmission System United Kingdom (North Ireland) |  | UGS-N-294 | Islandmagee Gas Storage Facility | Islandmagee Storage Limited | Less-Advanced Non-FID | Yes | Premier Transmission Ltd | 2026 | 132
Storage IP | Ballylumford | Transmission Premier Transmission System United Kingdom (North Ireland) | Storage United Kingdom (NBP) |  | UGS-N-294 | Islandmagee Gas Storage Facility | Islandmagee Storage Limited | Less-Advanced Non-FID | Yes | Premier Transmission Ltd | 2026 | 242
Storage IP | Damasławek (PL) | Storage Poland (VTP - GAZ-SYSTEM) | Transmission Poland (VTP - GAZ-SYSTEM) |  | UGS-N-914 | UGS Damaslawek | GAZ-SYSTEM S.A. | Less-Advanced Non-FID | No | GAZ-SYSTEM S.A. | 2026 | 200
Storage IP | Damasławek (PL) | Transmission Poland (VTP - GAZ-SYSTEM) | Storage Poland (VTP - GAZ-SYSTEM) |  | UGS-N-914 | UGS Damaslawek | GAZ-SYSTEM S.A. | Less-Advanced Non-FID | No | GAZ-SYSTEM S.A. | 2026 | 100
Storage IP | GMS Chiren | Transmission Bulgaria (NGTS) | Storage Bulgaria (NGTS) |  | UGS-N-138 | UGS Chiren Expansion | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | Bulgartransgaz EAD | 2022 | 61.5
Storage IP | GMS Chiren | Storage Bulgaria (NGTS) | Transmission Bulgaria (NGTS) |  | UGS-N-138 | UGS Chiren Expansion | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | Bulgartransgaz EAD | 2022 | 61.5
Storage IP | New Gas Storage Facility in Romania | Transmission Romania | Storage Romania |  | UGS-N-366 | New undergound gas storage in Romania | Societatea Naţională de Gaze Naturale ROMGAZ S.A. | Less-Advanced Non-FID | Yes | SNTGN Romgaz S.A. | 2023 | 15
Storage IP | New Gas Storage Facility in Romania | Storage Romania | Transmission Romania |  | UGS-N-366 | New undergound gas storage in Romania | Societatea Naţională de Gaze Naturale ROMGAZ S.A. | Less-Advanced Non-FID | Yes | SNTGN Romgaz S.A. | 2023 | 21
Storage IP | Position 5D.02 of ENAGAS pipeline from Martorell to Figueras | Transmission Spain (MS-ATR) | Storage Spain (MS-ATR) |  | UGS-N-127 | Underground Gas Storage in salt leached caverns in the Bages area (ES) | Gas Natural | Less-Advanced Non-FID | No | gasNatural fenosa | 2023 | 99
Storage IP | Position 5D.02 of ENAGAS pipeline from Martorell to Figueras | Storage Spain (MS-ATR) | Transmission Spain (MS-ATR) |  | UGS-N-127 | Underground Gas Storage in salt leached caverns in the Bages area (ES) | Gas Natural | Less-Advanced Non-FID | No | gasNatural fenosa | 2023 | 156
Storage IP | Preesall | Storage United Kingdom (NBP) | Transmission United Kingdom (NBP) |  | UGS-N-203 | Preesall Gas Storage | Halite Energy Group Ltd | Less-Advanced Non-FID | No | Halite Energy Group Ltd | 2018 | 330
Storage IP | Preesall | Transmission United Kingdom (NBP) | Storage United Kingdom (NBP) |  | UGS-N-203 | Preesall Gas Storage | Halite Energy Group Ltd | Less-Advanced Non-FID | No | Halite Energy Group Ltd | 2018 | 330
Storage IP | Syderiai | Transmission Lithuania | Storage Lithuania |  | UGS-N-034 | Syderiai | JSC Lietuvos energija AB | Less-Advanced Non-FID | No | Lietuvos energija AB | 2019 | 55
Storage IP | Syderiai | Storage Lithuania | Transmission Lithuania |  | UGS-N-034 | Syderiai | JSC Lietuvos energija AB | Less-Advanced Non-FID | No | Lietuvos energija AB | 2019 | 110
Storage IP | UGS - IT - Snam Rete Gas/Edison | Transmission Italia (PSV) | Storage Italia (PSV) |  | UGS-N-235 | Nuovi Sviluppi Edison Stoccaggio | Edison Stoccaggio S.p.A | Advanced Non-FID | No | Edison Stoccagio S.p.A. | 2017 | 11
Storage IP | UGS - IT - Snam Rete Gas/Edison | Storage Italia (PSV) | Transmission Italia (PSV) |  | UGS-N-235 | Nuovi Sviluppi Edison Stoccaggio | Edison Stoccaggio S.p.A | Advanced Non-FID | No | Edison Stoccagio S.p.A. | 2017 | 16
Storage IP | UGS - IT - Snam Rete Gas/Edison | Transmission Italia (PSV) | Storage Italia (PSV) |  | UGS-N-237 | Palazzo Moroni | Edison Stoccaggio S.p.A | Advanced Non-FID | No | Edison Stoccagio S.p.A. | 2019 | 11
Storage IP | UGS - IT - Snam Rete Gas/Edison | Storage Italia (PSV) | Transmission Italia (PSV) |  | UGS-N-237 | Palazzo Moroni | Edison Stoccaggio S.p.A | Advanced Non-FID | No | Edison Stoccagio S.p.A. | 2019 | 11
Storage IP | UGS - IT - Snam Rete Gas/STOGIT | Transmission Italia (PSV) | Storage Italia (PSV) |  | UGS-F-259 | Bordolano first phase | STOGIT | FID | No | STOGIT | 2016 | 109
Storage IP | UGS - IT - Snam Rete Gas/STOGIT | Storage Italia (PSV) | Transmission Italia (PSV) |  | UGS-F-259 | Bordolano first phase | STOGIT | FID | No | STOGIT | 2016 | 32
Storage IP | UGS - IT - Snam Rete Gas/STOGIT | Transmission Italia (PSV) | Storage Italia (PSV) |  | UGS-F-1045 | Bordolano Second phase | STOGIT S.p.A. | FID | No | STOGIT | 2019 | 109
Storage IP | UGS - IT - Snam Rete Gas/STOGIT | Storage Italia (PSV) | Transmission Italia (PSV) |  | UGS-F-1045 | Bordolano Second phase | STOGIT S.p.A. | FID | No | STOGIT | 2019 | 185
Storage IP | UGS - IT - Snam Rete Gas/STOGIT | Transmission Italia (PSV) | Storage Italia (PSV) |  | UGS-F-260 | System Enhancements - Stogit - on-shore gas fields | STOGIT | FID | No | STOGIT | 2026 | 147
Storage IP | UGS - IT - Snam Rete Gas/STOGIT | Storage Italia (PSV) | Transmission Italia (PSV) |  | UGS-F-260 | System Enhancements - Stogit - on-shore gas fields | STOGIT | FID | No | STOGIT | 2026 | 207
Storage IP | UGS Incukalns (LV) | Storage Latvia | Transmission Latvia |  | UGS-N-374 | Enhancement of Incukalns UGS | JSC "Latvijas Gaze" | Advanced Non-FID | Yes | Latvijas Gaze | 2019 | 30
Storage IP | UGS Incukalns (LV) | Storage Latvia | Transmission Latvia |  | UGS-N-374 | Enhancement of Incukalns UGS | JSC "Latvijas Gaze" | Advanced Non-FID | Yes | Latvijas Gaze | 2021 | 20
Storage IP | UGS Sarmasel | Transmission Romania | Storage Romania |  | UGS-N-371 | Sarmasel undeground gas storage in Romania | Societatea Naţională de Gaze Naturale ROMGAZ S.A. | Less-Advanced Non-FID | Yes | SNTGN Romgaz S.A. | 2022 | 42
Storage IP | UGS Sarmasel | Storage Romania | Transmission Romania |  | UGS-N-371 | Sarmasel undeground gas storage in Romania | Societatea Naţională de Gaze Naturale ROMGAZ S.A. | Less-Advanced Non-FID | Yes | SNTGN Romgaz S.A. | 2022 | 34
Storage IP | UGS South Kavala (GR) | Transmission Greece (Komotini) | Storage Greece |  | UGS-N-385 | South Kavala Underground Gas Storage facility | Hellenic Republic Asset anagement Fund | Less-Advanced Non-FID | No | Hellenic Republic Asset Management Fund | 2022 | 55
Storage IP | UGS South Kavala (GR) | Storage Greece | Transmission Greece (Komotini) |  | UGS-N-385 | South Kavala Underground Gas Storage facility | Hellenic Republic Asset anagement Fund | Less-Advanced Non-FID | No | Hellenic Republic Asset Management Fund | 2022 | 44
Storage IP | UGS South Kavala (GR) | Storage Greece | Transmission Greece (Komotini) |  | TRA-N-1092 | Metering and Regulating Station at UGS South Kavala | DESFA S.A. | Less-Advanced Non-FID | No | DESFA S.A. | 2023 | 44
Storage IP | UGS South Kavala (GR) | Transmission Greece (Komotini) | Storage Greece |  | TRA-N-1092 | Metering and Regulating Station at UGS South Kavala | DESFA S.A. | Less-Advanced Non-FID | No | DESFA S.A. | 2023 | 55
Storage IP | UGS Targu Mures | Transmission Romania | Storage Romania |  | UGS-N-233 | Depomures | Engie Romania SA | Advanced Non-FID | Yes | Depomures | 2019 | 15.78
Storage IP | UGS Targu Mures | Storage Romania | Transmission Romania |  | UGS-N-233 | Depomures | Engie Romania SA | Advanced Non-FID | Yes | Depomures | 2019 | 15.78
Storage IP | UGS Targu Mures | Transmission Romania | Storage Romania |  | UGS-N-233 | Depomures | Engie Romania SA | Advanced Non-FID | Yes | Depomures | 2022 | 18.92
Storage IP | UGS Targu Mures | Storage Romania | Transmission Romania |  | UGS-N-233 | Depomures | Engie Romania SA | Advanced Non-FID | Yes | Depomures | 2022 | 18.92
Storage IP | VIP Romgaz UGS (RO) | Transmission Romania | Storage Romania |  | UGS-N-371 | Sarmasel undeground gas storage in Romania | Societatea Naţională de Gaze Naturale ROMGAZ S.A. | Less-Advanced Non-FID | Yes | SNTGN Romgaz S.A. | 2022 | 42
Storage IP | VIP Romgaz UGS (RO) | Storage Romania | Transmission Romania |  | UGS-N-371 | Sarmasel undeground gas storage in Romania | Societatea Naţională de Gaze Naturale ROMGAZ S.A. | Less-Advanced Non-FID | Yes | SNTGN Romgaz S.A. | 2022 | 34
Transmission Point | Balticconnector / Siuntio (FI) | Transmission Finland | Transmission Balti Connector Finland |  | TRA-N-928 | Balticconnector Finnish part | Baltic Connector Oy | Advanced Non-FID | Yes | Baltic Connector Oy | 2019 | 79
Transmission Point | Balticconnector / Siuntio (FI) | Transmission Balti Connector Finland | Transmission Finland |  | TRA-N-928 | Balticconnector Finnish part | Baltic Connector Oy | Advanced Non-FID | Yes | Baltic Connector Oy | 2019 | 79
Transmission Point | Balticonnector / Paldiski (EE) | Transmission Balti Connector Finland | Transmission Estonia |  | TRA-N-895 | Balticconnector | Elering AS | Advanced Non-FID | Yes | Elering AS | 2019 | 79
Transmission Point | Balticonnector / Paldiski (EE) | Transmission Balti Connector Finland | Transmission Estonia |  | TRA-N-928 | Balticconnector Finnish part | Baltic Connector Oy | Advanced Non-FID | Yes | Baltic Connector Oy | 2019 | 79
Transmission Point | Balticonnector / Paldiski (EE) | Transmission Estonia | Transmission Balti Connector Finland |  | TRA-N-895 | Balticconnector | Elering AS | Advanced Non-FID | Yes | Elering AS | 2019 | 79
Transmission Point | Balticonnector / Paldiski (EE) | Transmission Estonia | Transmission Balti Connector Finland |  | TRA-N-928 | Balticconnector Finnish part | Baltic Connector Oy | Advanced Non-FID | Yes | Baltic Connector Oy | 2019 | 79
Transmission Point | Drohne GASCADE / OGE | Transmission Germany (GASPOOL) | Transmission Germany (NCG) |  | TRA-F-291 | NOWAL - Nord West Anbindungsleitung | GASCADE Gastransport GmbH | FID | No | GASCADE Gastransport GmbH | 2017 | 216
Transmission Point | Drohne GASCADE / OGE | Transmission Germany (GASPOOL) | Transmission Germany (NCG) |  | TRA-F-291 | NOWAL - Nord West Anbindungsleitung | GASCADE Gastransport GmbH | FID | No | GASCADE Gastransport GmbH | 2020 | 124.8
Transmission Point | Drohne GASCADE / OGE | Transmission Germany (GASPOOL) | Transmission Germany (NCG) |  | TRA-F-291 | NOWAL - Nord West Anbindungsleitung | GASCADE Gastransport GmbH | FID | No | GASCADE Gastransport GmbH | 2025 | 194.4
Transmission Point | Eastring BG Domestic Point | Transmission Eastring Bulgaria | Transmission Bulgaria (NGTS) |  | TRA-N-654 | Eastring - Bulgaria | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | Bulgartransgaz EAD | 2021 | 200
Transmission Point | Eastring BG Domestic Point | Transmission Bulgaria (NGTS) | Transmission Eastring Bulgaria |  | TRA-N-654 | Eastring - Bulgaria | Bulgartransgaz EAD | Less-Advanced Non-FID | Yes | Bulgartransgaz EAD | 2021 | 200
Transmission Point | Eastring HU Domestic Point | Transmission Eastring Hungary (MGP) | Transmission Hungary (MGP) |  | TRA-N-656 | Eastring - Hungary | FGSZ Ltd. | Less-Advanced Non-FID | Yes | FGSZ Ltd. | 2021 | 570
Transmission Point | Eastring HU Domestic Point | Transmission Hungary (MGP) | Transmission Eastring Hungary (MGP) |  | TRA-N-656 | Eastring - Hungary | FGSZ Ltd. | Less-Advanced Non-FID | Yes | FGSZ Ltd. | 2021 | 570
Transmission Point | Larino (IT) | Transmission Italia (SGI) | Transmission Italia (PSV) |  | TRA-N-974 | LARINO - RECANATI Adriatic coast backbone | Società Gasdotti Italia | Advanced Non-FID | No | Società Gasdotti Italia | 2022 | 53
Transmission Point | Larino (IT) | Transmission Italia (PSV) | Transmission Italia (SGI) |  | TRA-N-974 | LARINO - RECANATI Adriatic coast backbone | Società Gasdotti Italia | Advanced Non-FID | No | Società Gasdotti Italia | 2022 | 53
Transmission Point | Liaison Nord Sud | Transmission France (PEG South) | Transmission France (PEG North) |  | TRA-F-391 | Gascogne-Midi : adaptation of stations in Cruzy and St Martin | GRTgaz | FID | Yes | GRTgaz | 2018 | 0
Transmission Point | Liaison Nord Sud | Transmission France (PEG South) | Transmission France (PEG North) |  | TRA-F-43 | Val de Saône project | GRTgaz | FID | Yes | GRTgaz | 2018 | 999
Transmission Point | Liaison Nord Sud | Transmission France (PEG North) | Transmission France (PEG South) |  | TRA-F-43 | Val de Saône project | GRTgaz | FID | Yes | GRTgaz | 2018 | 999
Transmission Point | Nybro | NP Send-out Denmark (Offshore) | Transmission Denmark |  | TRA-N-394 | Gassled - Danish upstream system | Energinet.dk | Less-Advanced Non-FID | No | Energinet.dk | 2022 | 306.8
Transmission Point | Nybro | NP Send-out Denmark (Offshore) | Transmission Denmark |  | TRA-N-780 | Nybro-Interconnector PL-DK - reinforcement | Energinet.dk | Less-Advanced Non-FID | No | Energinet.dk | 2022 | 0.1
Transmission Point | PIR MIDI | Transmission France (PEG South) | Transmission France (PEG TIGF) |  | TRA-F-391 | Gascogne-Midi : adaptation of stations in Cruzy and St Martin | GRTgaz | FID | Yes | GRTgaz | 2018 | 0
Transmission Point | PIR MIDI | Transmission France (PEG TIGF) | Transmission France (PEG South) |  | TRA-F-391 | Gascogne-Midi : adaptation of stations in Cruzy and St Martin | GRTgaz | FID | Yes | GRTgaz | 2018 | 0
Transmission Point | Recanati (IT) | Transmission Italia (SGI) | Transmission Italia (PSV) |  | TRA-N-974 | LARINO - RECANATI Adriatic coast backbone | Società Gasdotti Italia | Advanced Non-FID | No | Società Gasdotti Italia | 2022 | 53
Transmission Point | Recanati (IT) | Transmission Italia (PSV) | Transmission Italia (SGI) |  | TRA-N-974 | LARINO - RECANATI Adriatic coast backbone | Società Gasdotti Italia | Advanced Non-FID | No | Società Gasdotti Italia | 2022 | 53
Transmission Point | TESLA / FYROM Offtake | Transmission TESLA former Yugoslav Republic of Macedonia | Transmission former Yugoslav Republic of Macedonia |  | TRA-N-582 | Macedonian part of Tesla project | GA-MA joint stock company Skopje | Less-Advanced Non-FID | Yes | GA-MA - Skopje | 2019 | 35
Transmission Point | TESLA / GR Offtake | Transmission TESLA Greece | Transmission Greece |  | TRA-N-631 | Greek part of Tesla project | DESFA S.A. | Less-Advanced Non-FID | Yes | DESFA S.A. | 2020 | 318
Transmission Point | TESLA / HU Offtake | Transmission TESLA Hungary (MGP) | Transmission Hungary (MGP) |  | TRA-N-585 | Hungarian section of Tesla project | FGSZ Ltd. | Less-Advanced Non-FID | Yes | FGSZ Ltd. | 2020 | 175
Transmission Point | Twynholm | Transmission Premier Transmission System United Kingdom (North Ireland) | Transmission United Kingdom (NBP) (Moffat) |  | TRA-N-027 | Physical reverse flow from NI to GB and IE via SNIP pipeline | Premier Transmission Limited | Less-Advanced Non-FID | Yes | Premier Transmission Ltd | 2021 | 131
Transmission Point | Vecsés MGT / FGSZ | Transmission Hungary (SK-HU Interconnector) | Transmission Hungary (MGP) |  | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | Magyar Gáz Tranzit Zrt. | Less-Advanced Non-FID | Yes | MGT Hungarian Gas Transit Ltd. | 2017 | 26
Transmission Point | Vecsés MGT / FGSZ | Transmission Hungary (MGP) | Transmission Hungary (SK-HU Interconnector) |  | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | Magyar Gáz Tranzit Zrt. | Less-Advanced Non-FID | Yes | MGT Hungarian Gas Transit Ltd. | 2017 | 102
Transmission Point | Vecsés MGT / FGSZ | Transmission Hungary (SK-HU Interconnector) | Transmission Hungary (MGP) |  | TRA-N-061 | Ercsi-Szazhalombatta | FGSZ Ltd. | Less-Advanced Non-FID | Yes | FGSZ Ltd. | 2022 | 25.5

## Transmission Projects
TYNDP Annex A |  |  |  | Transmission Projects - Page 3
Pipelines including Compressor Stations
Type | Code | Name | Promoter |  | Status | Commissioning Year | Other Variants Provided for Information? | Section | Length (km) | Diameter (mm) | Compressor Power (MW)
Pipeline including CS | TRA-F-029 | Romania-Bulgaria Interconnection (EEPR-2009-INTg-RO-BG) | SNTGN Transgaz SA |  | FID | 2016 | No | Giurgiu-Ruse | 25 | 500
Pipeline including CS | TRA-F-1047 | Exit Capacity Budince | eustream, a.s. |  | FID | 2016 | No | Exit Budince
Pipeline including CS | TRA-F-241 | MONACO section phase I (Burghausen-Finsing) | bayernets GmbH |  | FID | 2017 | No | Burghausen-Finsing | 87 | 1200
Pipeline including CS | TRA-F-291 | NOWAL - Nord West Anbindungsleitung | GASCADE Gastransport GmbH |  | FID | 2017 | No | Rehden-Drohne | 26 | 1000 | 16
Pipeline including CS | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | Plinacro Ltd |  | FID | 2017 | No
Pipeline including CS | TRA-F-768 | Extension Receiving Terminal Greifswald | NEL Gastransport, Fluxys Deutschland, Gasunie Deutschland |  | FID | 2017 | No
Pipeline including CS | TRA-F-43 | Val de Saône project | GRTgaz |  | FID | 2018 | No | Etrez CS |  |  | 9
Pipeline including CS | TRA-F-43 | Val de Saône project | GRTgaz |  | FID | 2018 | No | Palleau CS |  |  | 0
Pipeline including CS | TRA-F-43 | Val de Saône project | GRTgaz |  | FID | 2018 | No | Voisines CS |  |  | 0
Pipeline including CS | TRA-F-43 | Val de Saône project | GRTgaz |  | FID | 2018 | No | Bourgogne | 189 | 1200
Pipeline including CS | TRA-F-45 | Reverse capacity from CH to FR at Oltingue | GRTgaz |  | FID | 2018 | No | Morelmaison CS |  |  | 0
Pipeline including CS | TRA-F-45 | Reverse capacity from CH to FR at Oltingue | GRTgaz |  | FID | 2018 | No | Oltingue interconnection station |  |  | 0
Pipeline including CS | TRA-F-137 | Interconnection Bulgaria - Serbia | Ministry of Energy |  | FID | 2018 | No | Serbian territory | 108 | 700
Pipeline including CS | TRA-F-137 | Interconnection Bulgaria - Serbia | Ministry of Energy |  | FID | 2018 | No | Bulgarian territory | 62 | 700
Pipeline including CS | TRA-F-214 | Support to the North West market and bidirectional cross-border flows | Snam Rete Gas S.p.A. |  | FID | 2018 | No | Section 1 | 62 | 1400 | 0
Pipeline including CS | TRA-F-214 | Support to the North West market and bidirectional cross-border flows | Snam Rete Gas S.p.A. |  | FID | 2018 | No | Section 3 | 0 | 0 | 85
Pipeline including CS | TRA-F-214 | Support to the North West market and bidirectional cross-border flows | Snam Rete Gas S.p.A. |  | FID | 2018 | No | Section 2 | 19 | 1200 | 0
Pipeline including CS | TRA-F-230 | Reverse Flow Transitgas Switzerland | FluxSwiss |  | FID | 2018 | No
Pipeline including CS | TRA-F-331 | Gascogne Midi | TIGF - GRTgaz |  | FID | 2018 | No | Pipeline Lussagnet - Barran + CS in Barbaira | 60 | 900 | 6
Pipeline including CS | TRA-F-344 | Compressor station "Herbstein" | Open Grid Europe GmbH |  | FID | 2018 | No | Compressor station "Herbstein" |  |  | 39
Pipeline including CS | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | ICGB a.d. |  | FID | 2018 | No
Pipeline including CS | TRA-F-753 | West to East operation of the IP Waidhaus | GRTgaz Deutschland GmbH |  | FID | 2018 | No
Pipeline including CS | TRA-F-221 | TANAP - Trans Anatolian Natural Gas Pipeline Project | SOCAR (The State Oil Company of the Azerbaijan Republic) |  | FID | 2018 | No | Georgia/Turkey border- Eskishehir | 1347 | 1442 | 46
Pipeline including CS | TRA-F-221 | TANAP - Trans Anatolian Natural Gas Pipeline Project | SOCAR (The State Oil Company of the Azerbaijan Republic) |  | FID | 2018 | No | Eskishehir (Turkey)-Greece Border | 460 | 1219 | 46
Pipeline including CS | TRA-F-337 | CS Rothenstadt | GRTgaz Deutschland GmbH |  | FID | 2018 | No | MEGAL near Weiden in der Oberpfalz | 0 | 0 | 45
Pipeline including CS | TRA-F-391 | Gascogne-Midi : adaptation of stations in Cruzy and St Martin | GRTgaz |  | FID | 2018 | No | Cruzy CS |  |  | 0
Pipeline including CS | TRA-F-391 | Gascogne-Midi : adaptation of stations in Cruzy and St Martin | GRTgaz |  | FID | 2018 | No | St-Martin de Crau CS |  |  | 0
Pipeline including CS | TRA-F-208 | Reverse Flow TENP Germany | Fluxys TENP GmbH & Open Grid Europe GmbH |  | FID | 2018 | No
Pipeline including CS | TRA-F-343 | Pipeline project "Schwandorf-Finsing" | Open Grid Europe GmbH |  | FID | 2018 | No | Pipeline "Schwandorf-Forchheim" | 62 | 1000
Pipeline including CS | TRA-F-343 | Pipeline project "Schwandorf-Finsing" | Open Grid Europe GmbH |  | FID | 2018 | No | Pipeline "Forchheim-Finsing" | 79 | 1000
Pipeline including CS | TRA-F-345 | Compressor station "Werne" | Open Grid Europe GmbH |  | FID | 2018 | No | Compressor station "Werne" |  |  | 49
Pipeline including CS | TRA-F-051 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG |  | FID | 2019 | No | Main onshore section | 773 | 1200 | 90
Pipeline including CS | TRA-F-051 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG |  | FID | 2019 | No | Offshore section | 105 | 900 | 90
Pipeline including CS | TRA-F-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Rogatec) | Plinacro Ltd |  | FID | 2019 | No | Zabok-Rogatec | 36 | 700
Pipeline including CS | TRA-F-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Rogatec) | Plinacro Ltd |  | FID | 2019 | No | Lučko-Zabok | 33 | 700
Pipeline including CS | TRA-F-937 | Nord Stream 2 | Nord Stream 2 AG |  | FID | 2019 | No | Nord Stream 2 | 1200 | 1153
Pipeline including CS | TRA-F-1028 | Albania - Kosovo Gas Pipeline | Min. of Energy and Industry of AL & Min. of Economic Development of KO |  | FID | 2022 | No | Fier – Lezha (AL) – Prishtina (KO) | 260 | 610
Pipeline including CS | TRA-F-1028 | Albania - Kosovo Gas Pipeline | Min. of Energy and Industry of AL & Min. of Economic Development of KO |  | FID | 2022 | No | Lezha (AL) - Pristina (KO) | 175 | 610
Pipeline including CS | TRA-F-017 | System Enhancements - Eustream | eustream, a.s. |  | FID | 2026 | No
Pipeline including CS | TRA-F-025 | Industrial Emissions Directive (IPPC) - FID | National Grid Gas plc |  | FID | Unknown | No | Peterborough |  |  | 45
Pipeline including CS | TRA-F-025 | Industrial Emissions Directive (IPPC) - FID | National Grid Gas plc |  | FID | Unknown | No | Huntingdon |  |  | 45
Pipeline including CS | TRA-N-814 | Upgrade IP Deutschneudorf and Lasow | ONTRAS Gastransport GmbH |  | Advanced Non-FID | 2016 | No | Sayda - Deutschneudorf | 14 | 800 | 14
Pipeline including CS | TRA-N-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | Plinacro Ltd |  | Advanced Non-FID | 2018 | No | Omišalj-Zlobin | 18 | 1000
Pipeline including CS | TRA-N-063 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Gastrade S.A. |  | Advanced Non-FID | 2018 | No | Alexandroupolis LNG terminal - M/R Amfitriti | 28 | 762 | 0
Pipeline including CS | TRA-N-429 | Adaptation L- gas - H-gas | GRTgaz, GRDF and Storengy |  | Advanced Non-FID | 2018 | No | Connection to H-gas grid
Pipeline including CS | TRA-N-429 | Adaptation L- gas - H-gas | GRTgaz, GRDF and Storengy |  | Advanced Non-FID | 2018 | No | Taisnieres interconnection station
Pipeline including CS | TRA-N-429 | Adaptation L- gas - H-gas | GRTgaz, GRDF and Storengy |  | Advanced Non-FID | 2018 | No | Arleux interconnection station
Pipeline including CS | TRA-N-429 | Adaptation L- gas - H-gas | GRTgaz, GRDF and Storengy |  | Advanced Non-FID | 2018 | No | Bethune area | 8 | 300
Pipeline including CS | TRA-N-429 | Adaptation L- gas - H-gas | GRTgaz, GRDF and Storengy |  | Advanced Non-FID | 2018 | No | Loon Plage H-to-L adaptator
Pipeline including CS | TRA-N-429 | Adaptation L- gas - H-gas | GRTgaz, GRDF and Storengy |  | Advanced Non-FID | 2018 | No | Brouckerque area | 2 | 200
Pipeline including CS | TRA-N-429 | Adaptation L- gas - H-gas | GRTgaz, GRDF and Storengy |  | Advanced Non-FID | 2018 | No | Interconnection with Gournay UGS
Pipeline including CS | TRA-N-066 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Plinacro Ltd |  | Advanced Non-FID | 2019 | No | Slobodnica - Bosanski Brod | 6 | 700
Pipeline including CS | TRA-N-136 | Poland-Czech Republic Interconnection (CZ) | NET4GAS, s.r.o. |  | Advanced Non-FID | 2019 | No | Tvrdonice (CZ) - Hať (CZ/PL) | 207 | 1000 | 24
Pipeline including CS | TRA-N-273 | Poland - Czech Republic interconnection (PL section) | GAZ-SYSTEM S.A. |  | Advanced Non-FID | 2019 | No | CS Kedzierzyn |  |  | 30
Pipeline including CS | TRA-N-273 | Poland - Czech Republic interconnection (PL section) | GAZ-SYSTEM S.A. |  | Advanced Non-FID | 2019 | No | Czeszow-Wierzchowice pipeline | 14 | 1000
Pipeline including CS | TRA-N-273 | Poland - Czech Republic interconnection (PL section) | GAZ-SYSTEM S.A. |  | Advanced Non-FID | 2019 | No | Czeszow-Kielczow pipeline | 32 | 1000
Pipeline including CS | TRA-N-273 | Poland - Czech Republic interconnection (PL section) | GAZ-SYSTEM S.A. |  | Advanced Non-FID | 2019 | No | Kedzierzyn node
Pipeline including CS | TRA-N-273 | Poland - Czech Republic interconnection (PL section) | GAZ-SYSTEM S.A. |  | Advanced Non-FID | 2019 | No | PL-CZ interconnection - Polish section | 54 | 1000
Pipeline including CS | TRA-N-273 | Poland - Czech Republic interconnection (PL section) | GAZ-SYSTEM S.A. |  | Advanced Non-FID | 2019 | No | Zdzieszowice-Kędzierzyn pipeline | 19 | 1000
Pipeline including CS | TRA-N-273 | Poland - Czech Republic interconnection (PL section) | GAZ-SYSTEM S.A. |  | Advanced Non-FID | 2019 | No | Zdzieszowice-Wrocław pipeline | 130 | 1000
Pipeline including CS | TRA-N-361 | GCA 2015/08: Entry/Exit Murfeld | GAS CONNECT AUSTRIA GmbH |  | Advanced Non-FID | 2019 | No | Murfeld
Pipeline including CS | TRA-N-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | GASCADE Gastransport GmbH |  | Advanced Non-FID | 2019 | No | EUGAL | 484 | 1400 | 75
Pipeline including CS | TRA-N-012 | GALSI Pipeline Project | Galsi S.p.A. |  | Advanced Non-FID | 2019 | No | GALSI International Section | 288 | 660 | 99
Pipeline including CS | TRA-N-012 | GALSI Pipeline Project | Galsi S.p.A. |  | Advanced Non-FID | 2019 | No | GALSI Italian Section 1 onshore pipeline crossing Sardinia | 285 | 1219
Pipeline including CS | TRA-N-012 | GALSI Pipeline Project | Galsi S.p.A. |  | Advanced Non-FID | 2019 | No | GALSI Italian Section 2 sealine Sardinia - Tuscany | 288 | 812 | 52
Pipeline including CS | TRA-N-902 | Capacity increase at IP Lanžhot entry | eustream, a.s. |  | Advanced Non-FID | 2019 | Yes (See Project Fiche) | Capacity increase at IP Lanžhot Entry
Pipeline including CS | TRA-N-902 | Capacity increase at IP Lanžhot entry | eustream, a.s. |  | Advanced Non-FID | 2019 | Yes (See Project Fiche) | Capacity increase at IP Lanžhot Entry
Pipeline including CS | TRA-N-928 | Balticconnector Finnish part | Baltic Connector Oy |  | Advanced Non-FID | 2019 | No | Offshore | 80 | 700
Pipeline including CS | TRA-N-928 | Balticconnector Finnish part | Baltic Connector Oy |  | Advanced Non-FID | 2019 | No | FI Onshore | 20 | 500 | 10
Pipeline including CS | TRA-N-928 | Balticconnector Finnish part | Baltic Connector Oy |  | Advanced Non-FID | 2019 | No | EE Onshore | 50 | 500 | 10
Pipeline including CS | TRA-N-190 | Poland - Slovakia interconnection | eustream, a.s. |  | Advanced Non-FID | 2019 | No | Slovak section | 100 | 1000 | 16
Pipeline including CS | TRA-N-247 | North - South Gas Corridor in Western Poland | GAZ-SYSTEM S.A. |  | Advanced Non-FID | 2019 | No | Odolanow compressor station |  |  | 20
Pipeline including CS | TRA-N-247 | North - South Gas Corridor in Western Poland | GAZ-SYSTEM S.A. |  | Advanced Non-FID | 2019 | No | Lwowek-Odolanow pipeline | 162 | 1000
Pipeline including CS | TRA-N-247 | North - South Gas Corridor in Western Poland | GAZ-SYSTEM S.A. |  | Advanced Non-FID | 2019 | No | Tworóg-Kędzierzyn Koźle pipeline | 43 | 1000
Pipeline including CS | TRA-N-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | GAZ-SYSTEM S.A. |  | Advanced Non-FID | 2019 | No | CS Gustorzyn |  |  | 14
Pipeline including CS | TRA-N-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | GAZ-SYSTEM S.A. |  | Advanced Non-FID | 2019 | No | GIPL - Polish section | 357 | 700
Pipeline including CS | TRA-N-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | GAZ-SYSTEM S.A. |  | Advanced Non-FID | 2019 | No | CS Rembelszczyzna |  |  | 14
Pipeline including CS | TRA-N-275 | Poland - Slovakia interconnection (PL section) | GAZ-SYSTEM S.A. |  | Advanced Non-FID | 2019 | No | PL-SK interconnection - Polish section | 58 | 1000 | 19
Pipeline including CS | TRA-N-275 | Poland - Slovakia interconnection (PL section) | GAZ-SYSTEM S.A. |  | Advanced Non-FID | 2019 | No | Tworóg - Tworzeń | 56 | 1000
Pipeline including CS | TRA-N-275 | Poland - Slovakia interconnection (PL section) | GAZ-SYSTEM S.A. |  | Advanced Non-FID | 2019 | No | Strachocina - Pogórska Wola | 98 | 1000
Pipeline including CS | TRA-N-275 | Poland - Slovakia interconnection (PL section) | GAZ-SYSTEM S.A. |  | Advanced Non-FID | 2019 | No | Pogórska Wola - Tworzeń pipeline | 160 | 1000
Pipeline including CS | TRA-N-341 | Gas Interconnection Poland-Lithuania (GIPL) (Lithuania's section) | AB Amber Grid |  | Advanced Non-FID | 2019 | No | Border PL/LT - Jauniunai | 165 | 700
Pipeline including CS | TRA-N-752 | Capacity4Gas (C4G) – DE/CZ | NET4GAS, s.r.o. |  | Advanced Non-FID | 2019 | No | C4G - DE/CZ
Pipeline including CS | TRA-N-895 | Balticconnector | Elering AS |  | Advanced Non-FID | 2019 | No | FI Onshore | 20 | 500 | 10
Pipeline including CS | TRA-N-895 | Balticconnector | Elering AS |  | Advanced Non-FID | 2019 | No | Offshore | 80 | 500
Pipeline including CS | TRA-N-895 | Balticconnector | Elering AS |  | Advanced Non-FID | 2019 | No | EE Onshore | 50 | 700 | 10
Pipeline including CS | TRA-N-915 | Enhancement of Estonia-Latvia interconnection | Elering AS |  | Advanced Non-FID | 2019 | No | Karsi GMS, Puiatu CS | 0 | 0 | 10
Pipeline including CS | TRA-N-918 | Capacity4Gas (C4G) – CZ/SK | NET4GAS, s.r.o. |  | Advanced Non-FID | 2019 | No | C4G – CZ/SK
Pipeline including CS | TRA-N-010 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A |  | Advanced Non-FID | 2020 | No | Poseidon pipeline | 216 | 808 | 120
Pipeline including CS | TRA-N-021 | Bidirectional Austrian-Czech Interconnector (BACI, formerly LBL project) | GAS CONNECT AUSTRIA GmbH |  | Advanced Non-FID | 2020 | No | Austrian Side
Pipeline including CS | TRA-N-021 | Bidirectional Austrian-Czech Interconnector (BACI, formerly LBL project) | GAS CONNECT AUSTRIA GmbH |  | Advanced Non-FID | 2020 | No | Czech Side | 12 | 800 | 0
Pipeline including CS | TRA-N-075 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Plinacro Ltd |  | Advanced Non-FID | 2020 | No | Zlobin - Bosiljevo | 58 | 1000
Pipeline including CS | TRA-N-075 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Plinacro Ltd |  | Advanced Non-FID | 2020 | No | Bosiljevo - Sisak | 102 | 1000
Pipeline including CS | TRA-N-075 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Plinacro Ltd |  | Advanced Non-FID | 2020 | No | Kozarac - Sisak | 20 | 1000
Pipeline including CS | TRA-N-500 | L/H Conversion | Fluxys Belgium |  | Advanced Non-FID | 2020 | No
Pipeline including CS | TRA-N-801 | Břeclav-Baumgarten Interconnection (BBI) AT | GAS CONNECT AUSTRIA GmbH |  | Advanced Non-FID | 2020 | No | Břeclav-Baumgarten Interconnection (BBI) AT | 49 | 1400 | 10
Pipeline including CS | TRA-N-807 | Expansion NEL | Gasunie Deutschland, NEL Gastransport, Fluxys Deutschland |  | Advanced Non-FID | 2020 | No
Pipeline including CS | TRA-N-133 | Bidirectional Austrian Czech Interconnection (BACI) | NET4GAS, s.r.o. |  | Advanced Non-FID | 2020 | No | Břeclav (CZ) - Poštorná/Reintal (CZ/AT) | 12 | 800
Pipeline including CS | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | Plinovodi d.o.o. |  | Advanced Non-FID | 2020 | No | Upgrade of Rogatec interconnection | 4 | 800
Pipeline including CS | TRA-N-423 | GCA Mosonmagyaróvár | GAS CONNECT AUSTRIA GmbH |  | Advanced Non-FID | 2020 | No | Mosonmagyarovar
Pipeline including CS | TRA-N-919 | Capacity4Gas (C4G) – CZ/AT | NET4GAS, s.r.o. |  | Advanced Non-FID | 2020 | No | Břeclav (CZ) - Poštorná/Reintal (CZ/AT) | 12 | 1400
Pipeline including CS | TRA-N-161 | South Transit East Pyrenees (STEP) - ENAGAS | Enagás Transporte, S.A.U. |  | Advanced Non-FID | 2021 | No | CS Martorell |  |  | 36
Pipeline including CS | TRA-N-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | Plinacro Ltd |  | Advanced Non-FID | 2021 | No | Zagvozd-Imotski-Posušje | 22 | 500
Pipeline including CS | TRA-N-320 | Carregado Compressor Station | REN-Gasodutos, S.A. |  | Advanced Non-FID | 2021 | No | Setubal - Leiria (Lote 1) |  |  | 14
Pipeline including CS | TRA-N-808 | Transport of gas volumes to the Netherlands | Gasunie Deutschland Technical Services GmbH |  | Advanced Non-FID | 2021 | No
Pipeline including CS | TRA-N-161 | South Transit East Pyrenees (STEP) - ENAGAS | Enagás Transporte, S.A.U. |  | Advanced Non-FID | 2021 | No | Hostalrich - Figueras | 79 | 900
Pipeline including CS | TRA-N-161 | South Transit East Pyrenees (STEP) - ENAGAS | Enagás Transporte, S.A.U. |  | Advanced Non-FID | 2021 | No | Pipeline Figueras - French Border | 28 | 900
Pipeline including CS | TRA-N-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | REN-Gasodutos, S.A. |  | Advanced Non-FID | 2021 | No | Celorico-Spanish border | 162 | 700
Pipeline including CS | TRA-N-068 | Ionian Adriatic Pipeline | Plinacro Ltd |  | Advanced Non-FID | 2022 | No | IAP - Croatian part | 250 | 800 | 1
Pipeline including CS | TRA-N-068 | Ionian Adriatic Pipeline | Plinacro Ltd |  | Advanced Non-FID | 2022 | No | IAP- Albanian part | 180 | 800
Pipeline including CS | TRA-N-068 | Ionian Adriatic Pipeline | Plinacro Ltd |  | Advanced Non-FID | 2022 | No | IAP- Montenego part | 110 | 800
Pipeline including CS | TRA-N-252 | South Transit East Pyrenees (STEP) - TIGF | TIGF |  | Advanced Non-FID | 2022 | No | Pipeline Spanish Border-Barbaira + CS Barbaira | 120 | 900
Pipeline including CS | TRA-N-974 | LARINO - RECANATI Adriatic coast backbone | Società Gasdotti Italia |  | Advanced Non-FID | 2022 | No | Larino - Chieti | 110 | 600
Pipeline including CS | TRA-N-974 | LARINO - RECANATI Adriatic coast backbone | Società Gasdotti Italia |  | Advanced Non-FID | 2022 | No | San Marco-Recanati | 32 | 600 | 3
Pipeline including CS | TRA-N-974 | LARINO - RECANATI Adriatic coast backbone | Società Gasdotti Italia |  | Advanced Non-FID | 2022 | No | Cellino-San Marco | 90 | 500
Pipeline including CS | TRA-N-974 | LARINO - RECANATI Adriatic coast backbone | Società Gasdotti Italia |  | Advanced Non-FID | 2022 | No | Chieti-Cellino | 55 | 500
Pipeline including CS | TRA-N-660 | Gas to the West | West Transmission Limited |  | Less-Advanced Non-FID | 2017 | No | West Transmission Limited | 77 | 400
Pipeline including CS | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | Magyar Gáz Tranzit Zrt. |  | Less-Advanced Non-FID | 2017 | No | Slovak | 18 | 800
Pipeline including CS | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | Magyar Gáz Tranzit Zrt. |  | Less-Advanced Non-FID | 2017 | No | Hungarian section | 92 | 800
Pipeline including CS | TRA-N-636 | Development of Transmission Capacity at Slovak-Hungarian interconnector | Magyar Gáz Tranzit Zrt. |  | Less-Advanced Non-FID | 2017 | No | Slovak section | 18 | 800
Pipeline including CS | TRA-N-636 | Development of Transmission Capacity at Slovak-Hungarian interconnector | Magyar Gáz Tranzit Zrt. |  | Less-Advanced Non-FID | 2017 | No | Hungarian section | 92 | 800
Pipeline including CS | TRA-N-645 | HU-UA Interconnector (Ukrainian section) | PJSC Ukrtransgaz |  | Less-Advanced Non-FID | 2017 | No
Pipeline including CS | TRA-N-954 | TAG Reverse Flow | Trans Austria Gasleitung GmbH |  | Less-Advanced Non-FID | 2018 | No
Pipeline including CS | TRA-N-357 | NTS developments in North-East Romania | SNTGN Transgaz SA |  | Less-Advanced Non-FID | 2018 | No | Onesti - Letcani | 165 | 711 | 10
Pipeline including CS | TRA-N-545 | Infrastructure gas pipeline Skopje - Tetovo - Gostivar - Albanian border | GA-MA joint stock company Skopje |  | Less-Advanced Non-FID | 2018 | No | Infrastructure gas pipeline Skopje - Tetovo - Gostivar - Albanian border | 165 | 500
Pipeline including CS | TRA-N-379 | ​A project for the construction of a gas pipeline BG-RO | Bulgartransgaz EAD |  | Less-Advanced Non-FID | 2018 | No | ​A project for the construction of a gas pipeline (pipelines) aiming at exp
Pipeline including CS | TRA-N-365 | M6 Ajdovščina – Lucija | Plinovodi d.o.o. |  | Less-Advanced Non-FID | 2019 | No | M6 Ajdovščina - Lucija | 69 | 250
Pipeline including CS | TRA-N-941 | Metering and Regulating station at Nea Messimvria | DESFA S.A. |  | Less-Advanced Non-FID | 2019 | No | Nea-Messivria to TAP | 1
Pipeline including CS | TRA-N-139 | Interconnection of the NTS with the DTS and reverse flow at Isaccea | SNTGN Transgaz SA |  | Less-Advanced Non-FID | 2019 | No | Onesti-Isaccea | 77 | 813 | 22
Pipeline including CS | TRA-N-561 | Poland-Ukraine Interconnector (Ukrainian section) | PJSC Ukrtransgaz |  | Less-Advanced Non-FID | 2019 | No | Drozdovychi - Bilche Volytsya | 110 | 1000
Pipeline including CS | TRA-N-964 | New NTS developments for taking over gas from the Black Sea shore | SNTGN Transgaz SA |  | Less-Advanced Non-FID | 2019 | No | Black Sea Shore - T1 | 30
Pipeline including CS | TRA-N-340 | VDS Wertingen | bayernets GmbH |  | Less-Advanced Non-FID | 2019 | No
Pipeline including CS | TRA-N-582 | Macedonian part of Tesla project | GA-MA joint stock company Skopje |  | Less-Advanced Non-FID | 2019 | No
Pipeline including CS | TRA-N-140 | Interconnection Turkey-Bulgaria | Bulgartransgaz EAD |  | Less-Advanced Non-FID | 2020 | No | ITB Bulgarian Section | 76 | 700 | 13
Pipeline including CS | TRA-N-140 | Interconnection Turkey-Bulgaria | Bulgartransgaz EAD |  | Less-Advanced Non-FID | 2020 | No | ITB Turkish Section | 130
Pipeline including CS | TRA-N-191 | Blending | Gasunie Transport Services B.V. |  | Less-Advanced Non-FID | 2020 | No
Pipeline including CS | TRA-N-325 | Slovenian-Hungarian interconnector | FGSZ Ltd. |  | Less-Advanced Non-FID | 2020 | No | Nagykanizsa-Tornyiszentmiklós | 41 | 500 | 9
Pipeline including CS | TRA-N-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A |  | Less-Advanced Non-FID | 2020 | No | EastMed pipeline: section from Crete to Peloponnese | 421 | 813 | 100
Pipeline including CS | TRA-N-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A |  | Less-Advanced Non-FID | 2020 | No | EastMed pipeline: section from Cyprus to Crete | 732 | 660 | 125
Pipeline including CS | TRA-N-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A |  | Less-Advanced Non-FID | 2020 | No | EastMed pipeline: section from Levantine Basin to Cyprus | 165 | 610
Pipeline including CS | TRA-N-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A |  | Less-Advanced Non-FID | 2020 | No | EastMed pipeline: section from West Greece to Thesprotia | 236 | 1070
Pipeline including CS | TRA-N-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A |  | Less-Advanced Non-FID | 2020 | No | EastMed: section from Peloponnese to West Greece | 317 | 1170
Pipeline including CS | TRA-N-382 | Enhancement of Latvia-Lithuania interconnection (Latvian part) | JSC "Latvijas Gaze" |  | Less-Advanced Non-FID | 2020 | No | Riga-Iecava-Lithuanian border | 93 | 700
Pipeline including CS | TRA-N-829 | PCI 5.1.1 Physical Reverse Flow at Moffat interconnection point (IE/UK) | GNI (UK) Limited |  | Less-Advanced Non-FID | 2020 | No | interconnector 1 & 2 | 100 | 914 | 40
Pipeline including CS | TRA-N-882 | H-gas conversion of L-gas export border points | Gasunie Transport Services B.V. |  | Less-Advanced Non-FID | 2020 | No
Pipeline including CS | TRA-N-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Gastransport Nord GmbH |  | Less-Advanced Non-FID | 2020 | No
Pipeline including CS | TRA-N-957 | Metering Station at Komotini to IGB | DESFA S.A. |  | Less-Advanced Non-FID | 2020 | No
Pipeline including CS | TRA-N-094 | CS Kidričevo, 2nd phase of upgrade | Plinovodi d.o.o. |  | Less-Advanced Non-FID | 2020 | No | CS Kidričevo, 2nd phase of upgrade |  |  | 30
Pipeline including CS | TRA-N-108 | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia | Plinovodi d.o.o. |  | Less-Advanced Non-FID | 2020 | No | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia | 31 | 500
Pipeline including CS | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Plinovodi d.o.o. |  | Less-Advanced Non-FID | 2020 | No | R15/1 Pince - Lendava - Kidričevo | 73 | 500 | 4
Pipeline including CS | TRA-N-128 | Compressor Station Kipi | DESFA S.A. |  | Less-Advanced Non-FID | 2020 | Yes (See Project Fiche) | Kipi | 0 | 0 | 9
Pipeline including CS | TRA-N-128 | Compressor Station Kipi | DESFA S.A. |  | Less-Advanced Non-FID | 2020 | Yes (See Project Fiche) | Kipi | 0 | 0 | 18
Pipeline including CS | TRA-N-192 | Entry capacity expansion GATE terminal | Gasunie Transport Services B.V. |  | Less-Advanced Non-FID | 2020 | No | Maasvlakte - Wijngaarden | 25 | 1200
Pipeline including CS | TRA-N-342 | Enhancement of Latvia-Lithuania interconnection (Lithuania's part) | AB Amber Grid |  | Less-Advanced Non-FID | 2020 | No
Pipeline including CS | TRA-N-362 | Development on the Romanian territory of the Southern Transmission Corridor | SNTGN Transgaz SA |  | Less-Advanced Non-FID | 2020 | No | Black Sea - Podişor | 307 | 1200
Pipeline including CS | TRA-N-586 | HU-UA reverse flow | FGSZ Ltd. |  | Less-Advanced Non-FID | 2020 | No | Hungarian section | 0
Pipeline including CS | TRA-N-631 | Greek part of Tesla project | DESFA S.A. |  | Less-Advanced Non-FID | 2020 | No | Greek section | 370 | 1400 | 280
Pipeline including CS | TRA-N-940 | Metering and Regulating station at Komotini | DESFA S.A. |  | Less-Advanced Non-FID | 2020 | No
Pipeline including CS | TRA-N-967 | Nea-Messimvria to FYROM pipeline | DESFA S.A. |  | Less-Advanced Non-FID | 2020 | No | Nea-Messimvria to Pontoiraklia/Stojakovo | 50 | 700
Pipeline including CS | TRA-N-286 | Romanian-Hungarian reverse flow Hungarian section 1st stage | FGSZ Ltd. |  | Less-Advanced Non-FID | 2020 | No | Csanadpalota |  |  | 9
Pipeline including CS | TRA-N-298 | Rehabilitation, Modernization and Expansion of the NTS | Bulgartransgaz EAD |  | Less-Advanced Non-FID | 2020 | No | PF Beglej - VA Dermantsi - VA Batultsi - VA Kalugerovo | 58 | 700
Pipeline including CS | TRA-N-298 | Rehabilitation, Modernization and Expansion of the NTS | Bulgartransgaz EAD |  | Less-Advanced Non-FID | 2020 | No | Lozenets-Nedyalsko | 20 | 1000
Pipeline including CS | TRA-N-298 | Rehabilitation, Modernization and Expansion of the NTS | Bulgartransgaz EAD |  | Less-Advanced Non-FID | 2020 | No | Gorni Bogrov - Novi Iskar | 19 | 700 | 20
Pipeline including CS | TRA-N-298 | Rehabilitation, Modernization and Expansion of the NTS | Bulgartransgaz EAD |  | Less-Advanced Non-FID | 2020 | No | Valchi Dol - Preselka | 23 | 700
Pipeline including CS | TRA-N-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT Corridor) | SNTGN Transgaz S.A. |  | Less-Advanced Non-FID | 2020 | No | Podisor - Horia | 528 | 813 | 50
Pipeline including CS | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak) | Plinovodi d.o.o. |  | Less-Advanced Non-FID | 2020 | No | Upgrade of Murfeld/Ceršak interconnection | 0 | 800
Pipeline including CS | TRA-N-585 | Hungarian section of Tesla project | FGSZ Ltd. |  | Less-Advanced Non-FID | 2020 | No | Hungarian section | 361 | 1200 | 50
Pipeline including CS | TRA-N-621 | Poland - Ukraine Gas interconnection (PL section) | GAZ-SYSTEM S.A. |  | Less-Advanced Non-FID | 2020 | No | Pipeline Hermanowice -PL/UA border | 2 | 1000
Pipeline including CS | TRA-N-621 | Poland - Ukraine Gas interconnection (PL section) | GAZ-SYSTEM S.A. |  | Less-Advanced Non-FID | 2020 | No | Hermanowice-Strachocina | 72 | 700
Pipeline including CS | TRA-N-621 | Poland - Ukraine Gas interconnection (PL section) | GAZ-SYSTEM S.A. |  | Less-Advanced Non-FID | 2020 | No | Strachocina CS |  |  | 30
Pipeline including CS | TRA-N-950 | Guitiriz - Zamora pipeline | Reganosa |  | Less-Advanced Non-FID | 2020 | No | Guitiriz Zamora | 320 | 762 | 16840
Pipeline including CS | TRA-N-951 | Embedding CS Folmhusen in H-Gas | Gasunie Deutschland Transport Services GmbH |  | Less-Advanced Non-FID | 2020 | No
Pipeline including CS | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | Plinacro Ltd |  | Less-Advanced Non-FID | 2020 | No
Pipeline including CS | TRA-N-1064 | Moffat Physical Reverse Flow | National Grid Gas plc |  | Less-Advanced Non-FID | 2020 | No
Pipeline including CS | TRA-N-1090 | Metering and Regulating Station at Alexandroupoli | DESFA S.A. |  | Less-Advanced Non-FID | 2020 | No
Pipeline including CS | TRA-N-092 | CS Ajdovščina, 1st phase of upgrade | Plinovodi d.o.o. |  | Less-Advanced Non-FID | 2021 | No | CS Ajdovščina, 1st phase of upgrade |  |  | 5
Pipeline including CS | TRA-N-329 | ZEELINK | Open Grid Europe GmbH |  | Less-Advanced Non-FID | 2021 | No
Pipeline including CS | TRA-N-654 | Eastring - Bulgaria | Bulgartransgaz EAD |  | Less-Advanced Non-FID | 2021 | Yes (See Project Fiche) | Eastring-BG-3 | 0 | 1200 | 0
Pipeline including CS | TRA-N-654 | Eastring - Bulgaria | Bulgartransgaz EAD |  | Less-Advanced Non-FID | 2021 | Yes (See Project Fiche) | Eastring-BG-4 | 257 | 1400 | 90
Pipeline including CS | TRA-N-654 | Eastring - Bulgaria | Bulgartransgaz EAD |  | Less-Advanced Non-FID | 2021 | Yes (See Project Fiche) | Eastring-BG-2 | 257 | 1400 | 88
Pipeline including CS | TRA-N-654 | Eastring - Bulgaria | Bulgartransgaz EAD |  | Less-Advanced Non-FID | 2021 | Yes (See Project Fiche) | Eastring-BG-1 | 0 | 1200 | 0
Pipeline including CS | TRA-N-831 | Vecsés-Városföld gas transit pipeline | Magyar Gáz Tranzit Zrt. |  | Less-Advanced Non-FID | 2021 | No | Vecsés-Városföld | 80 | 800
Pipeline including CS | TRA-N-976 | Interconnection Macedonia-Bulgaria | MER JSC Skopje |  | Less-Advanced Non-FID | 2021 | No | Main gas pipeline section Hamzali – Novo Selo (border with Bulgaria) | 25 | 700
Pipeline including CS | TRA-N-027 | Physical reverse flow from NI to GB and IE via SNIP pipeline | Premier Transmission Limited |  | Less-Advanced Non-FID | 2021 | No | SNIP-Scotland to Northern Ireland |  | 600 | 10
Pipeline including CS | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Enagás Transporte, S.A.U. |  | Less-Advanced Non-FID | 2021 | No | Zamora - Portuguese Border | 86 | 700
Pipeline including CS | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Enagás Transporte, S.A.U. |  | Less-Advanced Non-FID | 2021 | No | CS Zamora |  |  | 4
Pipeline including CS | TRA-N-628 | Eastring - Slovakia | Eastring B.V. |  | Less-Advanced Non-FID | 2021 | Yes (See Project Fiche) | Eastring-SK-1 | 19 | 1400 | 42
Pipeline including CS | TRA-N-628 | Eastring - Slovakia | Eastring B.V. |  | Less-Advanced Non-FID | 2021 | Yes (See Project Fiche) | Eastring-SK-2 | 19 | 1400 | 52
Pipeline including CS | TRA-N-628 | Eastring - Slovakia | Eastring B.V. |  | Less-Advanced Non-FID | 2021 | Yes (See Project Fiche) | Eastring-SK-3/4 | 0 | 1400 | 0
Pipeline including CS | TRA-N-655 | Eastring - Romania | SNTGN Transgaz SA |  | Less-Advanced Non-FID | 2021 | No
Pipeline including CS | TRA-N-656 | Eastring - Hungary | FGSZ Ltd. |  | Less-Advanced Non-FID | 2021 | No | Eastring-HU-1/2 | 112 | 1400 | 0
Pipeline including CS | TRA-N-851 | Southern Interconnection pipeline BiH/CRO | BH-GAS d.o.o. |  | Less-Advanced Non-FID | 2021 | No | Posusje-Travnik with branch to Mostar | 165 | 500 | 0
Pipeline including CS | TRA-N-980 | Interconnection Macedonia-Greece | MER JSC Skopje |  | Less-Advanced Non-FID | 2021 | No | Stip-Hamzali-Stojakovo (border with Greece) | 110 | 700
Pipeline including CS | TRA-N-1138 | South Caucasus Pipeline Future Expansion - SCPFX | SOCAR Midstream Operations LLC |  | Less-Advanced Non-FID | 2021 | No | South-Caucasus Pipeline | 93 | 1219 | 80
Pipeline including CS | TRA-N-873 | Capacity expansion OSZ related to West Stream | Gasunie Transport Services B.V. |  | Less-Advanced Non-FID | 2021 | No
Pipeline including CS | TRA-N-965 | Interconnection Macedonia-Serbia | MER JSC Skopje |  | Less-Advanced Non-FID | 2021 | No | Main gas pipeline section Klechovce-Sopot (border with Serbia) | 23 | 500
Pipeline including CS | TRA-N-047 | Reverse capacity from France to Germany at Obergailbach | GRTgaz |  | Less-Advanced Non-FID | 2022 | No | Morelmaison CS |  |  | 0
Pipeline including CS | TRA-N-047 | Reverse capacity from France to Germany at Obergailbach | GRTgaz |  | Less-Advanced Non-FID | 2022 | No | Artère du Nord-Est | 87 | 1050 | 0
Pipeline including CS | TRA-N-047 | Reverse capacity from France to Germany at Obergailbach | GRTgaz |  | Less-Advanced Non-FID | 2022 | No | Cheppy CS
Pipeline including CS | TRA-N-047 | Reverse capacity from France to Germany at Obergailbach | GRTgaz |  | Less-Advanced Non-FID | 2022 | No | Obergailbach interconnection station
Pipeline including CS | TRA-N-047 | Reverse capacity from France to Germany at Obergailbach | GRTgaz |  | Less-Advanced Non-FID | 2022 | No | Dierrey CS
Pipeline including CS | TRA-N-047 | Reverse capacity from France to Germany at Obergailbach | GRTgaz |  | Less-Advanced Non-FID | 2022 | No | Voisines CS
Pipeline including CS | TRA-N-061 | Ercsi-Szazhalombatta | FGSZ Ltd. |  | Less-Advanced Non-FID | 2022 | No | Ercsi-Szazhalombatta | 11 | 800
Pipeline including CS | TRA-N-053 | White Stream | White Stream Ltd |  | Less-Advanced Non-FID | 2022 | No | Vale to Supsa | 135 | 1039
Pipeline including CS | TRA-N-053 | White Stream | White Stream Ltd |  | Less-Advanced Non-FID | 2022 | No | Supsa to Constanta | 1115 | 726 | 375
Pipeline including CS | TRA-N-093 | CS Ajdovščina, 2nd phase of upgrade | Plinovodi d.o.o. |  | Less-Advanced Non-FID | 2022 | No | CS Ajdovščina, 2nd phase of upgrade |  |  | 20
Pipeline including CS | TRA-N-099 | M3/1a Šempeter - Ajdovščina | Plinovodi d.o.o. |  | Less-Advanced Non-FID | 2022 | No | M3/1a Šempeter - Ajdovščina | 30 | 1100
Pipeline including CS | TRA-N-101 | M8 Kalce - Jelšane | Plinovodi d.o.o. |  | Less-Advanced Non-FID | 2022 | No | M8 Kalce - Jelšane | 60 | 1200
Pipeline including CS | TRA-N-107 | M6 Interconnection Osp | Plinovodi d.o.o. |  | Less-Advanced Non-FID | 2022 | No | M6 Interconnection Osp | 1 | 250
Pipeline including CS | TRA-N-123 | Városföld CS | FGSZ Ltd. |  | Less-Advanced Non-FID | 2022 | No | Városföld CS |  |  | 6
Pipeline including CS | TRA-N-261 | M3/1c Kalce - Vodice | Plinovodi d.o.o. |  | Less-Advanced Non-FID | 2022 | No | M3/1c Kalce - Vodice | 47 | 1100
Pipeline including CS | TRA-N-271 | Poland - Denmark interconnection (Baltic Pipe) - PL section | GAZ-SYSTEM S.A. |  | Less-Advanced Non-FID | 2022 | No | Mogilno - Odolanow pipeline | 165 | 1000
Pipeline including CS | TRA-N-271 | Poland - Denmark interconnection (Baltic Pipe) - PL section | GAZ-SYSTEM S.A. |  | Less-Advanced Non-FID | 2022 | No | Baltic Pipe (offshore section) | 280 | 900
Pipeline including CS | TRA-N-271 | Poland - Denmark interconnection (Baltic Pipe) - PL section | GAZ-SYSTEM S.A. |  | Less-Advanced Non-FID | 2022 | No | Damaslawek - Mogilno pipeline | 50 | 1200
Pipeline including CS | TRA-N-271 | Poland - Denmark interconnection (Baltic Pipe) - PL section | GAZ-SYSTEM S.A. |  | Less-Advanced Non-FID | 2022 | No | Onshore terminal - Ploty | 80 | 1000
Pipeline including CS | TRA-N-271 | Poland - Denmark interconnection (Baltic Pipe) - PL section | GAZ-SYSTEM S.A. |  | Less-Advanced Non-FID | 2022 | No | Ploty-Damaslawek pipeline | 240 | 1200
Pipeline including CS | TRA-N-428 | (Mirror) Baltic Pipe | Energinet.dk |  | Less-Advanced Non-FID | 2022 | No
Pipeline including CS | TRA-N-593 | Varna-Oryahovo gas pipeline | Bulgartransgaz EAD |  | Less-Advanced Non-FID | 2022 | No | Varna-Oryahovo gas pipeline | 844 | 1200 | 265
Pipeline including CS | TRA-N-018 | Városföld-Ercsi-Győr | FGSZ Ltd. |  | Less-Advanced Non-FID | 2022 | No | Városfold-Ercsi-Gyor | 210 | 1000
Pipeline including CS | TRA-N-998 | Interconnection Macedonia-Albania | MER JSC Skopje |  | Less-Advanced Non-FID | 2022 | No
Pipeline including CS | TRA-N-1091 | Metering and Regulating station at Megalopoli | DESFA S.A. |  | Less-Advanced Non-FID | 2022 | No
Pipeline including CS | TRA-N-071 | Physical Reverse Flow on South North Pipeline | Gas Networks Ireland |  | Less-Advanced Non-FID | 2022 | No
Pipeline including CS | TRA-N-135 | Connection to Oberkappel | NET4GAS, s.r.o. |  | Less-Advanced Non-FID | 2022 | No | Záboří (CZ) - CZ/AT Border | 75 | 800 | 2
Pipeline including CS | TRA-N-258 | Developments for Montoir LNG terminal 2.5 bcm expansion | GRTgaz |  | Less-Advanced Non-FID | 2022 | No | Artère du Maine | 200 | 1050
Pipeline including CS | TRA-N-258 | Developments for Montoir LNG terminal 2.5 bcm expansion | GRTgaz |  | Less-Advanced Non-FID | 2022 | No | Auvers-le-Hamon CS |  |  | 0
Pipeline including CS | TRA-N-258 | Developments for Montoir LNG terminal 2.5 bcm expansion | GRTgaz |  | Less-Advanced Non-FID | 2022 | No | Artère du Perche | 63 | 900
Pipeline including CS | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | GRTgaz |  | Less-Advanced Non-FID | 2022 | No | Palleau CS |  |  | 50
Pipeline including CS | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | GRTgaz |  | Less-Advanced Non-FID | 2022 | No | St-Martin de Crau CS |  |  | 30
Pipeline including CS | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | GRTgaz |  | Less-Advanced Non-FID | 2022 | No | Arc Lyonnais | 150 | 1200
Pipeline including CS | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | GRTgaz |  | Less-Advanced Non-FID | 2022 | No | Eridan | 220 | 1200
Pipeline including CS | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | GRTgaz |  | Less-Advanced Non-FID | 2022 | No | Perche | 63 | 900
Pipeline including CS | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | GRTgaz |  | Less-Advanced Non-FID | 2022 | No | St-Avit CS |  |  | 15
Pipeline including CS | TRA-N-594 | Construction of a Looping CS Provadia – Rupcha village | Bulgartransgaz EAD |  | Less-Advanced Non-FID | 2022 | No | Looping CS Provadia – Rupcha village | 50 | 1200 | 10
Pipeline including CS | TRA-N-594 | Construction of a Looping CS Provadia – Rupcha village | Bulgartransgaz EAD |  | Less-Advanced Non-FID | 2022 | No | CS Strandja – a new IP with Turkey. | 20 | 1000
Pipeline including CS | TRA-N-727 | Iberian‐French corridor: Eastern Axis ‐ Midcat Project | Enagás Transporte, S.A.U. |  | Less-Advanced Non-FID | 2022 | No | Loop Castelnou – Villar de Arnedo + CS Zaragoza (increment) | 214 | 640 | 5
Pipeline including CS | TRA-N-727 | Iberian‐French corridor: Eastern Axis ‐ Midcat Project | Enagás Transporte, S.A.U. |  | Less-Advanced Non-FID | 2022 | No | Loop Tivissa – Arbós + CS Tivissa filters + CS Arbós (increment) | 114 | 740 | 21
Pipeline including CS | TRA-N-971 | Compressor station at Nea Messimvria | DESFA S.A. |  | Less-Advanced Non-FID | 2022 | No | Nea Messimvria to TAP |  |  | 27
Pipeline including CS | TRA-N-262 | M3/1b Ajdovščina - Kalce | Plinovodi d.o.o. |  | Less-Advanced Non-FID | 2022 | No | M3/1b Ajdovščina - Kalce | 24 | 1100
Pipeline including CS | TRA-N-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | FGSZ Ltd. |  | Less-Advanced Non-FID | 2022 | No | Csanádpalota |  |  | 4
Pipeline including CS | TRA-N-394 | Gassled - Danish upstream system | Energinet.dk |  | Less-Advanced Non-FID | 2022 | No
Pipeline including CS | TRA-N-592 | Looping CS Valchi Dol - Line valve Novi Iskar | Bulgartransgaz EAD |  | Less-Advanced Non-FID | 2022 | No | Looping CS Valchi Dol - Line valve Novi Iskar | 383 | 700
Pipeline including CS | TRA-N-780 | Nybro-Interconnector PL-DK - reinforcement | Energinet.dk |  | Less-Advanced Non-FID | 2022 | No
Pipeline including CS | TRA-N-966 | Interconnection Macedonia-Kosovo | MER JSC Skopje |  | Less-Advanced Non-FID | 2022 | No | Main gas pipeline section Matka-Grachani (border with Kosovo) | 16 | 500
Pipeline including CS | TRA-N-007 | Development for new import from the South (Adriatica Line) | Snam Rete Gas S.p.A. |  | Less-Advanced Non-FID | 2023 | No | All the pipe | 430 | 1200 | 33
Pipeline including CS | TRA-N-014 | Komotini-Thesprotia pipeline | DESFA S.A. |  | Less-Advanced Non-FID | 2023 | No | Komotini-Thesprotia | 613 | 1067 | 58
Pipeline including CS | TRA-N-354 | Interconnection with Slovenia | Snam Rete Gas S.p.A. |  | Less-Advanced Non-FID | 2023 | No | All the pipe | 6 | 250 | 0
Pipeline including CS | TRA-N-1092 | Metering and Regulating Station at UGS South Kavala | DESFA S.A. |  | Less-Advanced Non-FID | 2023 | No
Pipeline including CS | TRA-N-070 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo) | Plinacro Ltd |  | Less-Advanced Non-FID | 2023 | No | Slobodnica - Sotin | 97 | 800
Pipeline including CS | TRA-N-070 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo) | Plinacro Ltd |  | Less-Advanced Non-FID | 2023 | No | Sotin- Bačko Novo Selo | 5 | 800
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. |  | Less-Advanced Non-FID | 2023 | No | CS Pomorze |  |  | 35
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. |  | Less-Advanced Non-FID | 2023 | No | Gustorzyn-Wronow pipeline | 410 | 1200
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. |  | Less-Advanced Non-FID | 2023 | No | Kolnik-Gustorzyn pipeline | 230 | 1200
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. |  | Less-Advanced Non-FID | 2023 | No | Hermanowice-Jaroslaw pipeline | 39 | 700
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. |  | Less-Advanced Non-FID | 2023 | No | Pierscien Trojmiejski | 100 | 1000
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. |  | Less-Advanced Non-FID | 2023 | No | Hermanowice-Strachocina pipeline | 72 | 700
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. |  | Less-Advanced Non-FID | 2023 | No | Rembelszczyzna compressor station |  |  | 23
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. |  | Less-Advanced Non-FID | 2023 | No | Jaroslaw-Rozwadow pipeline | 60 | 700
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. |  | Less-Advanced Non-FID | 2023 | No | Rembelszczyzna-Wronow pipeline | 135 | 1000
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. |  | Less-Advanced Non-FID | 2023 | No | Rozwadow-Konskowola-Wronow pipeline | 103 | 700
Pipeline including CS | TRA-N-755 | CS Rimpar | GRTgaz Deutschland GmbH |  | Less-Advanced Non-FID | 2023 | No | CS Rimpar / MEGAL |  |  | 39
Pipeline including CS | TRA-N-809 | Additional East-West transport NL | Gasunie Deutschland Transport Services GmbH |  | Less-Advanced Non-FID | 2023 | No
Pipeline including CS | TRA-N-825 | Compressor station "Legden" | Open Grid Europe GmbH |  | Less-Advanced Non-FID | 2023 | No
Pipeline including CS | TRA-N-224 | Gaspipeline Brod - Zenica | BH-Gas d.o.o. |  | Less-Advanced Non-FID | 2023 | No | Brod-Zenica (section through FBiH and RS) | 140 | 500 | 0
Pipeline including CS | TRA-N-910 | Western interconnection BiH/CRO | BH-Gas d.o.o. |  | Less-Advanced Non-FID | 2023 | No | Licka Jesenica - Trzac - Bos.Krupa | 35 | 500 | 0
Pipeline including CS | TRA-N-959 | Further enlargement of the BG—RO—HU—AT transmission corridor (BRUA) phase 3 | SNTGN Transgaz SA |  | Less-Advanced Non-FID | 2023 | No | Onesti - Nadlac | 843 | 813 | 82
Pipeline including CS | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | Plinacro Ltd |  | Less-Advanced Non-FID | 2023 | No | Kozarac-Slobodnica | 128 | 800
Pipeline including CS | TRA-N-114 | R61 Dragonja - Izola | Plinovodi d.o.o. |  | Less-Advanced Non-FID | 2024 | No | R61 Dragonja - Izola | 10 | 300
Pipeline including CS | TRA-N-380 | BG-RO-HU-AT transmission corridor | FGSZ Ltd. |  | Less-Advanced Non-FID | 2024 | No | Csanádpalota-Városföld | 115 | 1000 | 54
Pipeline including CS | TRA-N-380 | BG-RO-HU-AT transmission corridor | FGSZ Ltd. |  | Less-Advanced Non-FID | 2024 | No | Győr-HU/AT border Mosonmagyaróvár | 71 | 1000 | 0
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF |  | Less-Advanced Non-FID | 2024 | No | Arc Lyonnais (GRTgaz section) | 150 | 1200
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF |  | Less-Advanced Non-FID | 2024 | No | Barbaira CS (TIGF section) |  |  | 7
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF |  | Less-Advanced Non-FID | 2024 | No | Midi pipeline (GRTgaz section) | 200 | 1050
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF |  | Less-Advanced Non-FID | 2024 | No | Midi pipeline (TIGF section) | 40 | 1050
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF |  | Less-Advanced Non-FID | 2024 | No | Barbaira - Border (TIGF section) | 120 | 900
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF |  | Less-Advanced Non-FID | 2024 | No | Perche (GRTgaz section) | 63 | 900
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF |  | Less-Advanced Non-FID | 2024 | No | St-Martin de Crau CS |  |  | 30
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF |  | Less-Advanced Non-FID | 2024 | No | Eridan (GRTgaz section) | 220 | 1200
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF |  | Less-Advanced Non-FID | 2024 | No | Palleau CS (GRTgaz section) |  |  | 50
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF |  | Less-Advanced Non-FID | 2024 | No | St-Avit CS (GRTgaz section) |  |  | 15
Pipeline including CS | TRA-N-285 | 3rd IP between Portugal and Spain (pipeline Cantanhede-Mangualde) | REN-Gasodutos, S.A. |  | Less-Advanced Non-FID | 2025 | No | Pipeline Cantanhede-Mangualde | 67 | 500
Pipeline including CS | TRA-N-729 | Interconnection ES-PT (3rd IP) - 2nd phase | Enagás Transporte, S.A.U. |  | Less-Advanced Non-FID | 2025 | No | Castropodame - Zamora | 170 | 600
Pipeline including CS | TRA-N-729 | Interconnection ES-PT (3rd IP) - 2nd phase | Enagás Transporte, S.A.U. |  | Less-Advanced Non-FID | 2025 | No | Lugo - Villafranca del Bierzo | 90 | 740
Pipeline including CS | TRA-N-729 | Interconnection ES-PT (3rd IP) - 2nd phase | Enagás Transporte, S.A.U. |  | Less-Advanced Non-FID | 2025 | No | Zamora - La Barbolla - Adradas | 307 | 800
Pipeline including CS | TRA-N-729 | Interconnection ES-PT (3rd IP) - 2nd phase | Enagás Transporte, S.A.U. |  | Less-Advanced Non-FID | 2025 | No | Guitiriz - Lugo | 28 | 740
Pipeline including CS | TRA-N-729 | Interconnection ES-PT (3rd IP) - 2nd phase | Enagás Transporte, S.A.U. |  | Less-Advanced Non-FID | 2025 | No | Villafranca del Bierzo - Castropodame | 30 | 740
Pipeline including CS | TRA-N-284 | 3rd IP between Portugal and Spain (Compressor Station) | REN-Gasodutos, S.A. |  | Less-Advanced Non-FID | 2025 | No | Cantanhede Compressor Station |  |  | 12
Pipeline including CS | TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Plinacro Ltd |  | Less-Advanced Non-FID | 2026 | No | Rakovica-Bihać | 10 | 500
Pipeline including CS | TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Plinacro Ltd |  | Less-Advanced Non-FID | 2026 | No | Lička Jesenica-Rakovica | 20 | 500
Pipeline including CS | TRA-N-031 | Connection of Malta to the European Gas Network - Pipelines | Office of the Prime Minister (Energy) |  | Less-Advanced Non-FID | 2026 | No | FSRU (Malta) to Delimara (Malta) | 12 | 560
Pipeline including CS | TRA-N-031 | Connection of Malta to the European Gas Network - Pipelines | Office of the Prime Minister (Energy) |  | Less-Advanced Non-FID | 2026 | No | Delimara (Malta) to Gela (Sicily) Italy | 155 | 560
Pipeline including CS | TRA-N-376 | Azerbaijan, Georgia, Romania Interconnector - AGRI | AGRI LNG Project Company SRL (RO) |  | Less-Advanced Non-FID | 2026 | No
Pipeline including CS | TRA-N-336 | Interconnection Croatia/Slovenia (Umag-Koper) | Plinacro Ltd |  | Less-Advanced Non-FID | 2026 | No | Umag - Plovanija (HR)- Koper (SI) | 8 | 300
Pipeline including CS | TRA-N-955 | GUD: Complete conversion to H-gas | Gasunie Deutschland Transport Services GmbH |  | Less-Advanced Non-FID | 2030 | No
Pipeline including CS | TRA-N-975 | Sardinia Gas Transportation Network | Società Gasdotti Italia |  | Less-Advanced Non-FID | 2031 | No
Pipeline including CS | TRA-N-009 | Additional Southern developments | Snam Rete Gas S.p.A. |  | Less-Advanced Non-FID | 2034 | No | Section 2 | 115 | 1050 | 0
Pipeline including CS | TRA-N-009 | Additional Southern developments | Snam Rete Gas S.p.A. |  | Less-Advanced Non-FID | 2034 | No | Section 1 | 255 | 800 | 0
Pipeline including CS | TRA-N-009 | Additional Southern developments | Snam Rete Gas S.p.A. |  | Less-Advanced Non-FID | 2034 | No | Section 3 | 590 | 1200 | 0
Pipeline including CS | TRA-N-009 | Additional Southern developments | Snam Rete Gas S.p.A. |  | Less-Advanced Non-FID | 2034 | No | Section 4 | 0 | 0 | 60
Pipeline including CS | TRA-N-008 | Import developments from North-East | Snam Rete Gas S.p.A. |  | Less-Advanced Non-FID | 2034 | No | Section 1 | 15 | 1050 | 0
Pipeline including CS | TRA-N-008 | Import developments from North-East | Snam Rete Gas S.p.A. |  | Less-Advanced Non-FID | 2034 | No | Section 3 | 0 | 0 | 75
Pipeline including CS | TRA-N-008 | Import developments from North-East | Snam Rete Gas S.p.A. |  | Less-Advanced Non-FID | 2034 | No | Section 2 | 119 | 1400 | 0
Pipeline including CS | TRA-N-065 | Hajduszoboszlo CS | FGSZ Natural Gas transmission Company limited by Shares. |  | Less-Advanced Non-FID | Unknown | No | Hajduszoboszlo node |  |  | 0
Pipeline including CS | TRA-N-065 | Hajduszoboszlo CS | FGSZ Natural Gas transmission Company limited by Shares. |  | Less-Advanced Non-FID | Unknown | No | hajdúszoboszló CS |  |  | 6
Pipeline including CS | TRA-N-339 | Trans-Caspian | W-Stream Caspian Pipeline Company Ltd |  | Less-Advanced Non-FID | Unknown | No
Pipeline including CS | TRA-N-349 | Industrial Emisssion Directive (IPPC) - Non-FID | National Grid Gas plc |  | Less-Advanced Non-FID | Unknown | No
Pipeline including CS | TRA-N-346 | Industrial Emissions Directive (LCP) | National Grid Gas plc |  | Less-Advanced Non-FID | Unknown | No

## LNG Terminals
TYNDP Annex A |  |  |  | LNG Terminals - Page 4
LNG Terminals
Type | Code | Name | LNG Facility |  | Promoter | Status | Commissioning Year | Reloading Ability | Project Yearly Volume (bcm/y) | Project Ship Size (m3 LNG) | Project Storage Capacity (m3 LNG) | Yearly Volume Comments | Ship Size Comments | Storage Capacity Comments
LNG Terminal | LNG-F-147 | Revythoussa (2nd upgrade) | Revythoussa LNG Terminal |  | DESFA S.A. | FID | 2017 | Yes | 2.4 | 120000 | 95000 |  | 140.000 presently | 130,000 presently
LNG Terminal | LNG-F-229 | Zeebrugge LNG Terminal - 5th Tank & 2nd Jetty | Zeebrugge LNG Terminal |  | Fluxys LNG | FID | 2019 | Yes | 3 | 0 | 180000 |  | 3500 to 217 000 m³LNG
LNG Terminal | LNG-F-183 | Tenerife LNG Terminal | Tenerife LNG Terminal |  | Gascan | FID | 2020 |  | 1.3 | 200000 | 150000
LNG Terminal | LNG-F-163 | Gran Canaria LNG Terminal | Gran Canaria |  | Gascan | FID | 2021 |  | 1.3 | 140000 | 150000
LNG Terminal | LNG-F-178 | Musel LNG terminal | Musel |  | Enagás Transporte, S.A.U. | FID | 2026 |  | 7 | 266000 | 300000
LNG Terminal | LNG-N-062 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | LNG terminal in northern Greece / Alexandroupolis |  | Gastrade S.A. | Advanced Non-FID | 2018 | Yes | 6.1 | 170000 | 170000 | New regaseification technical capacity increment will be available from start of operations. | DWT 85,000 MT, LOA 300-310 m., Breadth 46 m., Draft 12m. | 4 storage tanks
LNG Terminal | LNG-N-082 | LNG terminal Krk | The import terminal for the liquefied natural gas(LNG) on the Island of Krk |  | LNG Hrvatska d.o.o. za poslovanje ukapljenim prirodnim plinom | Advanced Non-FID | 2018 | Yes | 4 | 265000 | 300000 | 1st stage - 1-4 bcm/y (According to FSRU ship and pepeline availability), 2nd stage - 3,5 bcm/y, 3rd stage - 5bcm/y, 4th stage - 8.75 bcm/y | 75,000.00 – 265,000.00 (Jetty construction and sea depth will enable Q Max LNG carriers to bearth at the site. The size of the carriers that are going to berth alongside to the FSRU will depend on the storage and regasification capabilities of the FSRU) | 1st stage depending on FSRU storage capacity availability, 2nd stage 1 x 150,000.00, 3rd stage 2 x 150,000.00, 4th stage 2 x 150,000.00
LNG Terminal | LNG-N-912 | Skulte LNG | FRU |  | AS Skulte LNG Terminal | Advanced Non-FID | 2019 | Yes | 4.6 | 170000 | 400 |  |  | No gas trorage needed - direct link to UGS
LNG Terminal | LNG-N-032 | Project GO4LNG LNG terminal Gothenburg | GO4LNG Gothenburg |  | Swedegas AB | Advanced Non-FID | 2020 | Yes | 0.5 | 75000 | 25000 |  | This size is subject to certain availability at the jetty. If not available, 15600 m3 is the limit. | 7,500 m3 bullet tanks or 25,000 m3 full containment tank
LNG Terminal | LNG-N-079 | Paldiski LNG Terminal | Paldiski LNG Terminal |  | Balti Gaas plc | Advanced Non-FID | 2020 | Yes | 0.4 | 175000 | 160000 | Preliminary estimate only | Dependent on tank size | There is size to increase the terminal to 320 000 m3.
LNG Terminal | LNG-N-198 | Porto Empedocle LNG | Porto Empedocle LNG |  | Nuove Energie S.r.l. | Advanced Non-FID | 2021 | Yes | 8 | 155000 | 320000 |  | Current design foresees that the terminal will be able to receive LNG tankers up to 155.000 m3 of capacity. Possible future studies to allow the berthing of larger ships
LNG Terminal | LNG-N-962 | Tallinn LNG | Tallinn LNG |  | Vopak E.O.S. AS / Vopak LNG Holdings B.V/ Port of Tallinn AS | Less-Advanced Non-FID | 2019 |  | 4 | 160000 | 160000 |  | Terminal berths can recieve any size LNG carrier on the market
LNG Terminal | LNG-N-050 | Gate terminal phase 3 | Gate terminal Rotterdam |  | Gate | Less-Advanced Non-FID | 2020 | Yes | 4 | 266000 | 180000 | additional 4 (in 10^9 Nm^3/y) |  | additional 180000 (in m^3 LNG)
LNG Terminal | LNG-N-225 | Montoir LNG Terminal Expansion | Montoir LNG Terminal |  | Elengy | Less-Advanced Non-FID | 2020 | Yes | 2.5 | 0 | 190000 | existing capacity: 10 bcm/y | Reception of Q-Max vessels is already operational | 1 possible additional tank (existing storage capacity: 3 x 120 000 m3)
LNG Terminal | LNG-N-227 | Fos Cavaou LNG Terminal Expansion | Fos Cavaou LNG Terminal |  | Fosmax LNG | Less-Advanced Non-FID | 2020 | Yes | 8.25 | 0 | 220000 | possible intermediate steps up to a doubling of the existing capacity | Reception of Q-Max vessels is already operational | up to 2 additional storage tanks (existing storage: 3 x 110 000 m3)
LNG Terminal | LNG-N-272 | Upgrade of LNG terminal in Świnoujście | LNG terminal in Świnoujście |  | GAZ-SYSTEM S.A. | Less-Advanced Non-FID | 2020 | Yes | 5 | 216000 | 200000
LNG Terminal | LNG-N-296 | Mugardos LNG Terminal: 2nd Jetty | Mugardos LNG Terminal |  | Reganosa | Less-Advanced Non-FID | 2020 | Yes | 0 | 0 | 0 |  | Existing jetty is yet compatible with Q-Max
LNG Terminal | LNG-N-328 | Eagle LNG and Pipeline | Eagle LNG |  | Burns Srl | Less-Advanced Non-FID | 2020 |  | 8 | 230000 | 230000
LNG Terminal | LNG-N-947 | FSRU Polish Baltic Sea Coast | FSRU Polish Baltic Sea Coast |  | GAZ-SYSTEM S.A. | Less-Advanced Non-FID | 2020 |  | 9 | 170000 | 170000 | The project under assessment (considered capacity ranges from 4.5 bcm/y up to 9 bcm/y)
LNG Terminal | LNG-N-217 | Onshore LNG terminal in the Northern Adriatic | Zaule LNG Terminal (Trieste - Italy) |  | Gas Natural Rigassificazione Italia | Less-Advanced Non-FID | 2021 |  | 8 | 145000 | 280000 |  |  | net storage capacity in 2 tanks
LNG Terminal | LNG-N-297 | Mugardos LNG Terminal: Storage Extension | Mugardos LNG Terminal |  | Reganosa | Less-Advanced Non-FID | 2022 | Yes | 0 | 0 | 190000
LNG Terminal | LNG-N-742 | Zeebrugge LNG Terminal - 3rd Jetty | Zeebrugge LNG Terminal |  | Fluxys LNG | Less-Advanced Non-FID | 2022 | Yes | 0.8 | 30000 | 0 |  | about 2.000 m³ up to about 30.000 m³
LNG Terminal | LNG-N-295 | Mugardos LNG Terminal: Send-out Increase | Mugardos LNG Terminal |  | Reganosa | Less-Advanced Non-FID | 2023 | Yes | 3.6 | 0 | 0
LNG Terminal | LNG-N-824 | LNG Terminal in Klaipeda | FSRU Independence |  | AB Klaipėdos Nafta | Less-Advanced Non-FID | 2024 | Yes | 4 | 170000 | 170000 |  |  | 170.000 m3 of LNG capacity for short period of time due to LNG aging
LNG Terminal | LNG-N-165 | Gran Canaria send out increase | Gran Canaria LNG Terminal |  | Gascan | Less-Advanced Non-FID | 2026 |  | 0.7 | 0 | 0
LNG Terminal | LNG-N-185 | Tenerife Send-Out increase | Tenerife LNG Terminal |  | Gascan | Less-Advanced Non-FID | 2026 |  | 0.7 | 0 | 0
LNG Terminal | LNG-N-211 | Connection of Malta to the European Gas Network - LNG Regasification | Malta FSRU Offshore Terminal |  | Office of the Prime Minister (Energy) | Less-Advanced Non-FID | 2031 | Yes | 2 | 135000 | 180000 | No change from TYNDP 2015 | No change from TYNDP 2015 | No change from TYNDP 2015
LNG Terminal | LNG-N-030 | Shannon LNG Terminal and Connecting Pipeline | Shannon LNG Limited |  | Shannon LNG | Less-Advanced Non-FID | Unknown |  | 2.7 | 265000 | 200000 | Year1: 2.7 Year2: 2.9 Year3: 3.4 | Up to 265,000 m3 LNG | up to 800,000 at full build out.
LNG Terminal | LNG-N-162 | Gran Canaria 2º LNG Tank | Gran Canaria LNG Terminal |  | Gascan | Less-Advanced Non-FID | Unknown |  | 0 | 0 | 150000
LNG Terminal | LNG-N-184 | Tenerife 2º LNG Storage Tank | Tenerife LNG Terminal |  | Gascan | Less-Advanced Non-FID | Unknown |  | 0 | 0 | 150000

## Underground Storages
| TYNDP Annex A |  |  |  | Underground Storages - Page 5
Underground Storages
Type |  | Code | Name | UGS Facility |  | Type | Promoter | Status | Commissioning Year | WGV (mcm) | WGV Comments
Storage Facility |  | UGS-F-259 | Bordolano first phase | Bordolano |  | Depleted Field | STOGIT | FID | 2016 | 379 | Total w.g. of Bordolano (first + second phases) is 1136 M Nmc
Storage Facility |  | UGS-F-1045 | Bordolano Second phase | Bordolano |  | Depleted Field | STOGIT S.p.A. | FID | 2019 | 757 | the entire w.g. volume of Bordolano (first + second phases) is 1.136 M Nmc
Storage Facility |  | UGS-F-260 | System Enhancements - Stogit - on-shore gas fields | Stogit Enhancements and New Developments |  | Depleted Field | STOGIT | FID | 2026 | 2120
Storage Facility |  | UGS-N-235 | Nuovi Sviluppi Edison Stoccaggio | Nuovi Sviluppi Edison Stoccaggio |  | Depleted Field | Edison Stoccaggio S.p.A | Advanced Non-FID | 2017 | 0 | in 10^6 Sm^3
Storage Facility |  | UGS-N-233 | Depomures | Depomures |  | Depleted Field | Engie Romania SA | Advanced Non-FID | 2019 | 300 | The capacity increment is planned to be implemented in 2 phases: 100 mcm in 2019 and 200 mcm with COD in 2022
Storage Facility |  | UGS-N-237 | Palazzo Moroni | Palazzo Moroni |  | Depleted Field | Edison Stoccaggio S.p.A | Advanced Non-FID | 2019 | 50 | in 10^6 Sm^3
Storage Facility |  | UGS-N-374 | Enhancement of Incukalns UGS | Incukalns Underground Gas Storage |  | Aquifer | JSC "Latvijas Gaze" | Advanced Non-FID | 2019 | 0 | Depending on market needs the increment can reach 900 mcm
Storage Facility |  | UGS-N-203 | Preesall Gas Storage | Preesall |  | Salt Cavern | Halite Energy Group Ltd | Less-Advanced Non-FID | 2018 | 600
Storage Facility |  | UGS-N-034 | Syderiai | Syderiai underground gas storage |  | Aquifer | JSC Lietuvos energija AB | Less-Advanced Non-FID | 2019 | 500
Storage Facility |  | UGS-N-294 | Islandmagee Gas Storage Facility | Islandmagee Storage Facility |  | Salt Cavern | Islandmagee Storage Limited | Less-Advanced Non-FID | 2021 | 420
Storage Facility |  | UGS-N-138 | UGS Chiren Expansion | UGS Chiren |  | Aquifer | Bulgartransgaz EAD | Less-Advanced Non-FID | 2022 | 450 | 450
Storage Facility |  | UGS-N-371 | Sarmasel undeground gas storage in Romania | UGS SARMASEL |  | Depleted Field | Societatea Naţională de Gaze Naturale ROMGAZ S.A. | Less-Advanced Non-FID | 2022 | 650
Storage Facility |  | UGS-N-385 | South Kavala Underground Gas Storage facility | South Kavala |  | Aquifer | Hellenic Republic Asset anagement Fund | Less-Advanced Non-FID | 2022 | 360
Storage Facility |  | UGS-N-659 | RENC-8 Carriço UGS cavern | Armazenamento Subterrâneo do Carriço |  | Salt Cavern | REN - Armazenagem, S.A. | Less-Advanced Non-FID | 2022 | 58 | Equivalent to 690 GWh
Storage Facility |  | UGS-N-127 | Underground Gas Storage in salt leached caverns in the Bages area (ES) | Pinasses |  | Salt Cavern | Gas Natural | Less-Advanced Non-FID | 2023 | 240 | It will be the first storage in the area which counts with important transport, interconnection and regas facilities. The first phase of the project (8 cavities) will achieve the mentioned capacity. However it could be increased in the future.
Storage Facility |  | UGS-N-366 | New undergound gas storage in Romania | UGS Moldova |  | Depleted Field | Societatea Naţională de Gaze Naturale ROMGAZ S.A. | Less-Advanced Non-FID | 2023 | 200
Storage Facility |  | UGS-N-914 | UGS Damaslawek | UGS Damasławek |  | Salt Cavern | GAZ-SYSTEM S.A. | Less-Advanced Non-FID | 2026 | 450
Storage Facility |  | UGS-N-141 | Construction of new gas storage facility on the territory of Bulgaria | Not defined yet |  | Aquifer | Bulgartransgaz EAD | Less-Advanced Non-FID | Unknown | 0

## Time Schedule
| TYNDP Annex A |  |  |  | Time Schedule - Page 6
Time Schedule
Type |  | Code | Name | Host Country |  | Promoter | Status | FEED Starts | FEED Ends | Market Test Ends | Permitting Phase Starts | Permitting Phase Ends | Supply Contracts Ends | FID Ends | Construction Starts | Construction Ends | Commissioning Starts | Commissioning Ends
Storage Facility |  | UGS-F-259 | Bordolano first phase | Italy |  | STOGIT | FID | [9 empty] | 2016 | 2016
Pipeline including CS |  | TRA-F-029 | Romania-Bulgaria Interconnection (EEPR-2009-INTg-RO-BG) | Romania |  | SNTGN Transgaz SA | FID | [8 empty] | 2016-01-01 | 2016 | 2016
Pipeline including CS |  | TRA-F-1047 | Exit Capacity Budince | Slovakia |  | eustream, a.s. | FID | [9 empty] | 2016 | 2016
Pipeline including CS |  | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | Croatia |  | Plinacro Ltd | FID |  |  | 2016-08-01 | 2015-06-16 | 2017-12-01 | 2017-01-01 | 2015-04-01 | 2017-01-01 | 2017-12-01 | 2017 | 2017
Pipeline including CS |  | TRA-F-241 | MONACO section phase I (Burghausen-Finsing) | Germany |  | bayernets GmbH | FID | 2009-08-03 | 2009-12-08 | 2011-10-17 | 2013-11-15 | 2016-02-15 |  | 2015-04-02 | 2016-10-01 | 2017-12-31 | 2017 | 2017
Pipeline including CS |  | TRA-F-291 | NOWAL - Nord West Anbindungsleitung | Germany |  | GASCADE Gastransport GmbH | FID |  |  |  | 2016-01-01 | 2016-08-01 |  | 2016-03-01 | 2017-01-01 | 2018-01-01 | 2017 | 2025
Pipeline including CS |  | TRA-F-768 | Extension Receiving Terminal Greifswald | Germany |  | NEL Gastransport, Fluxys Deutschland, Gasunie Deutschland | FID |  |  |  | 2016-01-01 | 2016-12-31 |  | 2016-03-01 | 2017-01-01 | 2018-01-01 | 2017 | 2019
LNG Terminal |  | LNG-F-147 | Revythoussa (2nd upgrade) | Greece |  | DESFA S.A. | FID | [8 empty] | 2017-12-31 | 2017 | 2017
Pipeline including CS |  | TRA-F-137 | Interconnection Bulgaria - Serbia | Bulgaria |  | Ministry of Energy | FID |  |  | 2017-05-01 |  | 2016-08-01 | 2017-04-01 | 2012-12-03 | 2017-05-01 | 2018-12-01 | 2018 | 2018
Pipeline including CS |  | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | Bulgaria |  | ICGB a.d. | FID | 2008-08-01 | 2016-03-31 | 2016-09-08 | 2010-08-01 | 2016-11-30 | 2016-12-31 | 2015-12-10 | 2017-03-01 | 2018-12-31 | 2018 | 2021
Pipeline including CS |  | TRA-F-43 | Val de Saône project | France |  | GRTgaz | FID | 2013-07-31 | 2014-07-31 | 2014-03-21 | 2014-10-01 | 2016-06-30 | 2016-08-31 | 2015-09-07 | 2016-06-30 | 2018-11-01 | 2018 | 2018
Pipeline including CS |  | TRA-F-45 | Reverse capacity from CH to FR at Oltingue | France |  | GRTgaz | FID | 2015-09-01 | 2016-12-31 | 2012-06-05 |  |  | 2017-01-01 | 2015-07-24 | 2017-03-31 | 2017-12-31 | 2018 | 2018
Pipeline including CS |  | TRA-F-331 | Gascogne Midi | France |  | TIGF - GRTgaz | FID | 2015-03-15 | 2016-06-15 |  | 2016-02-15 | 2017-07-16 |  | 2014-09-15 | 2017-06-15 | 2018-07-15 | 2018 | 2018
Pipeline including CS |  | TRA-F-391 | Gascogne-Midi : adaptation of stations in Cruzy and St Martin | France |  | GRTgaz | FID | 2015-04-01 | 2016-01-31 | 2014-03-01 |  |  | 2017-06-30 | 2015-12-22 | 2015-12-01 | 2017-11-30 | 2018 | 2018
Pipeline including CS |  | TRA-F-208 | Reverse Flow TENP Germany | Germany |  | Fluxys TENP GmbH & Open Grid Europe GmbH | FID | 2016-07-01 | 2016-12-31 | 2014-05-30 | 2016-12-01 | 2018-01-01 | 2018-04-01 | 2015-01-01 | 2017-06-01 | 2018-06-01 | 2018 | 2025
Pipeline including CS |  | TRA-F-337 | CS Rothenstadt | Germany |  | GRTgaz Deutschland GmbH | FID | [9 empty] | 2018 | 2018
Pipeline including CS |  | TRA-F-343 | Pipeline project "Schwandorf-Finsing" | Germany |  | Open Grid Europe GmbH | FID | [6 empty] | 2016-01-15 | 2017-03-01 | 2018-12-31 | 2018 | 2018
Pipeline including CS |  | TRA-F-344 | Compressor station "Herbstein" | Germany |  | Open Grid Europe GmbH | FID | [6 empty] | 2016-01-15 | 2016-03-01 | 2018-12-31 | 2018 | 2018
Pipeline including CS |  | TRA-F-345 | Compressor station "Werne" | Germany |  | Open Grid Europe GmbH | FID | [6 empty] | 2016-01-15 | 2016-03-29 | 2018-12-31 | 2018 | 2018
Pipeline including CS |  | TRA-F-753 | West to East operation of the IP Waidhaus | Germany |  | GRTgaz Deutschland GmbH | FID | [9 empty] | 2018 | 2018
Pipeline including CS |  | TRA-F-214 | Support to the North West market and bidirectional cross-border flows | Italy |  | Snam Rete Gas S.p.A. | FID | [9 empty] | 2018 | 2018
Pipeline including CS |  | TRA-F-230 | Reverse Flow Transitgas Switzerland | Switzerland |  | FluxSwiss | FID | [9 empty] | 2018 | 2018
Pipeline including CS |  | TRA-F-221 | TANAP - Trans Anatolian Natural Gas Pipeline Project | Turkey |  | SOCAR (The State Oil Company of the Azerbaijan Republic) | FID | 2012-09-01 | 2014-05-01 | 2013-12-17 | 2014-04-01 | 2014-07-24 | 2019-06-30 | 2013-12-17 | 2014-06-26 | 2019-06-30 | 2018 | 2019
LNG Terminal |  | LNG-F-229 | Zeebrugge LNG Terminal - 5th Tank & 2nd Jetty | Belgium |  | Fluxys LNG | FID | [9 empty] | 2019 | 2019
Pipeline including CS |  | TRA-F-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Rogatec) | Croatia |  | Plinacro Ltd | FID |  |  | 2015-06-01 | 2015-10-14 | 2019-01-01 |  | 2016-01-01 | 2017-01-01 | 2019-01-01 | 2019 | 2019
Pipeline including CS |  | TRA-F-937 | Nord Stream 2 | Germany |  | Nord Stream 2 AG | FID |  |  |  | 2013-04-08 | 2018-01-31 | 2016-12-31 | 2015-09-04 | 2018-02-01 | 2019-10-31 | 2019 | 2019
Pipeline including CS |  | TRA-F-051 | Trans Adriatic Pipeline | Greece |  | Trans Adriatic Pipeline AG | FID | 2008-01-01 | 2013-03-25 | 2014-11-01 | 2011-09-01 | 2017-03-01 | 2013-09-19 | 2013-12-17 | 2016-05-16 | 2019-12-01 | 2019 | 2019
Storage Facility |  | UGS-F-1045 | Bordolano Second phase | Italy |  | STOGIT S.p.A. | FID | [9 empty] | 2019 | 2019
LNG Terminal |  | LNG-F-183 | Tenerife LNG Terminal | Spain |  | Gascan | FID | [9 empty] | 2020 | 2020
LNG Terminal |  | LNG-F-163 | Gran Canaria LNG Terminal | Spain |  | Gascan | FID | [9 empty] | 2021 | 2021
Pipeline including CS |  | TRA-F-1028 | Albania - Kosovo Gas Pipeline | Albania |  | Min. of Energy and Industry of AL & Min. of Economic Development of KO | FID | [9 empty] | 2022 | 2022
Storage Facility |  | UGS-F-260 | System Enhancements - Stogit - on-shore gas fields | Italy |  | STOGIT | FID |  |  |  |  | 2025-01-01 |  |  |  |  | 2026 | 2026
Pipeline including CS |  | TRA-F-017 | System Enhancements - Eustream | Slovakia |  | eustream, a.s. | FID | [9 empty] | 2026 | 2026
LNG Terminal |  | LNG-F-178 | Musel LNG terminal | Spain |  | Enagás Transporte, S.A.U. | FID | [9 empty] | 2026 | 2026
Pipeline including CS |  | TRA-F-025 | Industrial Emissions Directive (IPPC) - FID | United Kingdom |  | National Grid Gas plc | FID | [9 empty] | Unknown | Unknown
Pipeline including CS |  | TRA-N-814 | Upgrade IP Deutschneudorf and Lasow | Germany |  | ONTRAS Gastransport GmbH | Advanced Non-FID | 2016-03-31 |  | 2015-10-16 | [6 empty] | 2016 | 2019
Storage Facility |  | UGS-N-235 | Nuovi Sviluppi Edison Stoccaggio | Italy |  | Edison Stoccaggio S.p.A | Advanced Non-FID | 2016-01-01 | 2017-01-01 |  | 2016-01-01 | 2017-01-01 |  | 2016-12-01 | 2016-01-01 | 2017-01-01 | 2017 | 2017
LNG Terminal |  | LNG-N-082 | LNG terminal Krk | Croatia |  | LNG Hrvatska d.o.o. za poslovanje ukapljenim prirodnim plinom | Advanced Non-FID | 2015-06-19 | 2015-12-16 | 2015-10-30 | [6 empty] | 2018 | 2018
Pipeline including CS |  | TRA-N-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | Croatia |  | Plinacro Ltd | Advanced Non-FID |  |  | 2016-08-01 | 2009-07-02 | 2018-01-01 |  | 2017-01-01 | 2017-01-01 | 2018-05-01 | 2018 | 2018
Pipeline including CS |  | TRA-N-429 | Adaptation L- gas - H-gas | France |  | GRTgaz, GRDF and Storengy | Advanced Non-FID | 2015-08-01 | 2016-10-31 | 2017-03-31 | 2016-11-01 | 2018-02-28 |  | 2016-10-31 | 2017-04-01 | 2026-12-31 | 2018 | 2018
LNG Terminal |  | LNG-N-062 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | Greece |  | Gastrade S.A. | Advanced Non-FID | 2016-05-15 | 2016-12-31 | 2017-03-01 | 2010-12-01 | 2015-01-20 |  | 2016-12-31 | 2017-04-01 | 2018-06-30 | 2018 | 2018
Pipeline including CS |  | TRA-N-063 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Greece |  | Gastrade S.A. | Advanced Non-FID | 2016-05-15 | 2016-12-31 | 2017-03-01 | 2010-12-01 | 2015-01-20 |  | 2016-12-31 | 2017-04-01 | 2018-06-30 | 2018 | 2018
Pipeline including CS |  | TRA-N-361 | GCA 2015/08: Entry/Exit Murfeld | Austria |  | GAS CONNECT AUSTRIA GmbH | Advanced Non-FID |  |  |  | 2015-10-27 | 2017-07-01 |  |  |  | 2019-11-01 | 2019 | 2019
Pipeline including CS |  | TRA-N-066 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Croatia |  | Plinacro Ltd | Advanced Non-FID |  |  | 2016-08-01 | 2011-01-01 | 2019-01-01 |  | 2017-12-01 | 2018-01-01 | 2019-01-01 | 2019 | 2019
Pipeline including CS |  | TRA-N-136 | Poland-Czech Republic Interconnection (CZ) | Czechia |  | NET4GAS, s.r.o. | Advanced Non-FID | 2014-06-01 | 2017-02-01 | 2012-05-17 | 2010-09-01 | 2017-11-01 |  |  |  |  | 2019 | 2019
Pipeline including CS |  | TRA-N-752 | Capacity4Gas (C4G) – DE/CZ | Czechia |  | NET4GAS, s.r.o. | Advanced Non-FID | 2015-10-01 | 2018-06-01 | 2016-02-26 | [6 empty] | 2019 | 2020
Pipeline including CS |  | TRA-N-918 | Capacity4Gas (C4G) – CZ/SK | Czechia |  | NET4GAS, s.r.o. | Advanced Non-FID | 2015-12-01 | 2018-06-01 | 2016-02-26 | [6 empty] | 2019 | 2019
Pipeline including CS |  | TRA-N-895 | Balticconnector | Estonia |  | Elering AS | Advanced Non-FID | 2016-01-01 | 2016-02-29 | 2016-03-09 | 2012-12-02 | 2018-01-01 | 2016-11-30 | 2016-09-30 | 2016-11-30 | 2019-12-31 | 2019 | 2019
Pipeline including CS |  | TRA-N-915 | Enhancement of Estonia-Latvia interconnection | Estonia |  | Elering AS | Advanced Non-FID | 2015-05-01 | 2016-05-31 | 2016-03-09 | 2015-09-01 | 2016-09-30 | 2018-03-01 | 2016-09-30 | 2017-04-01 | 2019-12-31 | 2019 | 2019
Pipeline including CS |  | TRA-N-928 | Balticconnector Finnish part | Finland |  | Baltic Connector Oy | Advanced Non-FID | 2016-01-01 | 2016-02-29 | 2016-03-09 | 2012-12-02 | 2018-01-01 |  | 2016-09-30 | 2016-11-30 | 2019-12-27 | 2019 | 2019
Pipeline including CS |  | TRA-N-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | Germany |  | GASCADE Gastransport GmbH | Advanced Non-FID | 2016-01-01 | 2021-01-01 |  | 2016-05-02 | 2018-06-01 |  |  | 2020-12-01 |  | 2019 | 2021
Pipeline including CS |  | TRA-N-012 | GALSI Pipeline Project | Italy |  | Galsi S.p.A. | Advanced Non-FID | 2007-01-01 | 2010-12-31 | 2010-10-29 | 2008-07-31 | 2016-05-31 | 2016-05-31 | 2016-05-31 | 2016-06-01 | 2019-06-30 | 2019 | 2019
Storage Facility |  | UGS-N-237 | Palazzo Moroni | Italy |  | Edison Stoccaggio S.p.A | Advanced Non-FID | 2013-01-01 | 2017-01-01 | 2019-01-01 | 2009-01-01 | 2017-01-01 |  | 2017-01-01 | 2017-01-01 | 2019-01-01 | 2019 | 2019
Storage Facility |  | UGS-N-374 | Enhancement of Incukalns UGS | Latvia |  | JSC "Latvijas Gaze" | Advanced Non-FID |  |  |  | 2014-05-01 |  |  |  | 2014-03-01 |  | 2019 | 2021
LNG Terminal |  | LNG-N-912 | Skulte LNG | Latvia |  | AS Skulte LNG Terminal | Advanced Non-FID | 2015-05-10 | 2015-06-09 | 2016-05-05 | 2016-04-04 | 2016-12-15 | 2018-09-03 | 2017-01-09 | 2017-05-03 | 2018-12-11 | 2019 | 2019
Pipeline including CS |  | TRA-N-341 | Gas Interconnection Poland-Lithuania (GIPL) (Lithuania's section) | Lithuania |  | AB Amber Grid | Advanced Non-FID | 2015-05-01 | 2016-09-15 | 2012-09-21 | 2016-07-01 | 2016-09-15 | 2017-09-01 | 2016-10-01 | 2016-10-01 | 2019-06-30 | 2019 | 2019
Pipeline including CS |  | TRA-N-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | Poland |  | GAZ-SYSTEM S.A. | Advanced Non-FID | 2014-01-01 | 2017-01-01 |  |  | 2017-01-01 |  | 2017-01-01 | 2017-01-01 | 2019-01-01 | 2019 | 2019
Pipeline including CS |  | TRA-N-247 | North - South Gas Corridor in Western Poland | Poland |  | GAZ-SYSTEM S.A. | Advanced Non-FID | 2013-01-01 | 2017-01-01 |  |  | 2017-01-01 |  |  | 2017-01-01 | 2019-01-01 | 2019 | 2019
Pipeline including CS |  | TRA-N-273 | Poland - Czech Republic interconnection (PL section) | Poland |  | GAZ-SYSTEM S.A. | Advanced Non-FID | 2012-01-01 | 2017-01-01 |  |  | 2017-01-01 |  | 2017-01-01 | 2017-01-01 | 2019-01-01 | 2019 | 2019
Pipeline including CS |  | TRA-N-275 | Poland - Slovakia interconnection (PL section) | Poland |  | GAZ-SYSTEM S.A. | Advanced Non-FID | 2014-01-01 | 2017-01-01 |  |  | 2017-01-01 |  | 2017-01-01 | 2017-01-01 | 2019-12-31 | 2019 | 2019
Storage Facility |  | UGS-N-233 | Depomures | Romania |  | Engie Romania SA | Advanced Non-FID | 2011-06-01 | 2012-06-01 | 2016-06-01 | 2012-06-01 | 2016-06-01 |  | 2016-11-01 | 2015-07-10 | 2022-01-30 | 2019 | 2022
Pipeline including CS |  | TRA-N-190 | Poland - Slovakia interconnection | Slovakia |  | eustream, a.s. | Advanced Non-FID | 2015-10-01 | 2018-04-30 | 2016-06-01 | 2015-08-01 | 2017-09-30 |  |  |  | 2019-12-31 | 2019 | 2019
Pipeline including CS |  | TRA-N-902 | Capacity increase at IP Lanžhot entry | Slovakia |  | eustream, a.s. | Advanced Non-FID | 2015-09-01 | 2017-08-31 | 2017-06-01 | [6 empty] | 2019 | 2019
Pipeline including CS |  | TRA-N-021 | Bidirectional Austrian-Czech Interconnector (BACI, formerly LBL project) | Austria |  | GAS CONNECT AUSTRIA GmbH | Advanced Non-FID |  |  | 2016-06-11 | 2015-10-27 |  |  |  |  | 2020-10-01 | 2020 | 2020
Pipeline including CS |  | TRA-N-423 | GCA Mosonmagyaróvár | Austria |  | GAS CONNECT AUSTRIA GmbH | Advanced Non-FID |  |  |  | 2015-10-27 | 2017-07-01 |  |  |  | 2020-10-01 | 2020 | 2020
Pipeline including CS |  | TRA-N-801 | Břeclav-Baumgarten Interconnection (BBI) AT | Austria |  | GAS CONNECT AUSTRIA GmbH | Advanced Non-FID |  |  | 2016-04-01 | 2016-03-22 |  |  |  |  | 2020-10-01 | 2020 | 2020
Pipeline including CS |  | TRA-N-500 | L/H Conversion | Belgium |  | Fluxys Belgium | Advanced Non-FID | 2015-09-01 | [8 empty] | 2020 | 2020
Pipeline including CS |  | TRA-N-075 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Croatia |  | Plinacro Ltd | Advanced Non-FID |  |  | 2016-08-01 | 2009-07-02 | 2020-01-01 |  | 2017-01-01 | 2017-01-01 | 2020-01-01 | 2020 | 2020
Pipeline including CS |  | TRA-N-133 | Bidirectional Austrian Czech Interconnection (BACI) | Czechia |  | NET4GAS, s.r.o. | Advanced Non-FID | 2012-03-01 | 2018-06-01 | 2015-06-11 | [6 empty] | 2020 | 2020
Pipeline including CS |  | TRA-N-919 | Capacity4Gas (C4G) – CZ/AT | Czechia |  | NET4GAS, s.r.o. | Advanced Non-FID | 2015-12-01 | 2018-06-01 | 2016-02-26 | [6 empty] | 2020 | 2020
LNG Terminal |  | LNG-N-079 | Paldiski LNG Terminal | Estonia |  | Balti Gaas plc | Advanced Non-FID | 2013-04-01 | 2014-04-24 | 2013-10-31 | 2008-01-14 | 2016-04-29 |  | 2016-12-23 | 2017-04-24 | 2020-07-30 | 2020 | 2020
Pipeline including CS |  | TRA-N-807 | Expansion NEL | Germany |  | Gasunie Deutschland, NEL Gastransport, Fluxys Deutschland | Advanced Non-FID | 2016-03-15 |  |  | 2016-03-15 | [5 empty] | 2020 | 2020
Pipeline including CS |  | TRA-N-010 | Poseidon Pipeline | Greece |  | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced Non-FID | 2010-04-01 | 2013-04-01 | 2017-06-01 | 2006-11-01 | 2016-12-01 | 2017-12-01 | 2017-06-01 | 2017-12-01 | 2020-07-01 | 2020 | 2020
Pipeline including CS |  | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | Slovenia |  | Plinovodi d.o.o. | Advanced Non-FID | 2018-01-01 | 2019-11-01 |  | 2015-12-01 | 2019-10-01 |  | 2018-01-01 | 2019-01-01 | 2020-12-01 | 2020 | 2020
LNG Terminal |  | LNG-N-032 | Project GO4LNG LNG terminal Gothenburg | Sweden |  | Swedegas AB | Advanced Non-FID | 2016-04-01 | 2016-10-01 | 2013-01-01 | 2013-10-01 | 2014-05-01 | 2016-12-31 | 2017-01-01 | 2017-01-01 | 2020-01-01 | 2020 | 2020
Pipeline including CS |  | TRA-N-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | Croatia |  | Plinacro Ltd | Advanced Non-FID |  |  |  | 2014-08-25 | 2021-01-01 |  | 2019-01-01 | 2020-01-01 | 2021-01-01 | 2021 | 2021
Pipeline including CS |  | TRA-N-808 | Transport of gas volumes to the Netherlands | Germany |  | Gasunie Deutschland Technical Services GmbH | Advanced Non-FID |  |  | 2015-10-16 | 2016-03-15 | [5 empty] | 2021 | 2021
LNG Terminal |  | LNG-N-198 | Porto Empedocle LNG | Italy |  | Nuove Energie S.r.l. | Advanced Non-FID | 2006-03-01 | 2006-09-28 | 2018-01-01 | 2009-01-01 | 2009-10-22 |  | 2017-10-01 | 2017-11-01 | 2021-12-31 | 2021 | 2021
Pipeline including CS |  | TRA-N-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | Portugal |  | REN-Gasodutos, S.A. | Advanced Non-FID | 2015-07-22 | 2018-05-31 | 2017-12-29 | 2016-02-12 | 2018-12-31 | 2019-12-31 | 2018-05-31 | 2020-01-01 | 2021-11-30 | 2021 | 2021
Pipeline including CS |  | TRA-N-320 | Carregado Compressor Station | Portugal |  | REN-Gasodutos, S.A. | Advanced Non-FID | 2010-08-01 | 2010-11-01 |  | 2011-02-01 |  |  | 2018-05-01 | 2019-01-01 | 2021-12-31 | 2021 | 2021
Pipeline including CS |  | TRA-N-161 | South Transit East Pyrenees (STEP) - ENAGAS | Spain |  | Enagás Transporte, S.A.U. | Advanced Non-FID | 2016-01-01 | 2016-12-31 | 2017-03-01 | 2016-07-01 | 2019-12-01 |  | 2017-07-01 | 2020-04-01 | 2021-12-01 | 2021 | 2021
Pipeline including CS |  | TRA-N-068 | Ionian Adriatic Pipeline | Croatia |  | Plinacro Ltd | Advanced Non-FID |  |  |  | 2009-07-21 | 2023-01-01 |  | 2019-01-01 | 2020-01-01 | 2023-01-01 | 2022 | 2023
Pipeline including CS |  | TRA-N-252 | South Transit East Pyrenees (STEP) - TIGF | France |  | TIGF | Advanced Non-FID | 2016-01-20 | 2019-06-30 |  | 2019-02-17 | 2020-12-31 |  | 2019-04-15 | 2020-12-01 | 2022-10-31 | 2022 | 2022
Pipeline including CS |  | TRA-N-974 | LARINO - RECANATI Adriatic coast backbone | Italy |  | Società Gasdotti Italia | Advanced Non-FID | 2015-01-01 | 2015-01-31 | 2012-06-30 | 2015-01-01 | 2019-12-31 | 2019-06-30 | 2016-12-31 | 2018-06-01 | 2022-12-31 | 2022 | 2022
Pipeline including CS |  | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | Hungary |  | Magyar Gáz Tranzit Zrt. | Less-Advanced Non-FID | [9 empty] | 2017 | 2017
Pipeline including CS |  | TRA-N-636 | Development of Transmission Capacity at Slovak-Hungarian interconnector | Hungary |  | Magyar Gáz Tranzit Zrt. | Less-Advanced Non-FID | [9 empty] | 2017 | 2017
Pipeline including CS |  | TRA-N-645 | HU-UA Interconnector (Ukrainian section) | Ukraine |  | PJSC Ukrtransgaz | Less-Advanced Non-FID | [9 empty] | 2017 | 2017
Pipeline including CS |  | TRA-N-660 | Gas to the West | United Kingdom |  | West Transmission Limited | Less-Advanced Non-FID | [9 empty] | 2017 | 2017
Pipeline including CS |  | TRA-N-954 | TAG Reverse Flow | Austria |  | Trans Austria Gasleitung GmbH | Less-Advanced Non-FID | [9 empty] | 2018 | 2018
Pipeline including CS |  | TRA-N-379 | ​A project for the construction of a gas pipeline BG-RO | Bulgaria |  | Bulgartransgaz EAD | Less-Advanced Non-FID | [9 empty] | 2018 | 2018
Pipeline including CS |  | TRA-N-545 | Infrastructure gas pipeline Skopje - Tetovo - Gostivar - Albanian border | former Yugoslav Republic of Macedonia |  | GA-MA joint stock company Skopje | Less-Advanced Non-FID | 2017-05-01 | 2017-07-03 | 2017-08-03 | 2017-09-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-02 | 2018-12-03 | 2018 | 2018
Pipeline including CS |  | TRA-N-357 | NTS developments in North-East Romania | Romania |  | SNTGN Transgaz SA | Less-Advanced Non-FID | [9 empty] | 2018 | 2018
Storage Facility |  | UGS-N-203 | Preesall Gas Storage | United Kingdom |  | Halite Energy Group Ltd | Less-Advanced Non-FID | [9 empty] | 2018 | 2018
LNG Terminal |  | LNG-N-962 | Tallinn LNG | Estonia |  | Vopak E.O.S. AS / Vopak LNG Holdings B.V/ Port of Tallinn AS | Less-Advanced Non-FID | [9 empty] | 2019 | 2019
Pipeline including CS |  | TRA-N-582 | Macedonian part of Tesla project | former Yugoslav Republic of Macedonia |  | GA-MA joint stock company Skopje | Less-Advanced Non-FID | 2017-08-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-06-01 | 2018-07-02 | 2018-08-02 | 2018-09-03 | 2019-11-01 | 2019 | 2019
Pipeline including CS |  | TRA-N-340 | VDS Wertingen | Germany |  | bayernets GmbH | Less-Advanced Non-FID | 2018-02-01: 2016-04-29; 2018-06-01: 2017-04-03; 2018-09-03: 2017-04-28; 2019-11-01: 2019-12-31 | 2019 | 2019
Pipeline including CS |  | TRA-N-941 | Metering and Regulating station at Nea Messimvria | Greece |  | DESFA S.A. | Less-Advanced Non-FID | 2017-08-01: 2016-05-04; 2017-12-01: 2018-03-31 | 2019 | 2019
Storage Facility |  | UGS-N-034 | Syderiai | Lithuania |  | JSC Lietuvos energija AB | Less-Advanced Non-FID | [9 empty] | 2019 | 2019
Pipeline including CS |  | TRA-N-139 | Interconnection of the NTS with the DTS and reverse flow at Isaccea | Romania |  | SNTGN Transgaz SA | Less-Advanced Non-FID | [9 empty] | 2019 | 2019
Pipeline including CS |  | TRA-N-964 | New NTS developments for taking over gas from the Black Sea shore | Romania |  | SNTGN Transgaz SA | Less-Advanced Non-FID | 2018-01-01: 2016-12-05 | 2019 | 2019
Pipeline including CS |  | TRA-N-365 | M6 Ajdovščina – Lucija | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | [9 empty] | 2019 | 2019
Pipeline including CS |  | TRA-N-561 | Poland-Ukraine Interconnector (Ukrainian section) | Ukraine |  | PJSC Ukrtransgaz | Less-Advanced Non-FID | 2016-05-01 | 2017-01-31 |  | 2017-01-01 | 2017-12-31 |  | 2017-04-30 | 2018-01-15 | 2019-11-30 | 2019 | 2019
LNG Terminal |  | LNG-N-328 | Eagle LNG and Pipeline | Albania |  | Burns Srl | Less-Advanced Non-FID | 2017-03-01 | 2018-03-01 | 2017-12-01 | 2017-06-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-03-01 | 2020-01-01 | 2020 | 2020
Pipeline including CS |  | TRA-N-140 | Interconnection Turkey-Bulgaria | Bulgaria |  | Bulgartransgaz EAD | Less-Advanced Non-FID | 2018-01-01: 2017-05-02; 2018-02-01: 2017-08-01; 2018-06-01: 2017-11-01; 2018-09-03: 2018-12-03; 2019-11-01: 2020-07-01 | 2020 | 2020
Pipeline including CS |  | TRA-N-298 | Rehabilitation, Modernization and Expansion of the NTS | Bulgaria |  | Bulgartransgaz EAD | Less-Advanced Non-FID | 2018-01-01: 2017-05-02; 2018-06-01: 2018-11-01; 2018-07-02: 2018-11-01; 2019-11-01: 2020-11-01 | 2020 | 2020
Pipeline including CS |  | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | Croatia |  | Plinacro Ltd | Less-Advanced Non-FID | 2018-02-01: 2017-01-01; 2018-06-01: 2020-01-01; 2018-08-02: 2018-01-01; 2018-09-03: 2018-01-01; 2019-11-01: 2020-01-01 | 2020 | 2020
LNG Terminal |  | LNG-N-225 | Montoir LNG Terminal Expansion | France |  | Elengy | Less-Advanced Non-FID | 2018-08-02: 2018-06-01; 2018-09-03: 2018-06-01; 2019-11-01: 2020-06-01 | 2020 | 2020
LNG Terminal |  | LNG-N-227 | Fos Cavaou LNG Terminal Expansion | France |  | Fosmax LNG | Less-Advanced Non-FID | 2018-06-01: 2018-06-01; 2018-08-02: 2018-06-01; 2018-09-03: 2018-06-01; 2019-11-01: 2022-06-01 | 2020 | 2022
Pipeline including CS |  | TRA-N-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Germany |  | Gastransport Nord GmbH | Less-Advanced Non-FID | [9 empty] | 2020 | 2027
Pipeline including CS |  | TRA-N-951 | Embedding CS Folmhusen in H-Gas | Germany |  | Gasunie Deutschland Transport Services GmbH | Less-Advanced Non-FID | [9 empty] | 2020 | 2020
Pipeline including CS |  | TRA-N-128 | Compressor Station Kipi | Greece |  | DESFA S.A. | Less-Advanced Non-FID | [9 empty] | 2020 | 2020
Pipeline including CS |  | TRA-N-330 | EastMed Pipeline | Greece |  | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Less-Advanced Non-FID | 2016-09-01 | 2017-06-01 | 2017-07-01 | 2016-06-01 | 2017-12-01 | 2017-12-01 | 2017-06-01 | 2018-01-01 | 2020-12-01 | 2020 | 2020
Pipeline including CS |  | TRA-N-631 | Greek part of Tesla project | Greece |  | DESFA S.A. | Less-Advanced Non-FID | [9 empty] | 2020 | 2020
Pipeline including CS |  | TRA-N-940 | Metering and Regulating station at Komotini | Greece |  | DESFA S.A. | Less-Advanced Non-FID | [9 empty] | 2020 | 2020
Pipeline including CS |  | TRA-N-957 | Metering Station at Komotini to IGB | Greece |  | DESFA S.A. | Less-Advanced Non-FID | [9 empty] | 2020 | 2020
Pipeline including CS |  | TRA-N-967 | Nea-Messimvria to FYROM pipeline | Greece |  | DESFA S.A. | Less-Advanced Non-FID | [9 empty] | 2020 | 2020
Pipeline including CS |  | TRA-N-1090 | Metering and Regulating Station at Alexandroupoli | Greece |  | DESFA S.A. | Less-Advanced Non-FID | [9 empty] | 2020 | 2020
Pipeline including CS |  | TRA-N-286 | Romanian-Hungarian reverse flow Hungarian section 1st stage | Hungary |  | FGSZ Ltd. | Less-Advanced Non-FID | 2018-07-01 | 2018-10-03 | 2016-12-31 | 2018-07-01 |  | 2017-06-01 | 2017-05-31 | 2018-10-01 |  | 2020 | 2020
Pipeline including CS |  | TRA-N-325 | Slovenian-Hungarian interconnector | Hungary |  | FGSZ Ltd. | Less-Advanced Non-FID | 2017-06-01 | 2019-11-30 |  | 2016-11-01 | 2017-10-31 |  | 2018-02-28 | 2019-09-01 | 2020-12-31 | 2020 | 2020
Pipeline including CS |  | TRA-N-585 | Hungarian section of Tesla project | Hungary |  | FGSZ Ltd. | Less-Advanced Non-FID | 2016-10-01 | 2018-03-31 | 2016-10-31 | 2016-10-01 | 2018-03-31 | 2018-08-01 | 2018-03-01 | 2018-09-01 | 2020-05-31 | 2020 | 2020
Pipeline including CS |  | TRA-N-586 | HU-UA reverse flow | Hungary |  | FGSZ Ltd. | Less-Advanced Non-FID | [9 empty] | 2020 | 2020
Pipeline including CS |  | TRA-N-382 | Enhancement of Latvia-Lithuania interconnection (Latvian part) | Latvia |  | JSC "Latvijas Gaze" | Less-Advanced Non-FID | [9 empty] | 2020 | 2020
Pipeline including CS |  | TRA-N-342 | Enhancement of Latvia-Lithuania interconnection (Lithuania's part) | Lithuania |  | AB Amber Grid | Less-Advanced Non-FID | 2018-01-01 | 2018-12-31 | 2017-06-01 | 2019-01-01 | 2020-01-01 | 2020-01-01 | 2019-12-31 | 2020-01-01 | 2020-12-31 | 2020 | 2020
LNG Terminal |  | LNG-N-050 | Gate terminal phase 3 | Netherlands |  | Gate | Less-Advanced Non-FID | [9 empty] | 2020 | 2020
Pipeline including CS |  | TRA-N-191 | Blending | Netherlands |  | Gasunie Transport Services B.V. | Less-Advanced Non-FID | [9 empty] | 2020 | 2020
Pipeline including CS |  | TRA-N-192 | Entry capacity expansion GATE terminal | Netherlands |  | Gasunie Transport Services B.V. | Less-Advanced Non-FID | [9 empty] | 2020 | 2020
Pipeline including CS |  | TRA-N-882 | H-gas conversion of L-gas export border points | Netherlands |  | Gasunie Transport Services B.V. | Less-Advanced Non-FID | [9 empty] | 2020 | 2030
LNG Terminal |  | LNG-N-272 | Upgrade of LNG terminal in Świnoujście | Poland |  | GAZ-SYSTEM S.A. | Less-Advanced Non-FID | [9 empty] | 2020 | 2020
Pipeline including CS |  | TRA-N-621 | Poland - Ukraine Gas interconnection (PL section) | Poland |  | GAZ-SYSTEM S.A. | Less-Advanced Non-FID | [9 empty] | 2020 | 2020
LNG Terminal |  | LNG-N-947 | FSRU Polish Baltic Sea Coast | Poland |  | GAZ-SYSTEM S.A. | Less-Advanced Non-FID | [9 empty] | 2020 | 2020
Pipeline including CS |  | TRA-N-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT Corridor) | Romania |  | SNTGN Transgaz S.A. | Less-Advanced Non-FID | 2018-01-01: 2017-10-02 | 2020 | 2020
Pipeline including CS |  | TRA-N-362 | Development on the Romanian territory of the Southern Transmission Corridor | Romania |  | SNTGN Transgaz SA | Less-Advanced Non-FID | [9 empty] | 2020 | 2020
Pipeline including CS |  | TRA-N-094 | CS Kidričevo, 2nd phase of upgrade | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | 2017-08-01: 2018-01-01; 2017-12-01: 2019-11-01; 2018-08-02: 2018-01-01; 2018-09-03: 2019-01-01; 2019-11-01: 2020-12-01 | 2020 | 2020
Pipeline including CS |  | TRA-N-108 | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | [9 empty] | 2020 | 2020
Pipeline including CS |  | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | 2018-01-01 | 2019-11-01 | 2017-09-01 |  |  |  | 2018-01-01 | 2019-06-01 | 2020-12-01 | 2020 | 2020
Pipeline including CS |  | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak) | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | 2018-01-01 | 2019-11-01 | 2017-09-01 |  |  |  | 2018-01-01 | 2019-01-01 | 2020-12-01 | 2020 | 2020
LNG Terminal |  | LNG-N-296 | Mugardos LNG Terminal: 2nd Jetty | Spain |  | Reganosa | Less-Advanced Non-FID | 2018-03-01 | 2018-08-01 | 2018-08-01 | 2018-07-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2020-08-01 | 2020 | 2020
Pipeline including CS |  | TRA-N-950 | Guitiriz - Zamora pipeline | Spain |  | Reganosa | Less-Advanced Non-FID | 2017-06-01 | 2018-06-01 | 2017-06-01 | 2017-06-01 | 2019-01-01 | 2019-01-01 | 2019-01-01 | 2019-01-01 | 2020-01-01 | 2020 | 2020
Pipeline including CS |  | TRA-N-829 | PCI 5.1.1 Physical Reverse Flow at Moffat interconnection point (IE/UK) | United Kingdom |  | GNI (UK) Limited | Less-Advanced Non-FID | 2018-01-01 | 2018-12-31 | 2016-10-31 | 2018-01-01 | 2018-12-31 |  | 2018-12-31 | 2019-01-01 | 2019-12-31 | 2020 | 2020
Pipeline including CS |  | TRA-N-1064 | Moffat Physical Reverse Flow | United Kingdom |  | National Grid Gas plc | Less-Advanced Non-FID | [9 empty] | 2020 | 2020
Pipeline including CS |  | TRA-N-1138 | South Caucasus Pipeline Future Expansion - SCPFX | Azerbaijan |  | SOCAR Midstream Operations LLC | Less-Advanced Non-FID | 2018-01-01 | 2018-12-31 | 2018-09-30 | 2018-01-01 | 2018-12-31 | 2018-10-31 | 2018-12-31 | 2019-01-01 | 2021-12-31 | 2021 | 2021
Pipeline including CS |  | TRA-N-851 | Southern Interconnection pipeline BiH/CRO | Bosnia Herzegovina |  | BH-GAS d.o.o. | Less-Advanced Non-FID | 2018-04-01 | 2019-06-30 | 2017-12-31 | 2018-04-01 | 2019-06-30 | 2020-05-31 | 2018-03-31 | 2020-06-01 | 2021-09-30 | 2021 | 2021
Pipeline including CS |  | TRA-N-654 | Eastring - Bulgaria | Bulgaria |  | Bulgartransgaz EAD | Less-Advanced Non-FID | [9 empty] | 2021 | 2025
Pipeline including CS |  | TRA-N-965 | Interconnection Macedonia-Serbia | former Yugoslav Republic of Macedonia |  | MER JSC Skopje | Less-Advanced Non-FID | 2017-12-01: 2010-07-12 | 2021 | 2021
Pipeline including CS |  | TRA-N-976 | Interconnection Macedonia-Bulgaria | former Yugoslav Republic of Macedonia |  | MER JSC Skopje | Less-Advanced Non-FID | 2017-12-01: 2010-07-12 | 2021 | 2021
Pipeline including CS |  | TRA-N-980 | Interconnection Macedonia-Greece | former Yugoslav Republic of Macedonia |  | MER JSC Skopje | Less-Advanced Non-FID | 2017-12-01: 2010-07-12 | 2021 | 2021
Pipeline including CS |  | TRA-N-329 | ZEELINK | Germany |  | Open Grid Europe GmbH | Less-Advanced Non-FID | 2018-08-02: 2020-03-31; 2018-09-03: 2020-04-01; 2019-11-01: 2021-03-31 | 2021 | 2021
Pipeline including CS |  | TRA-N-656 | Eastring - Hungary | Hungary |  | FGSZ Ltd. | Less-Advanced Non-FID | [9 empty] | 2021 | 2025
Pipeline including CS |  | TRA-N-831 | Vecsés-Városföld gas transit pipeline | Hungary |  | Magyar Gáz Tranzit Zrt. | Less-Advanced Non-FID | [9 empty] | 2021 | 2021
LNG Terminal |  | LNG-N-217 | Onshore LNG terminal in the Northern Adriatic | Italy |  | Gas Natural Rigassificazione Italia | Less-Advanced Non-FID | 2018-08-02: 2017-12-01 | 2021 | 2021
Pipeline including CS |  | TRA-N-873 | Capacity expansion OSZ related to West Stream | Netherlands |  | Gasunie Transport Services B.V. | Less-Advanced Non-FID | [9 empty] | 2021 | 2023
Pipeline including CS |  | TRA-N-655 | Eastring - Romania | Romania |  | SNTGN Transgaz SA | Less-Advanced Non-FID | [9 empty] | 2021 | 2025
Pipeline including CS |  | TRA-N-628 | Eastring - Slovakia | Slovakia |  | Eastring B.V. | Less-Advanced Non-FID | [9 empty] | 2021 | 2025
Pipeline including CS |  | TRA-N-092 | CS Ajdovščina, 1st phase of upgrade | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | [9 empty] | 2021 | 2021
Pipeline including CS |  | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Spain |  | Enagás Transporte, S.A.U. | Less-Advanced Non-FID | 2017-01-01 | 2018-05-31 | 2018-03-01 | 2017-09-01 | 2019-12-31 |  | 2018-05-31 | 2020-04-01 | 2021-12-01 | 2021 | 2021
Pipeline including CS |  | TRA-N-027 | Physical reverse flow from NI to GB and IE via SNIP pipeline | United Kingdom |  | Premier Transmission Limited | Less-Advanced Non-FID | [9 empty] | 2021 | 2021
Storage Facility |  | UGS-N-294 | Islandmagee Gas Storage Facility | United Kingdom |  | Islandmagee Storage Limited | Less-Advanced Non-FID | [9 empty] | 2021 | 2026
LNG Terminal |  | LNG-N-742 | Zeebrugge LNG Terminal - 3rd Jetty | Belgium |  | Fluxys LNG | Less-Advanced Non-FID | [9 empty] | 2022 | 2022
Storage Facility |  | UGS-N-138 | UGS Chiren Expansion | Bulgaria |  | Bulgartransgaz EAD | Less-Advanced Non-FID | 2017-01-01 | 2017-12-31 | 2017-05-02 |  |  |  | 2019-01-01 | 2020-01-01 | 2021-12-01 | 2022 | 2022
Pipeline including CS |  | TRA-N-592 | Looping CS Valchi Dol - Line valve Novi Iskar | Bulgaria |  | Bulgartransgaz EAD | Less-Advanced Non-FID | 2018-01-01: 2017-05-02; 2019-11-01: 2022-06-01 | 2022 | 2022
Pipeline including CS |  | TRA-N-593 | Varna-Oryahovo gas pipeline | Bulgaria |  | Bulgartransgaz EAD | Less-Advanced Non-FID | 2018-01-01: 2017-05-02; 2019-11-01: 2022-06-01 | 2022 | 2022
Pipeline including CS |  | TRA-N-594 | Construction of a Looping CS Provadia – Rupcha village | Bulgaria |  | Bulgartransgaz EAD | Less-Advanced Non-FID | 2018-01-01: 2017-05-02; 2019-11-01: 2022-06-01 | 2022 | 2022
Pipeline including CS |  | TRA-N-135 | Connection to Oberkappel | Czechia |  | NET4GAS, s.r.o. | Less-Advanced Non-FID | [9 empty] | 2022 | 2022
Pipeline including CS |  | TRA-N-394 | Gassled - Danish upstream system | Denmark |  | Energinet.dk | Less-Advanced Non-FID | [9 empty] | 2022 | 2022
Pipeline including CS |  | TRA-N-428 | (Mirror) Baltic Pipe | Denmark |  | Energinet.dk | Less-Advanced Non-FID | [9 empty] | 2022 | 2022
Pipeline including CS |  | TRA-N-780 | Nybro-Interconnector PL-DK - reinforcement | Denmark |  | Energinet.dk | Less-Advanced Non-FID | [9 empty] | 2022 | 2022
Pipeline including CS |  | TRA-N-966 | Interconnection Macedonia-Kosovo | former Yugoslav Republic of Macedonia |  | MER JSC Skopje | Less-Advanced Non-FID | 2017-12-01: 2010-07-12 | 2022 | 2022
Pipeline including CS |  | TRA-N-998 | Interconnection Macedonia-Albania | former Yugoslav Republic of Macedonia |  | MER JSC Skopje | Less-Advanced Non-FID | 2017-12-01: 2010-07-12 | 2022 | 2022
Pipeline including CS |  | TRA-N-047 | Reverse capacity from France to Germany at Obergailbach | France |  | GRTgaz | Less-Advanced Non-FID | [9 empty] | 2022 | 2022
Pipeline including CS |  | TRA-N-258 | Developments for Montoir LNG terminal 2.5 bcm expansion | France |  | GRTgaz | Less-Advanced Non-FID | 2019-11-01: 2022-12-31 | 2022 | 2022
Pipeline including CS |  | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | France |  | GRTgaz | Less-Advanced Non-FID | [9 empty] | 2022 | 2022
Storage Facility |  | UGS-N-385 | South Kavala Underground Gas Storage facility | Greece |  | Hellenic Republic Asset anagement Fund | Less-Advanced Non-FID | [9 empty] | 2022 | 2022
Pipeline including CS |  | TRA-N-971 | Compressor station at Nea Messimvria | Greece |  | DESFA S.A. | Less-Advanced Non-FID | [9 empty] | 2022 | 2022
Pipeline including CS |  | TRA-N-1091 | Metering and Regulating station at Megalopoli | Greece |  | DESFA S.A. | Less-Advanced Non-FID | [9 empty] | 2022 | 2022
Pipeline including CS |  | TRA-N-018 | Városföld-Ercsi-Győr | Hungary |  | FGSZ Ltd. | Less-Advanced Non-FID | 2018-11-01 | 2020-04-30 | 2016-12-31 | 2017-05-01 | 2018-09-30 | 2017-04-30 | 2018-10-31 | 2021-03-01 | 2022-12-31 | 2022 | 2022
Pipeline including CS |  | TRA-N-061 | Ercsi-Szazhalombatta | Hungary |  | FGSZ Ltd. | Less-Advanced Non-FID | 2018-11-01 | 2020-04-30 | 2016-12-31 | 2017-05-01 | 2018-09-30 | 2017-04-30 | 2018-10-31 | 2021-03-01 | 2022-12-31 | 2022 | 2022
Pipeline including CS |  | TRA-N-123 | Városföld CS | Hungary |  | FGSZ Ltd. | Less-Advanced Non-FID | 2018-11-01 | 2020-04-30 | 2016-12-31 | 2017-05-01 | 2018-09-30 | 2017-04-30 | 2018-10-31 | 2021-03-01 | 2022-12-31 | 2022 | 2022
Pipeline including CS |  | TRA-N-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | Hungary |  | FGSZ Ltd. | Less-Advanced Non-FID | 2018-11-01 | 2020-04-30 | 2016-12-31 | 2017-05-01 | 2018-09-30 | 2017-04-30 | 2018-10-31 | 2021-03-01 | 2022-12-31 | 2022 | 2022
Pipeline including CS |  | TRA-N-071 | Physical Reverse Flow on South North Pipeline | Ireland |  | Gas Networks Ireland | Less-Advanced Non-FID | 2019-06-01 | 2020-05-31 | 2018-06-01 | 2020-06-01 | 2021-05-31 |  |  | 2021-06-01 | 2022-12-31 | 2022 | 2022
Pipeline including CS |  | TRA-N-271 | Poland - Denmark interconnection (Baltic Pipe) - PL section | Poland |  | GAZ-SYSTEM S.A. | Less-Advanced Non-FID | [9 empty] | 2022 | 2022
Storage Facility |  | UGS-N-659 | RENC-8 Carriço UGS cavern | Portugal |  | REN - Armazenagem, S.A. | Less-Advanced Non-FID | 2018-08-02: 2018-01-01; 2018-09-03: 2018-01-01; 2019-11-01: 2022-09-30 | 2022 | 2022
Pipeline including CS |  | TRA-N-053 | White Stream | Romania |  | White Stream Ltd | Less-Advanced Non-FID | [9 empty] | 2022 | 2022
Storage Facility |  | UGS-N-371 | Sarmasel undeground gas storage in Romania | Romania |  | Societatea Naţională de Gaze Naturale ROMGAZ S.A. | Less-Advanced Non-FID | 2017-11-01 | 2018-08-01 | 2017-10-01 | 2017-03-01 | 2018-09-01 | 2021-03-01 | 2018-09-01 | 2019-04-01 | 2022-05-01 | 2022 | 2022
Pipeline including CS |  | TRA-N-093 | CS Ajdovščina, 2nd phase of upgrade | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | [9 empty] | 2022 | 2022
Pipeline including CS |  | TRA-N-099 | M3/1a Šempeter - Ajdovščina | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | [9 empty] | 2022 | 2022
Pipeline including CS |  | TRA-N-101 | M8 Kalce - Jelšane | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | [9 empty] | 2022 | 2022
Pipeline including CS |  | TRA-N-107 | M6 Interconnection Osp | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | [9 empty] | 2022 | 2022
Pipeline including CS |  | TRA-N-261 | M3/1c Kalce - Vodice | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | [9 empty] | 2022 | 2022
Pipeline including CS |  | TRA-N-262 | M3/1b Ajdovščina - Kalce | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | [9 empty] | 2022 | 2022
LNG Terminal |  | LNG-N-297 | Mugardos LNG Terminal: Storage Extension | Spain |  | Reganosa | Less-Advanced Non-FID | 2019-04-01 | 2019-09-01 | 2019-09-01 | 2019-08-01 | 2020-03-01 | 2019-06-01 | 2019-06-01 | 2020-07-01 | 2022-12-01 | 2022 | 2022
Pipeline including CS |  | TRA-N-727 | Iberian‐French corridor: Eastern Axis ‐ Midcat Project | Spain |  | Enagás Transporte, S.A.U. | Less-Advanced Non-FID | 2018-01-01 | 2019-05-01 | 2018-03-01 | 2018-09-01 | 2020-12-01 |  | 2019-05-01 | 2021-01-01 | 2022-12-01 | 2022 | 2022
Pipeline including CS |  | TRA-N-224 | Gaspipeline Brod - Zenica | Bosnia Herzegovina |  | BH-Gas d.o.o. | Less-Advanced Non-FID | 2019-12-01 | 2021-04-30 | 2019-04-30 | 2020-01-01 | 2021-05-31 | 2022-05-31 | 2019-11-30 | 2022-06-01 | 2023-09-30 | 2023 | 2023
Pipeline including CS |  | TRA-N-910 | Western interconnection BiH/CRO | Bosnia Herzegovina |  | BH-Gas d.o.o. | Less-Advanced Non-FID | [9 empty] | 2023 | 2023
Pipeline including CS |  | TRA-N-070 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo) | Croatia |  | Plinacro Ltd | Less-Advanced Non-FID |  |  | 2016-08-01 | 2010-01-12 | 2023-10-02 |  | 2021-10-01 | 2022-01-01 | 2023-10-02 | 2023 | 2023
Pipeline including CS |  | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | Croatia |  | Plinacro Ltd | Less-Advanced Non-FID |  |  | 2016-08-01 | 2014-09-01 | 2023-01-01 |  | 2020-01-01 | 2021-01-01 | 2023-01-01 | 2023 | 2023
Pipeline including CS |  | TRA-N-755 | CS Rimpar | Germany |  | GRTgaz Deutschland GmbH | Less-Advanced Non-FID | [9 empty] | 2023 | 2023
Pipeline including CS |  | TRA-N-809 | Additional East-West transport NL | Germany |  | Gasunie Deutschland Transport Services GmbH | Less-Advanced Non-FID | 2017-08-01: 2018-01-01; 2018-02-01: 2018-01-01 | 2023 | 2023
Pipeline including CS |  | TRA-N-825 | Compressor station "Legden" | Germany |  | Open Grid Europe GmbH | Less-Advanced Non-FID | 2018-08-02: 2022-12-31; 2018-09-03: 2023-01-01; 2019-11-01: 2023-12-31 | 2023 | 2023
Pipeline including CS |  | TRA-N-014 | Komotini-Thesprotia pipeline | Greece |  | DESFA S.A. | Less-Advanced Non-FID | [9 empty] | 2023 | 2023
Pipeline including CS |  | TRA-N-1092 | Metering and Regulating Station at UGS South Kavala | Greece |  | DESFA S.A. | Less-Advanced Non-FID | [9 empty] | 2023 | 2023
Pipeline including CS |  | TRA-N-007 | Development for new import from the South (Adriatica Line) | Italy |  | Snam Rete Gas S.p.A. | Less-Advanced Non-FID | [9 empty] | 2023 | 2023
Pipeline including CS |  | TRA-N-354 | Interconnection with Slovenia | Italy |  | Snam Rete Gas S.p.A. | Less-Advanced Non-FID | [9 empty] | 2023 | 2023
Pipeline including CS |  | TRA-N-245 | North - South Gas Corridor in Eastern Poland | Poland |  | GAZ-SYSTEM S.A. | Less-Advanced Non-FID | [9 empty] | 2023 | 2023
Storage Facility |  | UGS-N-366 | New undergound gas storage in Romania | Romania |  | Societatea Naţională de Gaze Naturale ROMGAZ S.A. | Less-Advanced Non-FID | 2017-11-01 | 2018-11-01 | 2017-10-01 | 2017-03-01 | 2018-11-01 | 2021-07-01 | 2018-12-01 | 2019-07-01 | 2023-05-01 | 2023 | 2023
Pipeline including CS |  | TRA-N-959 | Further enlargement of the BG—RO—HU—AT transmission corridor (BRUA) phase 3 | Romania |  | SNTGN Transgaz SA | Less-Advanced Non-FID | [9 empty] | 2023 | 2023
Storage Facility |  | UGS-N-127 | Underground Gas Storage in salt leached caverns in the Bages area (ES) | Spain |  | Gas Natural | Less-Advanced Non-FID | 2012-09-30 | 2013-12-15 | 2018-09-30 | 2012-06-01 | 2018-09-30 |  | 2019-03-31 | 2019-03-31 | 2023-03-31 | 2023 | 2023
LNG Terminal |  | LNG-N-295 | Mugardos LNG Terminal: Send-out Increase | Spain |  | Reganosa | Less-Advanced Non-FID | 2021-04-01 | 2021-10-01 | 2021-10-01 | 2021-09-01 | 2022-03-01 | 2022-06-01 | 2022-06-01 | 2022-06-01 | 2023-12-31 | 2023 | 2025
Pipeline including CS |  | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | France |  | GRTgaz and TIGF | Less-Advanced Non-FID | 2018-01-01: 2017-06-30 | 2024 | 2024
Pipeline including CS |  | TRA-N-380 | BG-RO-HU-AT transmission corridor | Hungary |  | FGSZ Ltd. | Less-Advanced Non-FID | 2019-11-01: 2023-12-31 | 2024 | 2024
LNG Terminal |  | LNG-N-824 | LNG Terminal in Klaipeda | Lithuania |  | AB Klaipėdos Nafta | Less-Advanced Non-FID | 2018-08-02: 2018-12-31 | 2024 | 2024
Pipeline including CS |  | TRA-N-114 | R61 Dragonja - Izola | Slovenia |  | Plinovodi d.o.o. | Less-Advanced Non-FID | [9 empty] | 2024 | 2024
Pipeline including CS |  | TRA-N-284 | 3rd IP between Portugal and Spain (Compressor Station) | Portugal |  | REN-Gasodutos, S.A. | Less-Advanced Non-FID | 2018-08-02: 2022-12-31; 2018-09-03: 2023-01-03; 2019-11-01: 2025-12-31 | 2025 | 2025
Pipeline including CS |  | TRA-N-285 | 3rd IP between Portugal and Spain (pipeline Cantanhede-Mangualde) | Portugal |  | REN-Gasodutos, S.A. | Less-Advanced Non-FID | 2018-08-02: 2022-12-31; 2018-09-03: 2023-01-03; 2019-11-01: 2025-12-31 | 2025 | 2025
Pipeline including CS |  | TRA-N-729 | Interconnection ES-PT (3rd IP) - 2nd phase | Spain |  | Enagás Transporte, S.A.U. | Less-Advanced Non-FID | 2017-08-01: 2017-01-01; 2017-12-01: 2018-05-31; 2018-01-01: 2018-03-01 | 2025 | 2025
Pipeline including CS |  | TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Croatia |  | Plinacro Ltd | Less-Advanced Non-FID | 2018-02-01: 2012-12-05; 2018-06-01: 2026-09-01; 2018-08-02: 2024-12-01; 2018-09-03: 2025-04-01; 2019-11-01: 2026-11-01 | 2026 | 2026
Pipeline including CS |  | TRA-N-336 | Interconnection Croatia/Slovenia (Umag-Koper) | Croatia |  | Plinacro Ltd | Less-Advanced Non-FID | 2018-09-03: 2026-04-01; 2019-11-01: 2026-11-01 | 2026 | 2026
Pipeline including CS |  | TRA-N-031 | Connection of Malta to the European Gas Network - Pipelines | Malta |  | Office of the Prime Minister (Energy) | Less-Advanced Non-FID | 2019-08-01 | 2020-06-01 | 2019-04-01 | 2017-04-01 | 2020-06-01 | 2021-10-01 | 2020-06-01 | 2023-05-01 | 2025-11-01 | 2026 | 2026
Storage Facility |  | UGS-N-914 | UGS Damaslawek | Poland |  | GAZ-SYSTEM S.A. | Less-Advanced Non-FID | [9 empty] | 2026 | 2026
Pipeline including CS |  | TRA-N-376 | Azerbaijan, Georgia, Romania Interconnector - AGRI | Romania |  | AGRI LNG Project Company SRL (RO) | Less-Advanced Non-FID | 2019-01-01 | 2020-04-01 | 2021-06-01 | 2018-01-01 | 2019-09-01 | 2022-10-01 | 2020-11-01 | 2022-06-01 | 2026-08-01 | 2026 | 2026
LNG Terminal |  | LNG-N-165 | Gran Canaria send out increase | Spain |  | Gascan | Less-Advanced Non-FID | [9 empty] | 2026 | 2026
LNG Terminal |  | LNG-N-185 | Tenerife Send-Out increase | Spain |  | Gascan | Less-Advanced Non-FID | [9 empty] | 2026 | 2026
Pipeline including CS |  | TRA-N-955 | GUD: Complete conversion to H-gas | Germany |  | Gasunie Deutschland Transport Services GmbH | Less-Advanced Non-FID | [9 empty] | 2030 | 2030
Pipeline including CS |  | TRA-N-975 | Sardinia Gas Transportation Network | Italy |  | Società Gasdotti Italia | Less-Advanced Non-FID | 2016-03-01 | 2016-12-31 | 2014-06-30 | 2017-01-01 | 2018-12-31 | 2019-06-30 | 2016-12-31 | 2019-06-01 |  | 2031 | 2031
LNG Terminal |  | LNG-N-211 | Connection of Malta to the European Gas Network - LNG Regasification | Malta |  | Office of the Prime Minister (Energy) | Less-Advanced Non-FID | 2026-01-01 | 2028-01-01 | 2027-01-01 | 2025-01-01 | 2028-01-01 | 2028-01-01 | 2028-01-01 | 2029-01-01 | 2031-01-01 | 2031 | 2031
Pipeline including CS |  | TRA-N-008 | Import developments from North-East | Italy |  | Snam Rete Gas S.p.A. | Less-Advanced Non-FID | [9 empty] | 2034 | 2034
Pipeline including CS |  | TRA-N-009 | Additional Southern developments | Italy |  | Snam Rete Gas S.p.A. | Less-Advanced Non-FID | [9 empty] | 2034 | 2034
Storage Facility |  | UGS-N-141 | Construction of new gas storage facility on the territory of Bulgaria | Bulgaria |  | Bulgartransgaz EAD | Less-Advanced Non-FID | [9 empty] | Unknown | Unknown
Pipeline including CS |  | TRA-N-065 | Hajduszoboszlo CS | Hungary |  | FGSZ Natural Gas transmission Company limited by Shares. | Less-Advanced Non-FID | [9 empty] | Unknown | Unknown
LNG Terminal |  | LNG-N-030 | Shannon LNG Terminal and Connecting Pipeline | Ireland |  | Shannon LNG | Less-Advanced Non-FID | 2016-07-01 | 2017-06-01 | 2010-01-01 | 2007-10-01 | 2009-12-01 | 2018-06-01 | 2018-06-01 | 2018-07-01 | 2021-06-01 | Unknown | Unknown
LNG Terminal |  | LNG-N-162 | Gran Canaria 2º LNG Tank | Spain |  | Gascan | Less-Advanced Non-FID | [9 empty] | Unknown | Unknown
LNG Terminal |  | LNG-N-184 | Tenerife 2º LNG Storage Tank | Spain |  | Gascan | Less-Advanced Non-FID | [9 empty] | Unknown | Unknown
Pipeline including CS |  | TRA-N-339 | Trans-Caspian | Turkmenistan |  | W-Stream Caspian Pipeline Company Ltd | Less-Advanced Non-FID | [9 empty] | Unknown | Unknown
Pipeline including CS |  | TRA-N-346 | Industrial Emissions Directive (LCP) | United Kingdom |  | National Grid Gas plc | Less-Advanced Non-FID | [9 empty] | Unknown | Unknown
Pipeline including CS |  | TRA-N-349 | Industrial Emisssion Directive (IPPC) - Non-FID | United Kingdom |  | National Grid Gas plc | Less-Advanced Non-FID | [9 empty] | Unknown | Unknown

## Barriers to Investment
| TYNDP Annex A |  |  |  | Barriers to Investment - Page 7
Barriers to Investment
Project Type |  | Code | Name | Promoter |  | Barrier Type | Barrier
Pipeline including CS |  | TRA-N-428 | (Mirror) Baltic Pipe | Energinet.dk |  | Regulatory | Lack of confidence and risk-taking in the private gas sector as it requires coordinated long-term business cases, fundamental change in current business models/subsidies and involves many parties from three countries. In addition this project must be coordinated with a connection from Norwagian Gassled to Denmarks gas infrastructure.
Pipeline including CS |  | TRA-N-284 | 3rd IP between Portugal and Spain (Compressor Station) | REN-Gasodutos, S.A. |  | Market | Lack of market support
Pipeline including CS |  | TRA-N-284 | 3rd IP between Portugal and Spain (Compressor Station) | REN-Gasodutos, S.A. |  | Market | Regarding the market survey, the 3rd interconnection between the gas systems of Portugal and Spain is regarded as commercially non-viable as has been demonstrated by the responses of the stakeholders to the public consultation process on the gas sector TYNDP for Portugal held in 2015 in what concerns this specific project, meaning that its potential users are not willing to make any prior commitments in terms of capacity booking.
Pipeline including CS |  | TRA-N-284 | 3rd IP between Portugal and Spain (Compressor Station) | REN-Gasodutos, S.A. |  | Regulatory | In simple terms and according to the current Portuguese regulation, the revenue stream respecting the part of the project allocated to Portuguese consumers (after the CBCA decision by the regulators of Portugal and Spain) will be obtained by the remuneration of the net invested capital of the project plus the amortization recovery and the opex cost recovery (subject to a mix of price cap and revenue cap regimes). Nevertheless, it’s important to notice that it is not possible to predict if, when and to what extent any changes to this model may occur.
Pipeline including CS |  | TRA-N-285 | 3rd IP between Portugal and Spain (pipeline Cantanhede-Mangualde) | REN-Gasodutos, S.A. |  | Market | Regarding the market survey, the 3rd interconnection between the gas systems of Portugal and Spain is regarded as commercially non-viable as has been demonstrated by the responses of the stakeholders to the public consultation process on the gas sector TYNDP for Portugal held in 2015 in what concerns this specific project, meaning that its potential users are not willing to make any prior commitments in terms of capacity booking.
Pipeline including CS |  | TRA-N-285 | 3rd IP between Portugal and Spain (pipeline Cantanhede-Mangualde) | REN-Gasodutos, S.A. |  | Regulatory | In simple terms and according to the current Portuguese regulation, the revenue stream respecting the part of the project allocated to Portuguese consumers (after the CBCA decision by the regulators of Portugal and Spain) will be obtained by the remuneration of the net invested capital of the project plus the amortization recovery and the opex cost recovery (subject to a mix of price cap and revenue cap regimes). Nevertheless, it’s important to notice that it is not possible to predict if, when and to what extent any changes to this model may occur.
Pipeline including CS |  | TRA-N-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | REN-Gasodutos, S.A. |  | Market | Regarding the market survey, the 3rd interconnection between the gas systems of Portugal and Spain is regarded as commercially non-viable as has been demonstrated by the responses of the stakeholders to the public consultation process on the gas sector TYNDP for Portugal held in 2015 in what concerns this specific project, meaning that its potential users are not willing to make any prior commitments in terms of capacity booking.
Pipeline including CS |  | TRA-N-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | REN-Gasodutos, S.A. |  | Permit Granting | A pre-application decision is expected by December 2016 and the statutory decision is expected by December 2018.
Pipeline including CS |  | TRA-N-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | REN-Gasodutos, S.A. |  | Regulatory | In simple terms and according to the current Portuguese regulation, the revenue stream respecting the part of the project allocated to Portuguese consumers (after the CBCA decision by the regulators of Portugal and Spain) will be obtained by the remuneration of the net invested capital of the project plus the amortization recovery and the opex cost recovery (subject to a mix of price cap and revenue cap regimes). Nevertheless, it’s important to notice that it is not possible to predict if, when and to what extent any changes to this model may occur.
Pipeline including CS |  | TRA-N-376 | Azerbaijan, Georgia, Romania Interconnector - AGRI | AGRI LNG Project Company SRL (RO) |  | Financing | Availability of funds and associated conditions
Pipeline including CS |  | TRA-N-376 | Azerbaijan, Georgia, Romania Interconnector - AGRI | AGRI LNG Project Company SRL (RO) |  | Market | Lack of market support
Pipeline including CS |  | TRA-N-376 | Azerbaijan, Georgia, Romania Interconnector - AGRI | AGRI LNG Project Company SRL (RO) |  | Market | market further integration with the local Project is required
Pipeline including CS |  | TRA-N-376 | Azerbaijan, Georgia, Romania Interconnector - AGRI | AGRI LNG Project Company SRL (RO) |  | Permit Granting | long duration for obtaining permits
Pipeline including CS |  | TRA-N-895 | Balticconnector | Elering AS |  | Financing | Availability of funds and associated conditions
Pipeline including CS |  | TRA-N-928 | Balticconnector Finnish part | Baltic Connector Oy |  | Financing | Availability of funds and associated conditions
Pipeline including CS |  | TRA-N-380 | BG-RO-HU-AT transmission corridor | FGSZ Ltd. |  | Market | Lack of market maturity
Pipeline including CS |  | TRA-N-380 | BG-RO-HU-AT transmission corridor | FGSZ Ltd. |  | Market | Lack of market support
Pipeline including CS |  | TRA-N-380 | BG-RO-HU-AT transmission corridor | FGSZ Ltd. |  | Regulatory | Low rate of return
Pipeline including CS |  | TRA-N-902 | Capacity increase at IP Lanžhot entry | eustream, a.s. |  | Market | Lack of market maturity
Pipeline including CS |  | TRA-N-902 | Capacity increase at IP Lanžhot entry | eustream, a.s. |  | Regulatory | Capacity quotas
Pipeline including CS |  | TRA-N-902 | Capacity increase at IP Lanžhot entry | eustream, a.s. |  | Regulatory | Low rate of return
Pipeline including CS |  | TRA-N-320 | Carregado Compressor Station | REN-Gasodutos, S.A. |  | Regulatory | In simple terms and according to the current Portuguese regulation, the revenue stream will be obtained by the remuneration of the net invested capital of the project plus the amortization recovery and the opex cost recovery (subject to a mix of price cap and revenue cap regimes). These revenues will be ensured through the payment of regulated TPA tariffs by network users Nevertheless, it’s important to notice that it is not possible to predict if, when and to what extent any changes to this model may occur.
LNG Terminal |  | LNG-N-211 | Connection of Malta to the European Gas Network - LNG Regasification | Office of the Prime Minister (Energy) |  | Market | Lack of market maturity
LNG Terminal |  | LNG-N-211 | Connection of Malta to the European Gas Network - LNG Regasification | Office of the Prime Minister (Energy) |  | Market | Lack of market support
Storage Facility |  | UGS-N-233 | Depomures | Engie Romania SA |  | Financing | Availability of funds and associated conditions
Storage Facility |  | UGS-N-233 | Depomures | Engie Romania SA |  | Permit Granting | The permit granting process has been delayed due to difficulties in obtaining the building permit from local administration for the last section of the main collector pipeline, which may impact the implementation of the entire project.
Storage Facility |  | UGS-N-233 | Depomures | Engie Romania SA |  | Regulatory | Low or zero-priced short-term capacity
Storage Facility |  | UGS-N-233 | Depomures | Engie Romania SA |  | Regulatory | Low rate of return
Pipeline including CS |  | TRA-N-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT Corridor) | SNTGN Transgaz S.A. |  | Permit Granting | Long and complicated process implying the need to receive the right of access on the field
Pipeline including CS |  | TRA-N-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT Corridor) | SNTGN Transgaz S.A. |  | Regulatory | ​The Competent Authority to coordinate all permit granting processes is not yet functional in Romania.
Pipeline including CS |  | TRA-N-362 | Development on the Romanian territory of the Southern Transmission Corridor | SNTGN Transgaz SA |  | Financing | Availability of funds and associated conditions
Pipeline including CS |  | TRA-N-362 | Development on the Romanian territory of the Southern Transmission Corridor | SNTGN Transgaz SA |  | Permit Granting | Long and complicated process requiring also the obtaining of the right of way
Pipeline including CS |  | TRA-N-362 | Development on the Romanian territory of the Southern Transmission Corridor | SNTGN Transgaz SA |  | Regulatory | ​Changes in national/EU legislation whcih may impact the implementation of the project.
Pipeline including CS |  | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | GRTgaz |  | Market | Lack of market support
Pipeline including CS |  | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | GRTgaz |  | Others | The current context of LNG in Europe isn't favorable to the developements of LNG capacities
Pipeline including CS |  | TRA-N-258 | Developments for Montoir LNG terminal 2.5 bcm expansion | GRTgaz |  | Market | Lack of market support
LNG Terminal |  | LNG-N-328 | Eagle LNG and Pipeline | Burns Srl |  | Market | In Albania the legislation on gas market and gas infrastructure is not yet complete as the gas sector is under development. It is not yet clear the demand size and its build up timing in Albania, initially driven by new investments on gas-fired power plants. Likewise it is still uncertain the gas purchase price level that these anchor points can guarantee.
LNG Terminal |  | LNG-N-328 | Eagle LNG and Pipeline | Burns Srl |  | Market | Lack of market maturity
LNG Terminal |  | LNG-N-328 | Eagle LNG and Pipeline | Burns Srl |  | Permit Granting | The local (regional and communal) approvals in Italy for the onshore pipeline infrastructures represent a possible source of concern as a potential cause of delays.
Pipeline including CS |  | TRA-N-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A |  | Financing | It is going to be submitted a request to access CEF funds for feasibility studies
Pipeline including CS |  | TRA-N-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A |  | Political | EastMed Pipeline has been consistently supported by the Cypriot, Greek and Italian Governments.
Pipeline including CS |  | TRA-N-915 | Enhancement of Estonia-Latvia interconnection | Elering AS |  | Financing | Availability of funds and associated conditions
Storage Facility |  | UGS-N-374 | Enhancement of Incukalns UGS | JSC "Latvijas Gaze" |  | Financing | Availability of funds and associated conditions
Storage Facility |  | UGS-N-374 | Enhancement of Incukalns UGS | JSC "Latvijas Gaze" |  | Market | Lack of market support
LNG Terminal |  | LNG-N-227 | Fos Cavaou LNG Terminal Expansion | Fosmax LNG |  | Political | Discrimination aiming at preventing the project to be recognized as an efficient alternative to a third gas pipeline through the Pyreneans.
Pipeline including CS |  | TRA-N-959 | Further enlargement of the BG—RO—HU—AT transmission corridor (BRUA) phase 3 | SNTGN Transgaz SA |  | Market | Lack of market support
Pipeline including CS |  | TRA-N-959 | Further enlargement of the BG—RO—HU—AT transmission corridor (BRUA) phase 3 | SNTGN Transgaz SA |  | Permit Granting | The permitting procesc is long and complicated
Pipeline including CS |  | TRA-N-012 | GALSI Pipeline Project | Galsi S.p.A. |  | Financing | EEPR funds for 120 millions euros were granted by the European Commission with decision on 13th August 2010. This grant was then cancelled with decision on 26th September 2014. Future availability of new European Commission funds would be a key issue for the success of the project.
Pipeline including CS |  | TRA-N-012 | GALSI Pipeline Project | Galsi S.p.A. |  | Market | The persistent uncertainties in the market scenarios make more complex the finalisation by the Shareholders of the commercial framework of the project, i.e. the definition of suitable terms and conditions for the gas supply and gas transportation agreements, which represents an essential piece for the final investment decision.
Pipeline including CS |  | TRA-N-012 | GALSI Pipeline Project | Galsi S.p.A. |  | Permit Granting | Permitting process (involved inter alia 2 regions, 9 provinces and 40 townships) substantially completed: environmental permi
Pipeline including CS |  | TRA-N-012 | GALSI Pipeline Project | Galsi S.p.A. |  | Regulatory | The Italian Section of the project will be ruled under the Italian regulatory framework.​ The International Section (from Algeria to Italian territorial waters in Sardinia) will be build and operated by Galsi as an independent operator with a tariff agreed between the Company and shippers.
Pipeline including CS |  | TRA-N-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | GAZ-SYSTEM S.A. |  | Market | Lack of market maturity
Pipeline including CS |  | TRA-N-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | GAZ-SYSTEM S.A. |  | Others | Lack of guarantees of covering entire project costs when the project is not commercially viable in all market scenarios (SoS project). Risk of the lack of interest in capacity booking in the first period of operation due to unmaturity of the gas markets in the Baltic States.
Pipeline including CS |  | TRA-N-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | GAZ-SYSTEM S.A. |  | Permit Granting | Efficient permitting procedures are necessary for timely implementation of the project.
Pipeline including CS |  | TRA-N-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | GAZ-SYSTEM S.A. |  | Political | Lack of guarantees of covering entire project costs when the project is not commercially viable in all market scenarios (SoS project).
Pipeline including CS |  | TRA-N-224 | Gaspipeline Brod - Zenica | BH-Gas d.o.o. |  | Financing | Availability of funds and associated conditions
Pipeline including CS |  | TRA-N-224 | Gaspipeline Brod - Zenica | BH-Gas d.o.o. |  | Market | Lack of market support
Pipeline including CS |  | TRA-N-224 | Gaspipeline Brod - Zenica | BH-Gas d.o.o. |  | Permit Granting | Projects runs through the two BiH entities and procedures of providing neccessary consent have to be conducted in accordance with positive legilsation of both entities, and permits have to be issued by relevant bodies of Federation of BiH and Republic of Srpska. Provision of permits will be accordingly long lasting and expensive. The same is related to the land acquisition.
Pipeline including CS |  | TRA-N-224 | Gaspipeline Brod - Zenica | BH-Gas d.o.o. |  | Political | Lack of primary gas legislation in accordance with Third Energy Package, as well as energy policy at the state level.
Pipeline including CS |  | TRA-N-224 | Gaspipeline Brod - Zenica | BH-Gas d.o.o. |  | Regulatory | Lack of proper transposition of EU regulation
Pipeline including CS |  | TRA-N-394 | Gassled - Danish upstream system | Energinet.dk |  | Market | Currently negotiations are ongoing with Norwegian partner. An important issue is the coordination with the Baltic pipe project (connection between DK and PL).
Pipeline including CS |  | TRA-N-394 | Gassled - Danish upstream system | Energinet.dk |  | Market | Lack of market maturity
Pipeline including CS |  | TRA-N-631 | Greek part of Tesla project | DESFA S.A. |  | Political | Uncertainty on the implementation of upstream infrastructure due to geopolitical issues in the Region.
Pipeline including CS |  | TRA-N-950 | Guitiriz - Zamora pipeline | Reganosa |  | Regulatory | Lack of proper transposition of EU regulation
Pipeline including CS |  | TRA-N-585 | Hungarian section of Tesla project | FGSZ Ltd. |  | Others | Financing difficulties.
Pipeline including CS |  | TRA-N-586 | HU-UA reverse flow | FGSZ Ltd. |  | Others | Financing difficulties.
Pipeline including CS |  | TRA-N-727 | Iberian‐French corridor: Eastern Axis ‐ Midcat Project | Enagás Transporte, S.A.U. |  | Market | In the Open Season launched in 2010 between Spain and France MidCat didn't obtain enough market support .
Pipeline including CS |  | TRA-N-727 | Iberian‐French corridor: Eastern Axis ‐ Midcat Project | Enagás Transporte, S.A.U. |  | Market | Lack of market support
Pipeline including CS |  | TRA-N-727 | Iberian‐French corridor: Eastern Axis ‐ Midcat Project | Enagás Transporte, S.A.U. |  | Regulatory | In 2010, Enagás, TIGF and GRTgaz carried out an OS to ask for binding commitments for capacities provided by MidCat and/or Irún/Biriatou and GRTgaz North-South link. Concerning MidCat, none of the three proposed infrastructure scenarios received enough bids to be triggered. This OS is currently the latest call made to the market regarding MidCat.However, MidCat has demonstrated benefits in terms of market integration (price convergence), security of supply and diversification of supply.Taking into account that the OS2015 was carried out in a context of economic prosperity in comparison with the current situation jointly with the new tendency in contracting capacity (from long term to short term) well as the decrease in gas consumption, it is not foreseen that network users would make enough long-term commitments in order to fully cover the investment. Besides, recent changes in the Spanish regulatory framework would not contribute to have an appropriate rate of return of the investment
Pipeline including CS |  | TRA-N-727 | Iberian‐French corridor: Eastern Axis ‐ Midcat Project | Enagás Transporte, S.A.U. |  | Regulatory | Low rate of return
Pipeline including CS |  | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF |  | Market | Lack of market support
Pipeline including CS |  | TRA-N-346 | Industrial Emissions Directive (LCP) | National Grid Gas plc |  | Regulatory | ​Allowed Revenue
Pipeline including CS |  | TRA-N-066 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Plinacro Ltd |  | Political | ​This project is politicaly very sensitive and depends on the agreement with Republika Srpska and agremments within B&H and its TSOs (BH Gas and GasRES)
Pipeline including CS |  | TRA-F-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Rogatec) | Plinacro Ltd |  | Financing | Availability of funds and associated conditions
Pipeline including CS |  | TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Plinacro Ltd |  | Market | Lack of market maturity
Pipeline including CS |  | TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Plinacro Ltd |  | Market | Lack of market support
Pipeline including CS |  | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Enagás Transporte, S.A.U. |  | Market | Lack of market support
Pipeline including CS |  | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Enagás Transporte, S.A.U. |  | Others | It would be difficult to carry out an Open Season due to the size of the Portuguese market and the lack of long-term contracts in Portugal. The lack of long term binding commitments from network users cannot guarantee the return of the investment to the Spanish system.
Pipeline including CS |  | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Enagás Transporte, S.A.U. |  | Regulatory | It would be difficult to carry out an Open Season due to the size of the Portuguese market and the lack of long-term contracts in Portugal. The lack of long term binding commitments from network users cannot guarantee the return of the investment to the Spanish system.
Pipeline including CS |  | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Enagás Transporte, S.A.U. |  | Regulatory | Low rate of return
Pipeline including CS |  | TRA-N-729 | Interconnection ES-PT (3rd IP) - 2nd phase | Enagás Transporte, S.A.U. |  | Market | It would be difficult to carry out an Open Season due to the size of the Portuguese market and the lack of long-term contracts in Portugal. The lack of long term binding commitments from network users cannot guarantee the return of the investment to the Spanish system.
Pipeline including CS |  | TRA-N-729 | Interconnection ES-PT (3rd IP) - 2nd phase | Enagás Transporte, S.A.U. |  | Regulatory | It would be difficult to carry out an Open Season due to the size of the Portuguese market and the lack of long-term contracts in Portugal. The lack of long term binding commitments from network users cannot guarantee the return of the investment to the Spanish system.
Pipeline including CS |  | TRA-N-729 | Interconnection ES-PT (3rd IP) - 2nd phase | Enagás Transporte, S.A.U. |  | Regulatory | Low rate of return
Pipeline including CS |  | TRA-N-998 | Interconnection Macedonia-Albania | MER JSC Skopje |  | Others | Barriers regarding the implementation of the projects have not been encountered.
Pipeline including CS |  | TRA-N-976 | Interconnection Macedonia-Bulgaria | MER JSC Skopje |  | Others | Barriers regarding the realization of the project have not been encountered.
Pipeline including CS |  | TRA-N-980 | Interconnection Macedonia-Greece | MER JSC Skopje |  | Others | Barriers regarding the implementation of the project have not been encountered.
Pipeline including CS |  | TRA-N-966 | Interconnection Macedonia-Kosovo | MER JSC Skopje |  | Others | Due to obstacles to the development of the gasification, the projects in Kosovo have been postponed.
Pipeline including CS |  | TRA-N-965 | Interconnection Macedonia-Serbia | MER JSC Skopje |  | Others | Barriers regarding the implementation of the projects have not been encountered.
Pipeline including CS |  | TRA-N-965 | Interconnection Macedonia-Serbia | MER JSC Skopje |  | Permit Granting | After determining the project financing.
Pipeline including CS |  | TRA-N-139 | Interconnection of the NTS with the DTS and reverse flow at Isaccea | SNTGN Transgaz SA |  | Financing | Availability of funds and associated conditions
Pipeline including CS |  | TRA-N-139 | Interconnection of the NTS with the DTS and reverse flow at Isaccea | SNTGN Transgaz SA |  | Permit Granting | The permitting process is long and complicated
Pipeline including CS |  | TRA-N-139 | Interconnection of the NTS with the DTS and reverse flow at Isaccea | SNTGN Transgaz SA |  | Regulatory | ​The Competent Authority to coordinate all permit granting processes is not yet functional in Romania.
Pipeline including CS |  | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | ICGB a.d. |  | Market | ​Development of the networks of neighboring gas TSOs to be interconnected with IGB should be incentivised to ensure proper technical conditions for expected additional flows. Better integration of the gas transmission networks in the overall region affected by IGB must also be achieved in order to supply gas from IGB to the wider SEE region.
Pipeline including CS |  | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | ICGB a.d. |  | Permit Granting | Affected by delays
Pipeline including CS |  | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | ICGB a.d. |  | Political | ​Government support expected on issues such as streamlined permitting and regulatory decisions on commercial development, availability of financial incentives
Pipeline including CS |  | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | ICGB a.d. |  | Regulatory | ​The regulatory framework has to provide more streamlined process for decisions on TPA regime and licencing, and ensure a viable rate of financial return from the investment.
Pipeline including CS |  | TRA-N-068 | Ionian Adriatic Pipeline | Plinacro Ltd |  | Financing | Availability of funds and associated conditions
Pipeline including CS |  | TRA-N-068 | Ionian Adriatic Pipeline | Plinacro Ltd |  | Political | The pipeline passes by EU country and Non EU countries.
Pipeline including CS |  | TRA-N-068 | Ionian Adriatic Pipeline | Plinacro Ltd |  | Regulatory | Tarrifs which depends on the Business Model
Storage Facility |  | UGS-N-294 | Islandmagee Gas Storage Facility | Islandmagee Storage Limited |  | Market | The Islandmagee gas storage facility requires competitive gas storage transmission tariffs in order to compete against GB storage facilities.
Pipeline including CS |  | TRA-N-014 | Komotini-Thesprotia pipeline | DESFA S.A. |  | Market | Lack of market support
Pipeline including CS |  | TRA-N-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | Plinacro Ltd |  | Others | The project completly depends on the realisation of the Krk LNG project
Pipeline including CS |  | TRA-N-075 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Plinacro Ltd |  | Financing | Availability of funds and associated conditions
Pipeline including CS |  | TRA-N-075 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Plinacro Ltd |  | Others | Directly connected and depening on the LNG project on the island of Krk
LNG Terminal |  | LNG-N-824 | LNG Terminal in Klaipeda | AB Klaipėdos Nafta |  | Financing | Amortization rates
LNG Terminal |  | LNG-N-824 | LNG Terminal in Klaipeda | AB Klaipėdos Nafta |  | Financing | Availability of funds and associated conditions
LNG Terminal |  | LNG-N-824 | LNG Terminal in Klaipeda | AB Klaipėdos Nafta |  | Market | Lack of market maturity
LNG Terminal |  | LNG-N-824 | LNG Terminal in Klaipeda | AB Klaipėdos Nafta |  | Market | Lack of market support
LNG Terminal |  | LNG-N-824 | LNG Terminal in Klaipeda | AB Klaipėdos Nafta |  | Political | ​Klaipeda LNG terminal project is supported by all political institutions in Lithuania (i.e. President office, the Government, Ministries, Parliament, other). Project is supported by COM and pilot action is regarded as a success story: https://ec.europa.eu/energy/sites/ener/files/documents/1_EN_ACT_part1_v10-1.pdf
LNG Terminal |  | LNG-N-824 | LNG Terminal in Klaipeda | AB Klaipėdos Nafta |  | Regulatory | ​According to LNG terminal Law, all fixed LNG terminal expenses are covered via gas transmission tariff, while variable costs are included in regasification tariff. Due to low or none variable costs, capacity reservation is free of charge. Additional income from other regulated LNG terminal activities shall cover fixed terminal expenses and no additional profit shall be experienced.
LNG Terminal |  | LNG-N-824 | LNG Terminal in Klaipeda | AB Klaipėdos Nafta |  | Regulatory | Low or zero-priced short-term capacity
LNG Terminal |  | LNG-N-062 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | Gastrade S.A. |  | Financing | ​The Project has been awarded with grants for studies (CEF 2014 Call) and will apply for grants for works (in the next Calls) from the CEF. Award of such Public financing will be critical for the Project's commercial viability. Also access to EIB, EBRD, EFSI, IFC PCI favourable financing tools is very important for the Project.
LNG Terminal |  | LNG-N-062 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | Gastrade S.A. |  | Financing | Availability of funds and associated conditions
LNG Terminal |  | LNG-N-062 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | Gastrade S.A. |  | Market | Lack of market maturity
LNG Terminal |  | LNG-N-062 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | Gastrade S.A. |  | Market | The markets in SEE are not mature. Currently all gas transactions are done on a bilateral basis and no price transparency exists. Creation of a trading hub in the region with multiple supply options will generate significant opportunities for the marketing of gas imported through the LNG Alexandroupolis floating terminal.
LNG Terminal |  | LNG-N-062 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | Gastrade S.A. |  | Others | ​Delays in the implementation/start up of new regional interconnection infrastructures (IGB, IBS) and upgrade of existing ones including reverse flow availability. The most critical one is the Interconnector Greece-Bulgaria (IGB). Also, availability of capacity in the greek, bulgarian and romanian Transmission Systems and reverse flow capacity in Trans Balkan will enable flows from the terminal to Ukraine. Finally, reverse flow functionality to the Turkey-Greece Interconnector will open up the Turkish market to the Project. Regarding Financing: The project received grants for studies (from the 1st CEF Energy Call-August 2014) and will apply for grants for works in a future Call from CEF. Award of such Public financing will be critical for the Project's commercial viability. Also access to EIB, EBRD, EFSI, IFC PCI favourable financing tools is very important for the Project.
LNG Terminal |  | LNG-N-062 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | Gastrade S.A. |  | Permit Granting | See above. Delays in Permit granting have led to delays in Project implementation.
LNG Terminal |  | LNG-N-062 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | Gastrade S.A. |  | Political | ​​No political barriers. On the contrary, there is clear and declared Political support for the Project from the impacted Member States and in particular from the governments of Greece and Bulgaria​. Political stability in the region of the Project's direct influence will support commercial viability of the Project.
LNG Terminal |  | LNG-N-062 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | Gastrade S.A. |  | Regulatory | ​If tariff levels for the Project do not enjoy the same regulatory regime as the one applied for other competitive regulated infrastructures in the area, then the Project will become commercially unattractive to potential regional offtakers and therefore financially not viable.
Pipeline including CS |  | TRA-N-063 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Gastrade S.A. |  | Financing | ​The Project has been awarded with grants for studies (CEF 2014 Call) and will aply for grants for works (in the next Calls) from the CEF. Award of such Public financing will be critical for the Project's commercial viability. Also access to EIB, EBRD, EFSI, IFC PCI favourable financing tools is very important for the Project.
Pipeline including CS |  | TRA-N-063 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Gastrade S.A. |  | Financing | Availability of funds and associated conditions
Pipeline including CS |  | TRA-N-063 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Gastrade S.A. |  | Market | Lack of market maturity
Pipeline including CS |  | TRA-N-063 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Gastrade S.A. |  | Market | The markets in SEE are not mature. Currently all gas transactions are done in a bilateral basis and no price transparency exists. Creation of a trading hub in the region with multiple supply options will generate significant opportunities for the marketing of gas imported through the LNG Alexandroupolis floating terminal (that the pipeline will be connected to).
Pipeline including CS |  | TRA-N-063 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Gastrade S.A. |  | Others | Delays in the implementation/start up of new regional interconnection infrastructure (IGB/IBS) and upgrade of existing ones including reverse flow availability. The most critical one is the Interconnector Grece-Bulgaria (IGB). Also, availability of capacity in the greek, bulgarian and romanian Transmission Systems and reverse flow capacity in Trans Balkan will enable flows from the Terminal (through the assorted pipeline) to Ukraine. Finally, reverse flow functionality to the Turkey-Greece Interconnector will open up the Turkish market to the Project. Regarding financing: The Project received grants for studies (from the 1st CEF Energy Call-August 2014) and will apply for works in a future Call from CEF. Award of such Public financing will be critical for the Project's commercial viability. Also access to EIB, EBRD, EFSI, IFC PCI favourable financing tools is very important for the Project.
Pipeline including CS |  | TRA-N-063 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Gastrade S.A. |  | Permit Granting | See above. Delays in Permit granting have led to delays in Project implementation.
Pipeline including CS |  | TRA-N-063 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Gastrade S.A. |  | Political | ​No political barriers. On the contrary, there is clear and declared Political support for the Project from the impacted Member States and in particular from the governments of Greece and Bulgaria. Political stability in the region of the Project's direct influence will support commercial viability of the Project.
Pipeline including CS |  | TRA-N-063 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Gastrade S.A. |  | Regulatory | If tariff levels for the Project do not enjoy the same regulatory regime as the one applied for other competitive regulated infrastructures in the area, then the Project will become commercially unattractive to potential regional offtakers and therefore financially not viable.
LNG Terminal |  | LNG-N-082 | LNG terminal Krk | LNG Hrvatska d.o.o. za poslovanje ukapljenim prirodnim plinom |  | Market | Market Background Analysis was carried out and it indicated that the market has commercial potential. Open Season procedure will serve as an official confirmation of that analysis. The binding phase of Open Season has been carried out. Signing of the contract is expected to be upon NRA's approval of missing regulatory framework for liquefied natural gas i.e. methodology for determination of tariff for receiving LNG and gas send-out.
LNG Terminal |  | LNG-N-082 | LNG terminal Krk | LNG Hrvatska d.o.o. za poslovanje ukapljenim prirodnim plinom |  | Others | Potential barrier of enough pipeline capacity availability. The pipelines need to be build but FID has not yet been reached, which is a precondition for LNG terminal realization in forseen deadlines.
LNG Terminal |  | LNG-N-082 | LNG terminal Krk | LNG Hrvatska d.o.o. za poslovanje ukapljenim prirodnim plinom |  | Permit Granting | Permit granting process for the project has started in 10/2013 by requesting the EIA which was approved in 04/2014. Location permit was approved in 09/2015. Accordingly to the specific phase of the projects permits will be modified/ obtained.
LNG Terminal |  | LNG-N-082 | LNG terminal Krk | LNG Hrvatska d.o.o. za poslovanje ukapljenim prirodnim plinom |  | Political | Project named LNG terminal on the Island of Krk was declared on Government of Republic of Croatia session from 16th of July 2015 a project of strategic importance for the Republic of Croatia. The Act on strategic investments enables this kind of projects to have the highest priority with faster and simplified procedure in obtaining necessary documents and permits for the project implementation.
LNG Terminal |  | LNG-N-082 | LNG terminal Krk | LNG Hrvatska d.o.o. za poslovanje ukapljenim prirodnim plinom |  | Regulatory | National Regulatory Agency needs to approve missing regulatory framework for liquefied natural gas i.e. methodology for determination of tariff for receiving LNG and gas send-out. In order for the project to be implemented on time, when the CBA/CBCA request is submitted to the Croatian NRA all of the relevant NRA's (six identified countries) need to come to a fast decision.
Pipeline including CS |  | TRA-N-099 | M3/1a Šempeter - Ajdovščina | Plinovodi d.o.o. |  | Permit Granting | Long lasting and complicated procedures of Spatial planning (National Spatial Plan, SEA and EIA procedures, Environmental consent) as well as the procedure of acquiring the Construction permit (long procedures for land acquisition, etc.)
Pipeline including CS |  | TRA-N-262 | M3/1b Ajdovščina - Kalce | Plinovodi d.o.o. |  | Permit Granting | Long lasting and complicated procedures of Spatial planning (National Spatial Plan, SEA and EIA procedures, Environmental consent) as well as the procedure of acquiring the Construction permit (long procedures for land acquisition, etc.)
Pipeline including CS |  | TRA-N-261 | M3/1c Kalce - Vodice | Plinovodi d.o.o. |  | Permit Granting | Long lasting and complicated procedures of Spatial planning (National Spatial Plan, SEA and EIA procedures, Environmental consent) as well as the procedure of acquiring the Construction permit (long procedures for land acquisition, etc.)
Pipeline including CS |  | TRA-N-101 | M8 Kalce - Jelšane | Plinovodi d.o.o. |  | Permit Granting | Long lasting and complicated procedures of Spatial planning (National Spatial Plan, SEA and EIA procedures, Environmental consent) as well as the procedure of acquiring the Construction permit (long procedures for land acquisition, etc.)
Pipeline including CS |  | TRA-N-1090 | Metering and Regulating Station at Alexandroupoli | DESFA S.A. |  | Market | Lack of market maturity
Pipeline including CS |  | TRA-N-1091 | Metering and Regulating station at Megalopoli | DESFA S.A. |  | Market | Lack of market maturity
Pipeline including CS |  | TRA-N-1092 | Metering and Regulating Station at UGS South Kavala | DESFA S.A. |  | Market | Lack of market maturity
LNG Terminal |  | LNG-N-225 | Montoir LNG Terminal Expansion | Elengy |  | Political | Discrimination aiming at preventing the project to be recognized as an efficient alternative to a third gas pipeline through the Pyreneans.
LNG Terminal |  | LNG-N-296 | Mugardos LNG Terminal: 2nd Jetty | Reganosa |  | Market | Lack of market maturity
LNG Terminal |  | LNG-N-295 | Mugardos LNG Terminal: Send-out Increase | Reganosa |  | Market | Lack of market maturity
LNG Terminal |  | LNG-N-297 | Mugardos LNG Terminal: Storage Extension | Reganosa |  | Market | Lack of market maturity
Pipeline including CS |  | TRA-N-967 | Nea-Messimvria to FYROM pipeline | DESFA S.A. |  | Market | Lack of market maturity
Pipeline including CS |  | TRA-N-964 | New NTS developments for taking over gas from the Black Sea shore | SNTGN Transgaz SA |  | Financing | Availability of funds and associated conditions
Storage Facility |  | UGS-N-366 | New undergound gas storage in Romania | Societatea Naţională de Gaze Naturale ROMGAZ S.A. |  | Financing | Amortization rates
Storage Facility |  | UGS-N-366 | New undergound gas storage in Romania | Societatea Naţională de Gaze Naturale ROMGAZ S.A. |  | Market | Lack of market maturity
Storage Facility |  | UGS-N-366 | New undergound gas storage in Romania | Societatea Naţională de Gaze Naturale ROMGAZ S.A. |  | Market | Lack of market support
Storage Facility |  | UGS-N-366 | New undergound gas storage in Romania | Societatea Naţională de Gaze Naturale ROMGAZ S.A. |  | Regulatory | - no negotiated tariffs - no daily/weekly balance reports
Storage Facility |  | UGS-N-366 | New undergound gas storage in Romania | Societatea Naţională de Gaze Naturale ROMGAZ S.A. |  | Regulatory | Low or zero-priced short-term capacity
Storage Facility |  | UGS-N-366 | New undergound gas storage in Romania | Societatea Naţională de Gaze Naturale ROMGAZ S.A. |  | Regulatory | Low rate of return
Pipeline including CS |  | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. |  | Financing | Due to the project drivers which are mainly related to SoS in Central-Eastern Europe, the project does not meet the criterion of economic viability, so the external co-financing is indispensable. Lack of external financial support may be a serious barrier in implementation.
Pipeline including CS |  | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. |  | Others | Due to the project drivers which are mainly related to SoS in Central-Eastern Europe, the project does not meet the criterion of economic viability, so the external co-financing is indispensable. Lack of external financial support may be a serious barrier in implementation.
Pipeline including CS |  | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. |  | Permit Granting | Efficient permitting procedures are necessary for timely implementation of the project.
Pipeline including CS |  | TRA-N-247 | North - South Gas Corridor in Western Poland | GAZ-SYSTEM S.A. |  | Others | Due to the project drivers which are mainly related to SoS in Central-Eastern Europe, the project does not meet the criterion of economic viability, so the external co-financing is indispensable. Lack of external financial support may be a serious barrier in implementation.
Pipeline including CS |  | TRA-N-247 | North - South Gas Corridor in Western Poland | GAZ-SYSTEM S.A. |  | Permit Granting | Efficient permitting procedures are necessary for timely implementation of the Project.
Pipeline including CS |  | TRA-N-357 | NTS developments in North-East Romania | SNTGN Transgaz SA |  | Financing | Availability of funds and associated conditions
Pipeline including CS |  | TRA-N-357 | NTS developments in North-East Romania | SNTGN Transgaz SA |  | Permit Granting | The permitting process is long and complicated
Pipeline including CS |  | TRA-N-357 | NTS developments in North-East Romania | SNTGN Transgaz SA |  | Political | Area with potential conflicts Requires the conclusion of an Intergovernmental Agreement
Storage Facility |  | UGS-N-235 | Nuovi Sviluppi Edison Stoccaggio | Edison Stoccaggio S.p.A |  | Permit Granting | Local permitting
Storage Facility |  | UGS-N-235 | Nuovi Sviluppi Edison Stoccaggio | Edison Stoccaggio S.p.A |  | Regulatory | Authority has set a new regulation to boost the increase of withdrawal capacity.
Storage Facility |  | UGS-N-237 | Palazzo Moroni | Edison Stoccaggio S.p.A |  | Permit Granting | Delays with local permitting. The project has already achieved important autorization such as EIA and Seveso.
Storage Facility |  | UGS-N-237 | Palazzo Moroni | Edison Stoccaggio S.p.A |  | Regulatory | Authority has set a new regulatory framework for 2015-2018, which was really different from the previous. In 2018 the Authority will set the new framework for 2019-2022.
LNG Terminal |  | LNG-N-079 | Paldiski LNG Terminal | Balti Gaas plc |  | Financing | Amortization rates
LNG Terminal |  | LNG-N-079 | Paldiski LNG Terminal | Balti Gaas plc |  | Market | Lack of market maturity
LNG Terminal |  | LNG-N-079 | Paldiski LNG Terminal | Balti Gaas plc |  | Permit Granting | Long process
LNG Terminal |  | LNG-N-079 | Paldiski LNG Terminal | Balti Gaas plc |  | Political | ​The assesment methods of competing PCI projects is not well established.
LNG Terminal |  | LNG-N-079 | Paldiski LNG Terminal | Balti Gaas plc |  | Regulatory | ​Regulatory framework for LNG facilities in Estonia is insufficient to clarify this point.
LNG Terminal |  | LNG-N-079 | Paldiski LNG Terminal | Balti Gaas plc |  | Regulatory | Lack of proper transposition of EU regulation
Pipeline including CS |  | TRA-N-273 | Poland - Czech Republic interconnection (PL section) | GAZ-SYSTEM S.A. |  | Others | Due to the project drivers which are mainly related to SoS in Central-Eastern Europe, the project does not meet the criterion of economic viability, so the external co-financing is indispensable. Lack of external financial support may be a serious barrier in implementation.
Pipeline including CS |  | TRA-N-273 | Poland - Czech Republic interconnection (PL section) | GAZ-SYSTEM S.A. |  | Permit Granting | Efficient permitting procedures are necessary for timely implementation of the project.
Pipeline including CS |  | TRA-N-273 | Poland - Czech Republic interconnection (PL section) | GAZ-SYSTEM S.A. |  | Political | Due to the project drivers which are mainly related to SoS in Central-Eastern Europe, the project does not meet the criterion of economic viability, so the external co-financing is indispensable. Lack of external financial support may be a serious barrier in implementation.
Pipeline including CS |  | TRA-N-271 | Poland - Denmark interconnection (Baltic Pipe) - PL section | GAZ-SYSTEM S.A. |  | Others | There is a lack of confidence and risk-taking in the private gas sector to the Baltic Pipe project, as it requires coordinated long term business cases, fundamental change in current business models/susbisdies and involves many parties from at least three countries (PL, DK, NO). Granting the EU priority for the project and a grant to the Polish and Danish TSOs may well accelerate the implementation of the project.
Pipeline including CS |  | TRA-N-271 | Poland - Denmark interconnection (Baltic Pipe) - PL section | GAZ-SYSTEM S.A. |  | Permit Granting | Efficient permitting procedures are necessary for timely implementation of the project.
Pipeline including CS |  | TRA-N-190 | Poland - Slovakia interconnection | eustream, a.s. |  | Financing | Availability of funds and associated conditions
Pipeline including CS |  | TRA-N-190 | Poland - Slovakia interconnection | eustream, a.s. |  | Market | Lack of market support
Pipeline including CS |  | TRA-N-190 | Poland - Slovakia interconnection | eustream, a.s. |  | Regulatory | Low rate of return
Pipeline including CS |  | TRA-N-275 | Poland - Slovakia interconnection (PL section) | GAZ-SYSTEM S.A. |  | Others | Due to the project drivers which are mainly related to SoS in Central-Eastern Europe, the project does not meet the criterion of economic viability, so the external co-financing is indispensable. Lack of external financial support may be a serious barrier in implementation.
Pipeline including CS |  | TRA-N-275 | Poland - Slovakia interconnection (PL section) | GAZ-SYSTEM S.A. |  | Permit Granting | Efficient permitting procedures are necessary for timely implementation of the Project.
Pipeline including CS |  | TRA-N-275 | Poland - Slovakia interconnection (PL section) | GAZ-SYSTEM S.A. |  | Political | Due to the project drivers which are mainly related to SoS in Central-Eastern Europe, the project does not meet the criterion of economic viability, so the external co-financing is indispensable. Lack of external financial support may be a serious barrier in implementation.
LNG Terminal |  | LNG-N-198 | Porto Empedocle LNG | Nuove Energie S.r.l. |  | Financing | in the current italian market context, the PCI project status would help to finance the project
Pipeline including CS |  | TRA-N-010 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A |  | Others | Poseidon Pipeline was initially conceived to transport gas from the Azeri Shah Deniz 2 field. Following the selection of TAP by the SD2 Consortium, IGI Poseidon is in the process of securing new sources, while maintaining the project's objectives to diversify sources, rotues and counterparts.
Pipeline including CS |  | TRA-N-010 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A |  | Permit Granting | The major permits for Poseidon Pipeline have been obtained including the EIA in both Italy and Greece and no significant barriers are foreseen for the remaining permits.
Pipeline including CS |  | TRA-N-010 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A |  | Political | Poseidon Pipeline has been consistently supported by the Greek and Italian Governments.
LNG Terminal |  | LNG-N-032 | Project GO4LNG LNG terminal Gothenburg | Swedegas AB |  | Market | Lack of market support
LNG Terminal |  | LNG-N-032 | Project GO4LNG LNG terminal Gothenburg | Swedegas AB |  | Permit Granting | Permits obtained
LNG Terminal |  | LNG-N-032 | Project GO4LNG LNG terminal Gothenburg | Swedegas AB |  | Regulatory | ​Small scale LNG is an emerging market with no mature trade patterns which make it difficult to combine capacity holders in a cost-efficient way - given a low rate of return.
LNG Terminal |  | LNG-N-032 | Project GO4LNG LNG terminal Gothenburg | Swedegas AB |  | Regulatory | Low rate of return
Pipeline including CS |  | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Plinovodi d.o.o. |  | Permit Granting | Long lasting and complicated procedures of Spatial planning (National Spatial Plan, SEA and EIA procedures, Environmental consent) as well as the procedure of acquiring the Construction permit (long procedures for land acquisition, etc.)
Pipeline including CS |  | TRA-N-047 | Reverse capacity from France to Germany at Obergailbach | GRTgaz |  | Market | Lack of market support
Pipeline including CS |  | TRA-N-286 | Romanian-Hungarian reverse flow Hungarian section 1st stage | FGSZ Ltd. |  | Market | Lack of market support
Pipeline including CS |  | TRA-N-286 | Romanian-Hungarian reverse flow Hungarian section 1st stage | FGSZ Ltd. |  | Regulatory | Low rate of return
Pipeline including CS |  | TRA-N-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | FGSZ Ltd. |  | Market | Lack of market support
Pipeline including CS |  | TRA-N-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | FGSZ Ltd. |  | Regulatory | Low rate of return
Pipeline including CS |  | TRA-N-975 | Sardinia Gas Transportation Network | Società Gasdotti Italia |  | Others | Time-table of the project can be affected by the effective realization of LNG Terminals
Pipeline including CS |  | TRA-N-975 | Sardinia Gas Transportation Network | Società Gasdotti Italia |  | Regulatory | NRA to clarify: 1) that Tariff Regime applicable in mainland Italy is also applicable on Sardinia gas network development, irrespective of its physical connection with Italy's Network; 2) Tariff and TPA Regime for SSLNG (this only indirectly relevant to onshore network)
Storage Facility |  | UGS-N-371 | Sarmasel undeground gas storage in Romania | Societatea Naţională de Gaze Naturale ROMGAZ S.A. |  | Financing | Amortization rates
Storage Facility |  | UGS-N-371 | Sarmasel undeground gas storage in Romania | Societatea Naţională de Gaze Naturale ROMGAZ S.A. |  | Market | Lack of market maturity
Storage Facility |  | UGS-N-371 | Sarmasel undeground gas storage in Romania | Societatea Naţională de Gaze Naturale ROMGAZ S.A. |  | Market | Lack of market support
Storage Facility |  | UGS-N-371 | Sarmasel undeground gas storage in Romania | Societatea Naţională de Gaze Naturale ROMGAZ S.A. |  | Regulatory | - no negotiated tariffs - no daily/weekly balance reports
Storage Facility |  | UGS-N-371 | Sarmasel undeground gas storage in Romania | Societatea Naţională de Gaze Naturale ROMGAZ S.A. |  | Regulatory | Low or zero-priced short-term capacity
Storage Facility |  | UGS-N-371 | Sarmasel undeground gas storage in Romania | Societatea Naţională de Gaze Naturale ROMGAZ S.A. |  | Regulatory | Low rate of return
LNG Terminal |  | LNG-N-912 | Skulte LNG | AS Skulte LNG Terminal |  | Financing | Availability of funds and associated conditions
LNG Terminal |  | LNG-N-912 | Skulte LNG | AS Skulte LNG Terminal |  | Market | Lack of market maturity
LNG Terminal |  | LNG-N-912 | Skulte LNG | AS Skulte LNG Terminal |  | Regulatory | Low rate of return
Pipeline including CS |  | TRA-N-1138 | South Caucasus Pipeline Future Expansion - SCPFX | SOCAR Midstream Operations LLC |  | Financing | Availability of funds and associated conditions
Pipeline including CS |  | TRA-N-1138 | South Caucasus Pipeline Future Expansion - SCPFX | SOCAR Midstream Operations LLC |  | Others | Market uncertainty and volume commitment by producers
Storage Facility |  | UGS-N-385 | South Kavala Underground Gas Storage facility | Hellenic Republic Asset anagement Fund |  | Market | Lack of market maturity
Pipeline including CS |  | TRA-N-161 | South Transit East Pyrenees (STEP) - ENAGAS | Enagás Transporte, S.A.U. |  | Market | In the Open Season launched in 2010 between Spain and France MidCat didn't obtain enough market support .
Pipeline including CS |  | TRA-N-161 | South Transit East Pyrenees (STEP) - ENAGAS | Enagás Transporte, S.A.U. |  | Market | Lack of market support
Pipeline including CS |  | TRA-N-161 | South Transit East Pyrenees (STEP) - ENAGAS | Enagás Transporte, S.A.U. |  | Regulatory | In 2010, Enagás, TIGF and GRTgaz carried out an OS to ask for binding commitments for capacities provided by MidCat and/or Irún/Biriatou and GRTgaz North-South link. Concerning MidCat, none of the three proposed infrastructure scenarios received enough bids to be triggered. This OS is currently the latest call made to the market regarding MidCat.However, MidCat has demonstrated benefits in terms of market integration (price convergence), security of supply and diversification of supply.Taking into account that the OS2015 was carried out in a context of economic prosperity in comparison with the current situation jointly with the new endency in contracting capacity (from long term to short term) well as the decrease in gas consumption, it is not foreseen that network users would make enough long-term commitments in order to fully cover the investment. Besides, recent changes in the Spanish regulatory framework would not contribute to have an appropriate rate of return of the investments
Pipeline including CS |  | TRA-N-161 | South Transit East Pyrenees (STEP) - ENAGAS | Enagás Transporte, S.A.U. |  | Regulatory | Low rate of return
Pipeline including CS |  | TRA-N-252 | South Transit East Pyrenees (STEP) - TIGF | TIGF |  | Market | Lack of market support
Pipeline including CS |  | TRA-N-851 | Southern Interconnection pipeline BiH/CRO | BH-GAS d.o.o. |  | Financing | Availability of funds and associated conditions
Pipeline including CS |  | TRA-N-851 | Southern Interconnection pipeline BiH/CRO | BH-GAS d.o.o. |  | Market | Lack of market support
Pipeline including CS |  | TRA-N-851 | Southern Interconnection pipeline BiH/CRO | BH-GAS d.o.o. |  | Political | Lack of primary gas legislation in accordance with Third Energy Package, as well as energy policy at the state level.
Pipeline including CS |  | TRA-N-851 | Southern Interconnection pipeline BiH/CRO | BH-GAS d.o.o. |  | Regulatory | Lack of proper transposition of EU regulation
Storage Facility |  | UGS-N-034 | Syderiai | JSC Lietuvos energija AB |  | Financing | Availability of funds and associated conditions
Storage Facility |  | UGS-N-034 | Syderiai | JSC Lietuvos energija AB |  | Market | Lack of market maturity
Storage Facility |  | UGS-N-034 | Syderiai | JSC Lietuvos energija AB |  | Market | Lack of market support
Storage Facility |  | UGS-N-034 | Syderiai | JSC Lietuvos energija AB |  | Others | High investment costs, unclear payback potential, necessity of implementation of Lithuanian-Polish gas interconnection (GIPL) project.
Storage Facility |  | UGS-N-034 | Syderiai | JSC Lietuvos energija AB |  | Regulatory | Low rate of return
LNG Terminal |  | LNG-N-962 | Tallinn LNG | Vopak E.O.S. AS / Vopak LNG Holdings B.V/ Port of Tallinn AS |  | Market | Lack of market maturity
Pipeline including CS |  | TRA-F-221 | TANAP - Trans Anatolian Natural Gas Pipeline Project | SOCAR (The State Oil Company of the Azerbaijan Republic) |  | Financing | Availability of funds and associated conditions
Pipeline including CS |  | TRA-F-221 | TANAP - Trans Anatolian Natural Gas Pipeline Project | SOCAR (The State Oil Company of the Azerbaijan Republic) |  | Financing | Low oil prices in the world, which constitute the income of TANAP's major shareholder SGC, leads to difficulties on TANAP's financing
Pipeline including CS |  | TRA-N-339 | Trans-Caspian | W-Stream Caspian Pipeline Company Ltd |  | Regulatory | Lack of proper transposition of EU regulation
Storage Facility |  | UGS-N-127 | Underground Gas Storage in salt leached caverns in the Bages area (ES) | Gas Natural |  | Permit Granting | Long timig administrative and environmental permitting process, several Administrations involved with not well defined competence distribution lead to incertitude of obtaining all the authorisations required
Storage Facility |  | UGS-N-127 | Underground Gas Storage in salt leached caverns in the Bages area (ES) | Gas Natural |  | Political | Various Administrations involved (starte, regional and local) with different political composition and having differnet competences/opinions about the benefits and withdrawals of the Project
LNG Terminal |  | LNG-N-272 | Upgrade of LNG terminal in Świnoujście | GAZ-SYSTEM S.A. |  | Others | Possible lack of risk-taking in the private gas sector which would result in insufficient long term committments to enable the investment decision for the infrastructure operator. It could be mitgated by external susbisdies (EU) to cover positive externalities such as SoS, positive environmental impact (reduction of emissions due to fuel change in maritime transport) and supply diversification in the Baltic area and the CEE region (including Ukraine).
LNG Terminal |  | LNG-N-272 | Upgrade of LNG terminal in Świnoujście | GAZ-SYSTEM S.A. |  | Permit Granting | Efficient permitting procedures are necessary for timely implementation of the project.
Pipeline including CS |  | TRA-N-123 | Városföld CS | FGSZ Ltd. |  | Market | Lack of market support
Pipeline including CS |  | TRA-N-123 | Városföld CS | FGSZ Ltd. |  | Regulatory | Low rate of return
Pipeline including CS |  | TRA-N-018 | Városföld-Ercsi-Győr | FGSZ Ltd. |  | Market | Lack of market maturity
Pipeline including CS |  | TRA-N-018 | Városföld-Ercsi-Győr | FGSZ Ltd. |  | Market | Lack of market support
Pipeline including CS |  | TRA-N-018 | Városföld-Ercsi-Győr | FGSZ Ltd. |  | Regulatory | Low rate of return
Pipeline including CS |  | TRA-N-910 | Western interconnection BiH/CRO | BH-Gas d.o.o. |  | Financing | Availability of funds and associated conditions
Pipeline including CS |  | TRA-N-910 | Western interconnection BiH/CRO | BH-Gas d.o.o. |  | Market | Lack of market support
Pipeline including CS |  | TRA-N-910 | Western interconnection BiH/CRO | BH-Gas d.o.o. |  | Political | Lack of primary gas legislation in accordance with Third Energy Package, as well as energy policy at the state level.
Pipeline including CS |  | TRA-N-910 | Western interconnection BiH/CRO | BH-Gas d.o.o. |  | Regulatory | Lack of proper transposition of EU regulation

## Third-Party Access Exemptions
| TYNDP Annex A |  |  |  | Third-Party Access Exemptions - Page 8
Projects Having Applied for Third-Party Access Exemptions
Project Type |  | Code | Name | Promoter |  | Applied For Exemption | Exemption Granted | Exemption Stage Reached | Exempted % Entry | Exempted % Exit | Tariff Regime | TPA Regime Comments
Pipeline including CS |  | TRA-N-428 | (Mirror) Baltic Pipe | Energinet.dk |  | Yes | Yes |  | 0% | 0% | Regulated
Pipeline including CS |  | TRA-F-1028 | Albania - Kosovo Gas Pipeline | Min. of Energy and Industry of AL & Min. of Economic Development of KO |  | Yes | Yes |  | 0% | 0% | Regulated
Pipeline including CS |  | TRA-N-825 | Compressor station "Legden" | Open Grid Europe GmbH |  | Yes | Yes |  | 0% | 0% | Regulated
Pipeline including CS |  | TRA-N-636 | Development of Transmission Capacity at Slovak-Hungarian interconnector | Magyar Gáz Tranzit Zrt. |  | Yes | Yes |  | 0% | 0% | Regulated
Pipeline including CS |  | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | Magyar Gáz Tranzit Zrt. |  | Yes | No |  | 0% | 0% | Regulated
LNG Terminal |  | LNG-N-050 | Gate terminal phase 3 | Gate |  | Yes | Yes |  | 0% | 100% | Not Applicable | The exemption was applied for in March 2006; the exemption has been granted by the Dutch Minister on 14 July 2007; the EC gave its approval on 2 October 2007. Was not sure what to fill in regulated or negotiated. It is exempted
Pipeline including CS |  | TRA-N-423 | GCA Mosonmagyaróvár | GAS CONNECT AUSTRIA GmbH |  | Yes | Yes |  | 0% | 0% | Regulated
Pipeline including CS |  | TRA-N-965 | Interconnection Macedonia-Serbia | MER JSC Skopje |  | Yes | Not Relevant |  | 0% | 0% | Regulated | The transmission tariff will be regulated according to EU regulations.
Pipeline including CS |  | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | ICGB a.d. |  | Yes | Not Yet | Binding Phase of Market Test under par.6, art.36, Directive 2009/73. | 0% | 0% | Not Applicable
Pipeline including CS |  | TRA-N-1092 | Metering and Regulating Station at UGS South Kavala | DESFA S.A. |  | Yes | Yes |  | 0% | 0% | Regulated
Pipeline including CS |  | TRA-N-957 | Metering Station at Komotini to IGB | DESFA S.A. |  | Yes | Yes |  | 0% | 0% | Regulated
Pipeline including CS |  | TRA-N-967 | Nea-Messimvria to FYROM pipeline | DESFA S.A. |  | Yes | Yes |  | 0% | 0% | Regulated
Pipeline including CS |  | TRA-N-780 | Nybro-Interconnector PL-DK - reinforcement | Energinet.dk |  | Yes | Yes |  | 0% | 0% | Regulated
Pipeline including CS |  | TRA-N-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Gastransport Nord GmbH |  | Yes | Yes |  | 0% | 0% | Regulated
LNG Terminal |  | LNG-N-198 | Porto Empedocle LNG | Nuove Energie S.r.l. |  | Yes | Yes | Exemption has been granted | 100% | 100% | Negotiated | The TPA exemption has been granted as per EC Decision issued on 7.5.2012 and Italian Ministry of Economic Development Decree issued on June 6th, 2012. Nuove Energie is currently evaluating the possibility to revise its initial position of full TPA exemption.
Pipeline including CS |  | TRA-N-010 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A |  | Yes | Yes |  | 0% | 89% | Not Applicable | The exempted capacity is only relative to the forward flow capacity from Greece to Italy.
LNG Terminal |  | LNG-N-030 | Shannon LNG Terminal and Connecting Pipeline | Shannon LNG |  | Yes | Yes |  | 0% | 0% | Negotiated
Pipeline including CS |  | TRA-F-051 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG |  | Yes | Yes | Exemption has been granted by the relevant regulatory authorities and the Commission. The start of the Exemption period coincides with the start of commercial operations of TAP | 100% | 100% | Negotiated | Initial Capacity exempted from third party access. Expansion Capacity is subject to third party access and will be offered to the market via market tests, fromm no later than start of operations and subsequently every two years.
Pipeline including CS |  | TRA-N-831 | Vecsés-Városföld gas transit pipeline | Magyar Gáz Tranzit Zrt. |  | Yes | Yes |  | 0% | 0% | Regulated
Pipeline including CS |  | TRA-F-753 | West to East operation of the IP Waidhaus | GRTgaz Deutschland GmbH |  | Yes | Yes |  | 0% | 0% | Regulated

## Intergovernmental Agreements
| TYNDP Annex A |  |  |  | Intergovernmental Agreements - Page 9
Intergovernmental Agreements
Project Type |  | Code | Name | Promoter |  | Agreement | Signed | Signature Date | Description
LNG Terminal |  | LNG-N-328 | Eagle LNG and Pipeline | Trans-European Energy B.V., Sh.A |  | Italy-Albania | Yes | 2016-05-26 | Agreement on gas and power infrastructure integration
Pipeline including CS |  | TRA-N-965 | Interconnection Macedonia-Serbia | MER JSC Skopje |  | Memorandum of understanding between Macedonia and Serbia | No | 2016-05-18
Pipeline including CS |  | TRA-N-976 | Interconnection Macedonia-Bulgaria | MER JSC Skopje |  | Memorandum of understanding between Macedonia and Bulgaria | No | 2016-05-18
Pipeline including CS |  | TRA-N-980 | Interconnection Macedonia-Greece | MER JSC Skopje |  | Memorandum of understanding between DESFA S.A. and MER JSC Skopje | No | 2016-05-18
Pipeline including CS |  | TRA-N-998 | Interconnection Macedonia-Albania | MER JSC Skopje |  | Memorandum of understanding between Macedonia and Albania | No | 2016-05-18
LNG Terminal |  | LNG-N-082 | LNG terminal in Croatia | LNG Croatia Ltd. |  | CESEC MoU | Yes | 2015-07-10 | Memorandum of Understanding
Pipeline including CS |  | TRA-N-161 | Iberian-French corridor: Eastern Axis - Midcat Project | Enagás S.A. |  | Madrid Declaration | Yes | 2015-03-04 | Commission, France, Portugal and Spain sign High Level Group agreement to break energy barriers
Pipeline including CS |  | TRA-N-168 | Interconnection ES-PT (3rd IP) | Enagás S.A. |  | Madrid Declaration | Yes | 2015-03-04 | Commission, France, Portugal and Spain sign High Level Group agreement to break energy barriers
Pipeline including CS |  | TRA-N-727 | Iberian‐French corridor: Eastern Axis ‐ Midcat Project ‐ 2nd Phase | Enagas Transporte, S.A.U. |  | Madrid Declaration | Yes | 2015-03-04 | Commission, France, Portugal and Spain sign High Level Group agreement to break energy barriers
Pipeline including CS |  | TRA-N-729 | Interconnection ES-PT (3rd IP) - 2nd phase | Enagas Transporte, S.A.U. |  | Madrid Declaration | Yes | 2015-03-04 | Commission, France, Portugal and Spain sign High Level Group agreement to break energy barriers
Pipeline including CS |  | TRA-N-086 | Interconnection Croatia/Slovenia (Bosiljevo - Karlovac - Lučko - Zabok - Rogatec) | Plinacro Ltd |  | Memorandum of Understanding | Yes | 2014-12-28 | Signed among Plinacro, Plinovodi and Gas Connect Austria
LNG Terminal |  | LNG-N-079 | Paldiski LNG Terminal | Balti Gaas OÜ |  | Agreement between PMs of Estonia and Finland | Yes | 2014-11-17 | Agreement in regards to the gas infrastructure in the countries.
Pipeline including CS |  | TRA-N-275 | Poland - Slovakia interconnection within the North - South corridor | Operator Gazociągów Przesyłowych Gaz-System S.A. |  | Agreement between the Government of the Republic of Poland and the Government of the Slovak Republic for cooperation on the implementation of the project of a gas pipeline connecting the Polish transmission system and Slovak transmission system. | Yes | 2014-06-11 | In Comments
Pipeline including CS |  | TRA-N-086 | Interconnection Croatia/Slovenia (Bosiljevo - Karlovac - Lučko - Zabok - Rogatec) | Plinacro Ltd |  | Letter of Intent | Yes | 2014-05-22 | Signed between Plinacro and Plinovodi
Pipeline including CS |  | TRA-N-043 | Val de Saône project | GRTgaz |  | Cross border cost allocation | Yes | 2014-04-10 | Decision from CRE and CNMC on the request for cross order cost allocation between France and Spain for the project of common interest Val de Saône
Pipeline including CS |  | TRA-N-140 | Interconnection Turkey-Bulgaria | Bulgartransgaz EAD |  | Memorandum of Understanding | Yes | 2014-03-28 | a Memorandum of Understanding between the Ministry of Economy and Energy of the Republic of Bulgaria and the Ministry of Energy and Natural Resources of the Republic of Turkey, concerning ITB project
LNG Terminal |  | LNG-N-079 | Paldiski LNG Terminal | Balti Gaas OÜ |  | Memorandum of Understanding | Yes | 2014-02-28 | MoU between Estonia and Finland and LNG project promoters
Pipeline including CS |  | TRA-N-068 | Ionian Adriatic Pipeline | Plinacro Ltd |  | Agreement to extend the Memorandum of Understanding | Yes | 2014-02-25 | Signed between Plinacro and TAP
Pipeline including CS |  | TRA-N-190 | Poland - Slovakia interconnection | eustream, a.s. |  | Agreement between the Government of the Slovak Republic and the Government of the Republic of Poland for cooperation on the implementation of the project of a gas pipeline connecting the Slovak transmission system and Polish transmission system | Yes | 2013-11-22 | Intergovernmental agreement
Pipeline including CS |  | TRA-F-051 | Trans Adriatic Pipeline | Trans-Adriatic Pipeline AG |  | Host-government agreement between TAP and Greece | Yes | 2013-06-26 | The HGA is designed to fill legal, regulatory and fiscal caviats to mitigate commercial risks and thereby provide the necessary investor protection to ensure that the project is built and enable construction and operation in accordance with high standards
Pipeline including CS |  | TRA-F-051 | Trans Adriatic Pipeline | Trans-Adriatic Pipeline AG |  | Host-government agreement between TAP and Albania | Yes | 2013-04-05 | The HGA is designed to fill legal, regulatory and fiscal caviats to mitigate commercial risks and thereby provide the necessary investor protection to ensure that the project is built and enable construction and operation in accordance with high standards
Pipeline including CS |  | TRA-F-051 | Trans Adriatic Pipeline | Trans-Adriatic Pipeline AG |  | Inter-governmental Agreements (only applicable for import pipeline projects | Yes | 2013-02-13 | An IGA between Italy, Greece and Albania has formalized the state parties’ support for the TAP project, ensure cross-country harmonization of standards in order to facilitate the implementation of TAP and provide the necessary investor protection measure
Pipeline including CS |  | TRA-F-051 | Trans Adriatic Pipeline | Trans-Adriatic Pipeline AG |  | Inter-ministerial agreement between Italy, Albania and Greece | Yes | 2012-09-27 | An inter-ministerial agreement between Italy, Albania and Greece is required under Italian law to commence the TPA exemption application process in Italy.
Pipeline including CS |  | TRA-F-221 | TANAP - Trans Anatolian Natural Gas Pipeline Project | Socar |  | Intergovernmental Agreement between Turkey and Azerbaijan | Yes | 2012-06-26 | Intergovernmental Agreement (IGA) between the Government of the Republic of Turkey and the Government of the Republic of Azerbaijan Concerning the Trans Anatolian Natural Gas Pipeline System
Pipeline including CS |  | TRA-N-140 | Interconnection Turkey-Bulgaria | Bulgartransgaz EAD |  | Joint Declaration of the Minister of Energy and Natural Resources of the Republic of Turkey and the Minister of Economy, Energy and Tourism of the Republic of Bulgaria on Energy Cooperation | Yes | 2012-03-20 | Declarationon Energy Cooperation
Pipeline including CS |  | TRA-N-066 | Interconnection Croatia/Bosnia and Herzegovina (Slobodnica- Bosanski Brod-Zenica) | Plinacro Ltd |  | Letter of Intent | Yes | 2011-04-06 | between Plinacro and BH Gas for all projects of interconnection
Pipeline including CS |  | TRA-N-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | Plinacro Ltd |  | Letter of Intent | Yes | 2011-04-06 | between Plinacro and BH Gas for all projects of interconnection
Pipeline including CS |  | TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (Licka Jesenica-Rakovica-Trzac-Bosanska Krupa with branches to Bihać and Velika Kladusa) | Plinacro Ltd |  | Letter of Intent | Yes | 2011-04-06 | between Plinacro and BH Gas for all projects of interconnection
Pipeline including CS |  | TRA-N-068 | Ionian Adriatic Pipeline | Plinacro Ltd |  | Memorandum of Understanding | Yes | 2011-02-05 | Signed between Plinacro and TAP
Pipeline including CS |  | TRA-N-010 | Poseidon Pipeline | IGI Poseidon S.A. |  | Memorandum of Understanding between Greece and Turkey | Yes | 2010-05-01
Pipeline including CS |  | TRA-N-137 | Interconnection Bulgaria - Serbia | Bulgarian Ministry of Economy and energy |  | Joint statement by Bulgaria and Serbia | Yes | 2010-03-05 | Joint statement signed in Brussels by Bulgaria and Serbia in 2010
Pipeline including CS |  | TRA-N-140 | Interconnection Turkey-Bulgaria | Bulgartransgaz EAD |  | Memorandum of Understanding between the Ministry of Economy, Energy and Tourism of the Republic of Bulgaria and the Ministry of Energy and Natural Resources of the Republic of Turkey on Comprehensive Cooperation in the Field of Energy | Yes | 2010-01-29 | Memorandum of Understandingon Comprehensive Cooperation in the Field of Energy
Pipeline including CS |  | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Plinovodi d.o.o. |  | Memorandum of Understanding (MOU) | Yes | 2009-11-27
Pipeline including CS |  | TRA-N-010 | Poseidon Pipeline | IGI Poseidon S.A. |  | Joint statement of the Italian Minister of Economic Development and the Turkish Minister of Energy and Natural Resources | Yes | 2009-11-01
Pipeline including CS |  | TRA-N-010 | Poseidon Pipeline | IGI Poseidon S.A. |  | Protocol of Cooperation between Italy and Azerbaijan | Yes | 2007-12-01
Pipeline including CS |  | TRA-N-012 | GALSI Pipeline Project | Galsi S.p.A. |  | Italy – Algeria Inter-Governmental Agreement for Galsi project | Yes | 2007-11-14 | Agreement between Italy and Algeria to promote and support the permitting, the construction and the commissioning of the Galsi Pipeline Project.
Pipeline including CS |  | TRA-N-068 | Ionian Adriatic Pipeline | Plinacro Ltd |  | Ministerial declaration | Yes | 2007-09-27 | signed by the Ministries of enegry of Albania, Montenegro and Croatia, from dezember 2008, Bosnia and Herzegovina signed as well
Pipeline including CS |  | TRA-N-010 | Poseidon Pipeline | IGI Poseidon S.A. |  | Italy‐Greece‐Turkey Intergovernmental Agreement | Yes | 2007-07-01
Pipeline including CS |  | TRA-N-066 | Interconnection Croatia/Bosnia and Herzegovina (Slobodnica- Bosanski Brod-Zenica) | Plinacro Ltd |  | Memorandum of understanding | Yes | 2006-06-26 | signed between Plinacro and BH Gas
Pipeline including CS |  | TRA-N-014 | Komotini-Thesprotia pipeline | DESFA S.A. |  | Intergovernmental Agreement between Greece and Italy for the implementation of the Interconnection Greece Italy. | Yes | 2005-11-04 | The Agreement was ratified by the Greek Parliament in 2006 (Law 3441/Government Gazette A’ 39/27.02.2006).
Pipeline including CS |  | TRA-N-010 | Poseidon Pipeline | IGI Poseidon S.A. |  | Italy‐Greece Intergovernmental Agreement | Yes | 2005-11-01
Pipeline including CS |  | TRA-N-137 | Interconnection Bulgaria - Serbia | Bulgarian Ministry of Economy and energy |  | Memorandum of Understanding between Bulgaria and Serbia | Yes | 2005-04-08 | Memorandum of Understanding signed in Sofia between Bulgaria and Serbia in 2005
Pipeline including CS |  | TRA-N-1138 | South Caucasus Pipeline Future Expansion - SCPFX | SOCAR Midstream Operations LLC |  | Intergovernmental Agreement between Azerbaijan and Georgia | Yes | 2002-04-17

## Enablers
| TYNDP Annex A |  |  |  | Enablers - Page 10
Enabler Projects
Enabler Project Type |  | Enabler Code | Enabler Project Name | Enabled Code |  | Enabled Project Name
Pipeline including CS |  | TRA-N-428 | (Mirror) Baltic Pipe | TRA-N-394 |  | Gassled - Danish upstream system
Pipeline including CS |  | TRA-N-428 | (Mirror) Baltic Pipe | TRA-N-780 |  | Nybro-Interconnector PL-DK - reinforcement
Pipeline including CS |  | TRA-N-284 | 3rd IP between Portugal and Spain (Compressor Station) | TRA-N-285 |  | 3rd IP between Portugal and Spain (pipeline Cantanhede-Mangualde)
Pipeline including CS |  | TRA-N-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | TRA-N-284 |  | 3rd IP between Portugal and Spain (Compressor Station)
Pipeline including CS |  | TRA-N-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | TRA-N-285 |  | 3rd IP between Portugal and Spain (pipeline Cantanhede-Mangualde)
Pipeline including CS |  | TRA-N-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | TRA-N-320 |  | Carregado Compressor Station
Pipeline including CS |  | TRA-N-380 | BG-RO-HU-AT transmission corridor | TRA-N-061 |  | Ercsi-Szazhalombatta
Pipeline including CS |  | TRA-N-380 | BG-RO-HU-AT transmission corridor | TRA-N-286 |  | Romanian-Hungarian reverse flow Hungarian section 1st stage
Pipeline including CS |  | TRA-N-380 | BG-RO-HU-AT transmission corridor | TRA-N-377 |  | Romanian-Hungarian reverse flow Hungarian section 2nd stage
Pipeline including CS |  | TRA-N-380 | BG-RO-HU-AT transmission corridor | TRA-N-123 |  | Városföld CS
Pipeline including CS |  | TRA-N-380 | BG-RO-HU-AT transmission corridor | TRA-N-018 |  | Városföld-Ercsi-Győr
Pipeline including CS |  | TRA-N-801 | Břeclav-Baumgarten Interconnection (BBI) AT | TRA-N-021 |  | Bidirectional Austrian-Czech Interconnector (BACI, formerly LBL project)
Pipeline including CS |  | TRA-N-919 | Capacity4Gas (C4G) – CZ/AT | TRA-N-133 |  | Bidirectional Austrian Czech Interconnection (BACI)
Pipeline including CS |  | TRA-N-320 | Carregado Compressor Station | TRA-N-284 |  | 3rd IP between Portugal and Spain (Compressor Station)
Pipeline including CS |  | TRA-N-320 | Carregado Compressor Station | TRA-N-285 |  | 3rd IP between Portugal and Spain (pipeline Cantanhede-Mangualde)
Pipeline including CS |  | TRA-N-320 | Carregado Compressor Station | TRA-N-283 |  | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border)
Pipeline including CS |  | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | TRA-N-066 |  | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod)
Pipeline including CS |  | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | TRA-N-070 |  | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo)
Pipeline including CS |  | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | TRA-F-86 |  | Interconnection Croatia/Slovenia (Lučko - Zabok - Rogatec)
Pipeline including CS |  | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | TRA-N-1058 |  | LNG Evacuation Pipeline Kozarac-Slobodnica
Pipeline including CS |  | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | TRA-N-90 |  | LNG evacuation pipeline Omišalj - Zlobin (Croatia)
Pipeline including CS |  | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | TRA-N-075 |  | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac
Pipeline including CS |  | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | TRA-F-334 |  | Compressor station 1 at the Croatian gas transmission system
Pipeline including CS |  | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | TRA-N-066 |  | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod)
Pipeline including CS |  | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | TRA-N-070 |  | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo)
Pipeline including CS |  | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | TRA-F-86 |  | Interconnection Croatia/Slovenia (Lučko - Zabok - Rogatec)
Pipeline including CS |  | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | TRA-N-075 |  | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac
Pipeline including CS |  | TRA-N-031 | Connection of Malta to the European Gas Network - Pipelines | LNG-N-211 |  | Connection of Malta to the European Gas Network - LNG Regasification
Pipeline including CS |  | TRA-N-092 | CS Ajdovščina, 1st phase of upgrade | TRA-N-108 |  | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia
Pipeline including CS |  | TRA-N-093 | CS Ajdovščina, 2nd phase of upgrade | TRA-N-099 |  | M3/1a Šempeter - Ajdovščina
Pipeline including CS |  | TRA-N-093 | CS Ajdovščina, 2nd phase of upgrade | TRA-N-262 |  | M3/1b Ajdovščina - Kalce
Pipeline including CS |  | TRA-N-093 | CS Ajdovščina, 2nd phase of upgrade | TRA-N-261 |  | M3/1c Kalce - Vodice
Pipeline including CS |  | TRA-N-093 | CS Ajdovščina, 2nd phase of upgrade | TRA-N-101 |  | M8 Kalce - Jelšane
Pipeline including CS |  | TRA-N-094 | CS Kidričevo, 2nd phase of upgrade | TRA-N-389 |  | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak)
Pipeline including CS |  | TRA-N-094 | CS Kidričevo, 2nd phase of upgrade | TRA-N-390 |  | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec)
Pipeline including CS |  | TRA-N-636 | Development of Transmission Capacity at Slovak-Hungarian interconnector | TRA-N-524 |  | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector
Pipeline including CS |  | TRA-N-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT Corridor) | TRA-N-362 |  | Development on the Romanian territory of the Southern Transmission Corridor
Pipeline including CS |  | TRA-N-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT Corridor) | TRA-F-029 |  | Romania-Bulgaria Interconnection (EEPR-2009-INTg-RO-BG)
Pipeline including CS |  | TRA-N-362 | Development on the Romanian territory of the Southern Transmission Corridor | TRA-N-358 |  | Development on the Romanian territory of the NTS (BG–RO-HU-AT Corridor)
Pipeline including CS |  | TRA-N-656 | Eastring - Hungary | TRA-N-018 |  | Városföld-Ercsi-Győr
Pipeline including CS |  | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | TRA-N-636 |  | Development of Transmission Capacity at Slovak-Hungarian interconnector
Pipeline including CS |  | TRA-N-061 | Ercsi-Szazhalombatta | TRA-N-123 |  | Városföld CS
Pipeline including CS |  | TRA-N-061 | Ercsi-Szazhalombatta | TRA-N-018 |  | Városföld-Ercsi-Győr
Pipeline including CS |  | TRA-F-768 | Extension Receiving Terminal Greifswald | TRA-F-291 |  | NOWAL - Nord West Anbindungsleitung
Pipeline including CS |  | TRA-F-391 | Gascogne-Midi : adaptation of stations in Cruzy and St Martin | TRA-F-43 |  | Val de Saône project
Pipeline including CS |  | TRA-N-394 | Gassled - Danish upstream system | TRA-N-428 |  | (Mirror) Baltic Pipe
Pipeline including CS |  | TRA-N-394 | Gassled - Danish upstream system | TRA-N-780 |  | Nybro-Interconnector PL-DK - reinforcement
Pipeline including CS |  | TRA-N-950 | Guitiriz - Zamora pipeline | LNG-N-295 |  | Mugardos LNG Terminal: Send-out Increase
Pipeline including CS |  | TRA-F-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Rogatec) | TRA-N-1057 |  | Compressor stations 2 and 3 at the Croatian gas tranmission system
Pipeline including CS |  | TRA-N-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | TRA-N-068 |  | Ionian Adriatic Pipeline
Pipeline including CS |  | TRA-N-139 | Interconnection of the NTS with the DTS and reverse flow at Isaccea | TRA-N-959 |  | Further enlargement of the BG—RO—HU—AT transmission corridor (BRUA) phase 3
Pipeline including CS |  | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | TRA-N-1057 |  | Compressor stations 2 and 3 at the Croatian gas tranmission system
Pipeline including CS |  | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | TRA-N-90 |  | LNG evacuation pipeline Omišalj - Zlobin (Croatia)
Pipeline including CS |  | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | TRA-N-075 |  | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac
Pipeline including CS |  | TRA-N-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | TRA-N-1058 |  | LNG Evacuation Pipeline Kozarac-Slobodnica
Pipeline including CS |  | TRA-N-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | TRA-N-075 |  | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac
Pipeline including CS |  | TRA-N-075 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | TRA-N-1058 |  | LNG Evacuation Pipeline Kozarac-Slobodnica
Pipeline including CS |  | TRA-N-075 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | TRA-N-90 |  | LNG evacuation pipeline Omišalj - Zlobin (Croatia)
LNG Terminal |  | LNG-N-062 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | TRA-N-063 |  | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section
Pipeline including CS |  | TRA-N-063 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | LNG-N-062 |  | LNG terminal in northern Greece / Alexandroupolis - LNG Section
Pipeline including CS |  | TRA-N-592 | Looping CS Valchi Dol - Line valve Novi Iskar | TRA-N-594 |  | Construction of a Looping CS Provadia – Rupcha village
Pipeline including CS |  | TRA-N-592 | Looping CS Valchi Dol - Line valve Novi Iskar | TRA-F-057 |  | Interconnection Bulgaria–Romania
Pipeline including CS |  | TRA-N-592 | Looping CS Valchi Dol - Line valve Novi Iskar | UGS-N-138 |  | UGS Chiren Expansion
Pipeline including CS |  | TRA-N-592 | Looping CS Valchi Dol - Line valve Novi Iskar | TRA-N-593 |  | Varna-Oryahovo gas pipeline
Pipeline including CS |  | TRA-N-099 | M3/1a Šempeter - Ajdovščina | TRA-N-093 |  | CS Ajdovščina, 2nd phase of upgrade
Pipeline including CS |  | TRA-N-099 | M3/1a Šempeter - Ajdovščina | TRA-N-262 |  | M3/1b Ajdovščina - Kalce
Pipeline including CS |  | TRA-N-099 | M3/1a Šempeter - Ajdovščina | TRA-N-261 |  | M3/1c Kalce - Vodice
Pipeline including CS |  | TRA-N-099 | M3/1a Šempeter - Ajdovščina | TRA-N-101 |  | M8 Kalce - Jelšane
Pipeline including CS |  | TRA-N-262 | M3/1b Ajdovščina - Kalce | TRA-N-093 |  | CS Ajdovščina, 2nd phase of upgrade
Pipeline including CS |  | TRA-N-262 | M3/1b Ajdovščina - Kalce | TRA-N-099 |  | M3/1a Šempeter - Ajdovščina
Pipeline including CS |  | TRA-N-262 | M3/1b Ajdovščina - Kalce | TRA-N-261 |  | M3/1c Kalce - Vodice
Pipeline including CS |  | TRA-N-262 | M3/1b Ajdovščina - Kalce | TRA-N-101 |  | M8 Kalce - Jelšane
Pipeline including CS |  | TRA-N-261 | M3/1c Kalce - Vodice | TRA-N-093 |  | CS Ajdovščina, 2nd phase of upgrade
Pipeline including CS |  | TRA-N-261 | M3/1c Kalce - Vodice | TRA-N-099 |  | M3/1a Šempeter - Ajdovščina
Pipeline including CS |  | TRA-N-261 | M3/1c Kalce - Vodice | TRA-N-262 |  | M3/1b Ajdovščina - Kalce
Pipeline including CS |  | TRA-N-261 | M3/1c Kalce - Vodice | TRA-N-101 |  | M8 Kalce - Jelšane
Pipeline including CS |  | TRA-N-365 | M6 Ajdovščina – Lucija | TRA-N-107 |  | M6 Interconnection Osp
Pipeline including CS |  | TRA-N-365 | M6 Ajdovščina – Lucija | TRA-N-114 |  | R61 Dragonja - Izola
LNG Terminal |  | LNG-N-296 | Mugardos LNG Terminal: 2nd Jetty | LNG-N-297 |  | Mugardos LNG Terminal: Storage Extension
Pipeline including CS |  | TRA-N-245 | North - South Gas Corridor in Eastern Poland | TRA-N-212 |  | Gas Interconnection Poland-Lithuania (GIPL) - PL section
Pipeline including CS |  | TRA-N-245 | North - South Gas Corridor in Eastern Poland | TRA-N-275 |  | Poland - Slovakia interconnection (PL section)
Pipeline including CS |  | TRA-N-245 | North - South Gas Corridor in Eastern Poland | TRA-N-621 |  | Poland - Ukraine Gas interconnection (PL section)
Pipeline including CS |  | TRA-N-247 | North - South Gas Corridor in Western Poland | TRA-N-273 |  | Poland - Czech Republic interconnection (PL section)
Pipeline including CS |  | TRA-N-247 | North - South Gas Corridor in Western Poland | TRA-N-275 |  | Poland - Slovakia interconnection (PL section)
Pipeline including CS |  | TRA-F-291 | NOWAL - Nord West Anbindungsleitung | TRA-F-768 |  | Extension Receiving Terminal Greifswald
Pipeline including CS |  | TRA-N-780 | Nybro-Interconnector PL-DK - reinforcement | TRA-N-428 |  | (Mirror) Baltic Pipe
Pipeline including CS |  | TRA-N-780 | Nybro-Interconnector PL-DK - reinforcement | TRA-N-394 |  | Gassled - Danish upstream system
Pipeline including CS |  | TRA-N-027 | Physical reverse flow from NI to GB and IE via SNIP pipeline | UGS-N-294 |  | Islandmagee Gas Storage Facility
Pipeline including CS |  | TRA-N-273 | Poland - Czech Republic interconnection (PL section) | TRA-N-247 |  | North - South Gas Corridor in Western Poland
Pipeline including CS |  | TRA-N-275 | Poland - Slovakia interconnection (PL section) | TRA-N-245 |  | North - South Gas Corridor in Eastern Poland
Pipeline including CS |  | TRA-N-275 | Poland - Slovakia interconnection (PL section) | TRA-N-247 |  | North - South Gas Corridor in Western Poland
Pipeline including CS |  | TRA-N-010 | Poseidon Pipeline | TRA-N-330 |  | EastMed Pipeline
Pipeline including CS |  | TRA-N-286 | Romanian-Hungarian reverse flow Hungarian section 1st stage | TRA-N-377 |  | Romanian-Hungarian reverse flow Hungarian section 2nd stage
Pipeline including CS |  | TRA-N-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | TRA-N-286 |  | Romanian-Hungarian reverse flow Hungarian section 1st stage
Pipeline including CS |  | TRA-N-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | TRA-N-123 |  | Városföld CS
Pipeline including CS |  | TRA-N-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | TRA-N-018 |  | Városföld-Ercsi-Győr
Pipeline including CS |  | TRA-N-325 | Slovenian-Hungarian interconnector | TRA-N-123 |  | Városföld CS
Pipeline including CS |  | TRA-N-325 | Slovenian-Hungarian interconnector | TRA-N-018 |  | Városföld-Ercsi-Győr
Pipeline including CS |  | TRA-N-1138 | South Caucasus Pipeline Future Expansion - SCPFX | TRA-F-221 |  | TANAP - Trans Anatolian Natural Gas Pipeline Project
Pipeline including CS |  | TRA-N-339 | Trans-Caspian | TRA-N-053 |  | White Stream
Pipeline including CS |  | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak) | TRA-N-094 |  | CS Kidričevo, 2nd phase of upgrade
Pipeline including CS |  | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak) | TRA-N-390 |  | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec)
Pipeline including CS |  | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | TRA-N-094 |  | CS Kidričevo, 2nd phase of upgrade
Pipeline including CS |  | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | TRA-N-389 |  | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak)
Pipeline including CS |  | TRA-F-43 | Val de Saône project | TRA-F-391 |  | Gascogne-Midi : adaptation of stations in Cruzy and St Martin
Pipeline including CS |  | TRA-F-43 | Val de Saône project | TRA-F-45 |  | Reverse capacity from CH to FR at Oltingue
Pipeline including CS |  | TRA-F-43 | Val de Saône project | TRA-N-047 |  | Reverse capacity from France to Germany at Obergailbach
Pipeline including CS |  | TRA-N-123 | Városföld CS | TRA-N-286 |  | Romanian-Hungarian reverse flow Hungarian section 1st stage
Pipeline including CS |  | TRA-N-123 | Városföld CS | TRA-N-018 |  | Városföld-Ercsi-Győr
Pipeline including CS |  | TRA-N-018 | Városföld-Ercsi-Győr | TRA-N-286 |  | Romanian-Hungarian reverse flow Hungarian section 1st stage
Pipeline including CS |  | TRA-N-018 | Városföld-Ercsi-Győr | TRA-N-377 |  | Romanian-Hungarian reverse flow Hungarian section 2nd stage
Pipeline including CS |  | TRA-N-018 | Városföld-Ercsi-Győr | TRA-N-123 |  | Városföld CS
Pipeline including CS |  | TRA-N-340 | VDS Wertingen | TRA-F-241 |  | MONACO section phase I (Burghausen-Finsing)
Pipeline including CS |  | TRA-N-831 | Vecsés-Városföld gas transit pipeline | TRA-N-524 |  | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector
Pipeline including CS |  | TRA-N-053 | White Stream | TRA-N-339 |  | Trans-Caspian